## Cover sheet 1
Vendor: |  |  |  | Contractor: |  | Owner/Purchaser:
Inspection and Test Plan (ITP)
Vendor’s Doc. No.:
Inspection and Test Plan (ITP) Sample for Heatexchanger
DE |  | EXT
Eng. Phase |  | Purpose Of Distribution (POD) |  | Purpose Of Issue (POI)
Rev. | Date | Description | Prepared by |  | Checked by | Approved by
SAMPLE

## 1
|  | INSPECTION AND TEST PLAN | [5 empty] | DOC. NO :
CUSTOMER : |  |  | PROJECT : |  |  |  |  | PAGE: of | REV.: 00
PO. NO. : |  |  | ITEM NO. : |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
NOTE:
1. Description of Inspection Points
HOLD POINT (HP) |  | The designated feature shall to be witnessed by OWNER INSPECTOR. Vendor/manufacturer is to notify Project quality coordinator two weeks prior to performing the designated feature. Activities do not proceed until the continuation of work is permitted by Project Quality coordinator or waived in writing by him (“inspection waiver”).
WITNESS POINT (WP) |  | The designated feature is to be witnessed by OWNER INSPECTOR. Vendor/manufacturer is to notify Project quality coordinator two weeks prior to performing the designated feature. If the INSPECTOR fails to be present, activities may proceed without witnessing or waiving of the inspection as will be decided by Project quality coordinator.
RANDOM INSPECTION (RI) |  | The inspection of the designated feature will take place during inspection visits as a standard performance. Vendor/manufacturer does not have to notify Project quality coordinator prior to performing the designated feature. Activities may proceed without witnessing or waiving by Project quality coordinator
REVIEW DOCUMENTATION (RD/RA) |  | Documentation will be reviewed/approved by Project Engineering team or INSPECTOR depend the nature of documents (refer to RFD form in order to find that documents which shall be reviewed & approved by Project engineering team and/or inspector).
2. Abbreviations
FPA |  | FARNIKAN PARS AVIN COMPANY
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE

## 2
|  | INSPECTION AND TEST PLAN | [5 empty] | DOC. NO.:
CUSTOMER: |  |  | PROJECT : |  |  |  |  | PAGE: of | REV.:
PO. NO.: |  |  | ITEM NO.: |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
1 | Before Fabrication
1-1 | Review & Approval of Documents | - Drawing |  |  |  | Vendor Print Index & Schedule | HP |  | -
- Strength Calculation
- Inspection & Test Plan
|  | - Welding Procedure |  | Vendor Print Index & Schedule
|  | (WPS,PQR,Welding Map & NDT Map) |  | ASME Sec. V
|  | - Welders Performance Qualification |  | ASME Sec. VIII. Div.1
|  | - PWHT Procedure (if Any) |  | ASME Sec. IX
|  | -Hydrostatic Test Procedure |  | Project Specification
-Painting Procedure
-Packing, Marking And Shipping Procedure
- NDT Procedure, …
1-2 | Pre-Inspection Meeting (PIM) | Pre-Inspection Meeting (PIM) |  | PO NO : Pre-Inspection Meeting Agenda |  | Minutes of Meeting | HP
2 | Material Inspection & Components
2-1 | Material Receiving Inspection of Pressure Retaining Parts (Plate, Flange, Pipe,…) | - Check of Material Test Certificate(MTC) |  | ASME Sect. II | ASME Sect. II Part A | Material Indentification Report | HP
a. Confirmation of Heat No.
|  | c. Mechanical properties |  | MTC | Certificate Type : EN10204 Type 3.1
|  | d. Other tests |  | Fabrication Drawings
(NDE, Simulation Impact, etc.- if any)
2-2 | Material Identification | - Material Identification |  | ASME Sect. II | ASME Sect. II Part A | Material Indentification Record | HP
|  | - Visual & Dimensional Check of Material |  | MTC/Lab. Result | Certificate Type : EN10204 Type 3.1
|  | - Verify Transfer of Identification |  | Fabrication Drawings
2-3 | Welding Consumable Control | Check of Welding Material |  | WPS & PQR | WPS & PQR | - | HP
|  |  |  | ASME Sec. II, Part C | ASME Sec. II, Part C
2-4 | Inspection of Components | - Visual & Dimensional Inspection of Tube,Tubesheet,Baffle, Forg Disk & Ring,… |  | Fabrication Drawings | Fabrication Drawings | Material Indentification Report | HP
|  |  |  | MTC | MTC
|  |  |  | TEMA | TEMA
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE

## 3
|  | QUALITY CONTROL PLAN (INSPECTION AND TEST PLAN) | [5 empty] | DOC. NO.:
CUSTOMER: |  |  | PROJECT: |  |  |  |  | PAGE: of | REV.: 00
PO. NO.: |  |  | ITEM NO.: |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
3 | Fabrication and Inspection of Shellside
3-1 | Transfer of Material Identification Before Cutting | Visual Inspection |  | ASME Sect. II Fabrication Drawings |  | Material Indentification Record | HP
3-2 | Marking, Cutting, Rolling & Driling of Plate (If Any) | Visual & Dimensional Inspection |  | Fabrication Drawings |  | - | HP
3-3 | Edge Prepartion & Fit up Aligment Check | - For Long. & Circum. Joints - Head to Shell Joint |  | Fabrication Drawings |  | Report | HP
|  | - Nozzle Neck to Flange Joints |  | WPS & PQR
-Visual & Dimensional Inspection
3-4 | Welding Inspection | - Welding of Long. & Circum. Joints |  |  |  | NDT Report | HP
|  | - Welding of Head to Shell Joint |  | Fabrication Drawings
- Welding Nozzle Neck to Flange Joints
|  | - Visual Inspection |  | NDT Procedure
|  | - NDT: Full or Spot RT( Nozzle >= 10") |  | Welding Book (WPS, PQR, Welding Map)
100% PT (If Any)
3-5 | Marking & Cutting of Nozzle Opening | - Check of nozzle marking |  | Fabrication Drawings |  | - | HP
-Dimensional Inspection of Opening
( Elevation/Orientation/ Opening Size)
3-6 | Edge Prepartion & Fit up Aligment Check | - For Nozzle to shell joints |  | Fabrication Drawings |  | Report | HP
|  | -Visual & Dimensional Inspection |  | WPS & PQR
3-7 | Welding Inspection | - Welding of Nozzle to shell joints |  | Fabrication Drawings |  | NDT Report | HP
|  | - Visual Inspection |  | NDT Procedure
|  | - NDT of Weld |  | Welding Book (WPS, PQR, Welding Map)
3-3 | Edge Prepartion & Fit up Aligment Check | - Saddle/Skirt/Lug to shell welds |  | Fabrication Drawings |  | Report | HP
|  | -Visual & Dimensional Inspection |  | WPS & PQR
3-7 | Welding Inspection | - Welding of Saddle/Skirt/Lug to shell |  | Fabrication Drawings |  | NDT Report | HP
|  | - Visual Inspection |  | NDT Procedure
|  | - NDT of Weld |  | Welding Book (WPS, PQR, Welding Map)
3-8 | Final Visual & Dimensional Inspection | -Dimensional inspection: Overall length |  | Fabrication Drawing |  | Report | HP
|  | ID Check,Location of nozzle,… |  | ASME Sec. VIII, Div1, UW-35
|  | Visual for completed surface of internal &external welds,… |  | TEMA Fig. F-1~F-3, Purchase Order
All Vendor Procedure and QC verified test / Inspection reports / records
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE

## 4
|  | INSPECTION AND TEST PLAN | [5 empty] | DOC. NO.:
CUSTOMER: |  |  | PROJECT: |  |  |  |  | PAGE: of | REV.: 00
PO. NO. : |  |  | ITEM NO.: |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
4 | Fabrication and Inspection of Channel
4-1 | Transfer of Material Identification Before Cutting | Visual Inspection |  | ASME Sect. II Fabrication Drawings |  | Material Indentification Record | HP
4-2 | Marking, Cutting & Rolling of Plate | Visual & Dimensional Inspection |  | Fabrication Drawings |  | - | HP
4-3 | Edge Prepartion & Fit up Aligment Check | - For Long. & Circum. Joints- Head to Channel |  | Fabrication Drawings |  | Report | HP
|  | - Nozzle Neck to Flange Joints |  | WPS & PQR
-Visual & Dimensional Inspection
|  | - Welding of Long. & Circum. Joints |  |  |  | NDT Report | HP
4-4 | Welding Inspection | - Welding of Head to Channel Joints |  | Fabrication Drawings
- Welding Nozzle Neck to Flange Joints
|  | - Visual Inspection |  | NDT Procedure
|  | - NDT: Full or Spot RT( Nozzle >= 10") |  | Welding Book (WPS, PQR, Welding Map)
100% PT (If Any)
4-5 | Marking & Cutting of Nozzle Opening | - Check of nozzle marking |  | Fabrication Drawings |  | - | HP
-Dimensional Inspection of Opening
( Elevation/Orientation/ Opening Size)
4-6 | Edge Prepartion & Fit up Aligment Check | - For Nozzle to channel joints |  | Fabrication Drawings |  | Report | HP
|  | -Visual & Dimensional Inspection |  | WPS & PQR
4-7 | Welding Inspection | - Welding of Nozzle to channel joints |  | Fabrication Drawings |  | NDT Report | HP
|  | - Visual Inspection |  | NDT Procedure
|  | - NDT of Weld |  | Welding Book (WPS, PQR, Welding Map)
4-8 | Final Visual & Dimensional Inspection | -Dimensional inspection: Overall length |  | Fabrication Drawings |  | Report | HP
|  | ID Check,Location of nozzle,… |  | ASME Sec. VIII, Div1, UW-35
|  | Visual for completed surface of internal &external welds,… |  | TEMA Fig. F-1~F-3, Purchase Order
All Vendor Procedure and QC verified test / Inspection reports / records
5 | Fabrication and Inspection of Bundle
5-1 | Tube bundle Assembly | - Visual&dimension of tubesheet &Baffle |  | Fabrication Drawings |  | Report | HP
- Baffle arrangement
- Cleaning of tubesheet hole/tube end
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE

## 5
|  | QUALITY CONTROL PLAN (INSPECTION AND TEST PLAN) | [5 empty] | DOC. NO :
CUSTOMER: |  |  | PROJECT: |  |  |  |  | PAGE: of | REV.: 00
PO. NO. : |  |  | ITEM NO.: |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
5 | Fabrication and Inspection of Bundle
5-2 | Tube Insertion(Insert of tube to bundle) | - Visual Inspection |  | Fabrication Drawings |  | - | HP
5-3 | Welding Inspection (Tube to Tubesheet Joints) | - Welding of tube to tubesheet Joints |  | Fabrication Drawings |  | Report | HP
|  | - Visual Inspection 100% |  | NDT Procedure
|  | - PT on final welds |  | Welding Book (WPS, PQR, Welding Map)
5-4 | Tube Expanding | - Check of Expanded length |  | Fabrication Drawing |  | Report | HP
Tube Expanding Procedure
5-5 | Final Visual & Dimensional Inspection | -Dimensional inspection: Overall length |  |  |  | Report | HP
|  | Baffle distance,… |  | Fabrication Drawings
-Visual for weld / surface of material
5-6 | Bundle Insertion | Insert of bundle to shell |  | Fabrication Drawings |  | - | HP
5-7 | Edge Prepartion, Fit up & Welding of Tubesheet to Shell/Channel | -Visual & Dimensional Inspection |  | Fabrication Drawings |  | Report | HP
|  | - Welding of tubesheet to shell/channel |  | NDT Procedure
|  | - NDT: UT, PT (If Any) |  | Welding Book (WPS, PQR, Welding Map)
6 | Final Inspection
6-1 | Final Visual & Dimensional Inspection |  |  | AS-Built Drawing |  | Report | HP
6-2 | Positive Material Identification (PMI) & Ferrite Check on Weld Alloys |  |  | PMI Procedure | ASME Sec. II Part A & C | Report | HP
6-3 | PWHT for Shell and Channel (if Any) |  |  | PWHT Procedure | ASME Sec. VII, Div.1 | Report | HP
6-4 | Leak test of all reinforcing pad | Test pressure used on reinforcing pad shall be at 0.5 barg. |  | Fabrication Drawing |  | Report | HP
6-5 | Pressure Test (Hydrostatic Test) |  |  | Fabrication Drawings | No Deformation & No leak | Report | HP
ASME Sec. VIII,Div.1
| - 1st Shell Side |  |  | UG-99
| - 2nd Tube Side |  |  | Hydro. Test Procedure
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE

## 6
|  | INSPECTION AND TEST PLAN | [5 empty] | DOC. NO :
CUSTOMER: |  |  | PROJECT: |  |  |  |  | PAGE: of | REV.: 00
PO. NO.: |  |  | ITEM NO.: |  |  | ITEM DESCRIPTION : -
ITEM NO. | QUALITY VERIFICATION ACTIVITY |  |  | REFERENCE PROCEDURE/ DOCUMENT | ACCEPTANCE CRITERIA | VERIFYING DOCUMENTS | INSPECTION POINT
[7 empty] | FPA | OWNER/TPI | Contractor
6 | Final Inspection
6-6 | Picking & Passivation (if Any) |  |  | Picking & Passivation Procedure |  | Report | HP
6-7 | Blasting & Painting Inspection(if Any) |  |  | Project Spec. & Painting Procedure |  | Report | HP
6-8 | Marking / Packing & Shipping | - Final Visual & Dimension Inspection before shipment |  |  |  | Packing List | HP
Packing & Marking Procedure
|  | -Name Plate Check |  | Spare Part List
|  | -Spare Parts Check |  | AS-Built Drawing
|  | - Bolting and gaskets for blind flanges |  | N2 Purging Procedure
- N2 Purging or VCI inspection (if any)
6-7 | Release for Shipment |  |  | - |  | Release Note | HP
6-8 | Manufacturer's Data Book |  |  | Manufacturer's Data Book Index |  | MDB | HP
| LEGEND: | HOLD POINT(HP) |  | WITNESS POINT(WP) | RANDOM INSPECTION(RI) |  | REVIEW DOCUMENTATION(RD/RA)
SAMPLE