## Cover
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index Schedule (VPIS)
|  | Document No. : EI027-DMF-VD-GE-LST-001-R1 |  | Rev.: R1 | Page 1 of 3
STYRENE PARK OFFSITE Document Title: Vendor Print Index Schedule (VPIS)
R1 | 2024-06-10 | Issued For Approval | M.Irani | J.Beigloo | A.Gholizadeh
R0 | 2024-06-01 | Issued For Approval | M.Irani | J.Beigloo | A.Gholizadeh
Rev. | Issued Date | DESCRIPTION | PREPARED | CHECKED | APPROVED

## Index
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index Schedule (VPIS)
|  |  |  | Document No. : EI027-DMF-VD-GE-LST-001-R1 | [8 empty] | Rev.: R1 | Page 2 of 3
Page | Revisions | [6 empty] | Page | Revisions
| R0 | R1 | R2 | R3 | R4 | R5 | R6 |  | R0 | R1 | R2 | R3 | R4 | R5 | R6
1 | [7 empty] | 41 | bar: Revisions R0 to Revisions R1
2 | [7 empty] | 42 | bar: Revisions R0 to Revisions R1
3 | [7 empty] | 43 | bar: Revisions R0 to Revisions R1
4 | [7 empty] | 44
5 | [7 empty] | 45
6 | [7 empty] | 46
7 | [7 empty] | 47
8 | [7 empty] | 48
9 | [7 empty] | 49
10 | [7 empty] | 50
11 | [7 empty] | 51
12 | [7 empty] | 52
13 | [7 empty] | 53
14 | [7 empty] | 54
15 | [7 empty] | 55
16 | [7 empty] | 56
17 | [7 empty] | 57
18 | [7 empty] | 58
19 | [7 empty] | 59
20 | [7 empty] | 60
21 | [7 empty] | 61
22 | [7 empty] | 62
23 | [7 empty] | 63
24 | [7 empty] | 64
25 | [7 empty] | 65
26 | [7 empty] | 66
27 | [7 empty] | 67
28 | [7 empty] | 68
29 | [7 empty] | 69
30 | [7 empty] | 70
31 | [7 empty] | 71
32 | [7 empty] | 72
33 | [7 empty] | 73
34 | [7 empty] | 74
35 | [7 empty] | 75
36 | [7 empty] | 76
37 | [7 empty] | 77
38 | [7 empty] | 78
39 | [7 empty] | 79
40 | [7 empty] | 80

## VPIS
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index Schedule (VPIS)
|  | Document No. : EI027-DMF-VD-GE-LST-001-R1 |  |  | Rev.: R1 |  | Page 3 of 3
[8 empty] | Vendor | Purchaser | Status | Vendor | Purchaser | Status | Vendor | Purchaser | Status | Vendor | Purchaser | Status | Vendor | Purchaser | Status
Row | Document Number |  | Document Title | Planned Issue Date |  | P.O.I |  | Rev. R0 |  |  | Rev. R1 |  |  | Rev. R2 |  |  | Rev. R3 |  |  | Rev. R4
1 | EI027-DMF-VD-GE-LST-001 |  | Vendor Print Index Schedule (VPIS) |  |  | IFA |  | 2.JUN.2024(TR-1) | 8.JUN.2024 | CO
2 | EI027-DMF-VD-ME-DSH-002 |  | Air Cooler Thermal Data Sheet |  |  | IFA
3 | EI027-DMF-VD-ME-DWG-003 |  | General Arrangement Drawing |  |  | IFA
4 | EI027-DMF-VD-ST-CAL-004 |  | Steel Structure Calculation |  |  | IFA
5 | EI027-DMF-VD-ME-DWG-005 |  | Tube Bundle Drawing |  |  | IFA |  | 2.JUN.2024(TR-2)
6 | EI027-DMF-VD-ME-CAL-006 |  | Mechanical Calculation |  |  | IFA |  | 2.JUN.2024(TR-2)
7 | EI027-DMF-VD-ME-DWG-007 |  | Bundle Frame Drawing |  |  | IFA
8 | EI027-DMF-VD-ME-DWG-008 |  | Fan Drive Assembly Drawing |  |  | IFA
9 | EI027-DMF-VD-ME-DWG-009 |  | Fan Ring Drawing |  |  | IFA
10 | EI027-DMF-VD-ME-DWG-010 |  | Support Mechanism Drawing |  |  | IFA
11 | EI027-DMF-VD-ME-DWG-011 |  | Plenum Drawing |  |  | IFA
12 | EI027-DMF-VD-ME-DWG-012 |  | Name Plate Drawing |  |  | IFA
13 | EI027-DMF-VD-ST-DWG-013 |  | Steel Structure Drawing |  |  | IFA
14 | EI027-DMF-VD-ST-DWG-014 |  | Header Walkway Drawing |  |  | IFA
15 | EI027-DMF-VD-ST-DWG-015 |  | Ladder Drawing |  |  | IFA
16 | EI027-DMF-VD-ME-DSH-016 |  | Axial Fan Data Sheet |  |  | IFA
17 | EI027-DMF-VD-EL-DSH-017 |  | Electrical Motor Data Sheet |  |  | IFA
18 | EI027-DMF-VD-ME-DSH-018 |  | Belt & Pulley Data Sheet |  |  | IFA
19 | EI027-DMF-VD-IN-DSH-019 |  | Vibration Switch Data Sheet |  |  | IFA
20 | EI027-DMF-VD-EL-LST-020 |  | Electrical Load List |  |  | IFA
21 | EI027-DMF-VD-QC-ITP-021 |  | Inspection Test Plan (ITP) |  |  | IFA
22 | EI027-DMF-VD-QC-WPS-022 |  | WPS & PQR for Pressure Part and Structure Part |  |  | IFA
23 | EI027-DMF-VD-QC-PRO-023 |  | NDT Procedure & Weld Map |  |  | IFA
24 | EI027-DMF-VD-QC-PRO-024 |  | Surface Blasting & Painting & Galvanizing Specification and InspectionProcedure |  |  | IFA
25 | EI027-DMF-VD-QC-PRO-025 |  | PWHT Procedure |  |  | IFA
26 | EI027-DMF-VD-QC-PRO-026 |  | Tube Expanding Procedure |  |  | IFA
27 | EI027-DMF-VD-QC-PRO-027 |  | Packing & Marking Procedure |  |  | IFA
28 | EI027-DMF-VD-QC-PRO-028 |  | Hydrostatic Test Procedure |  |  | IFA
29 | EI027-DMF-VD-QC-PRO-029 |  | N2 Purging Procedure |  |  | IFA
30 | EI027-DMF-VD-QC-CRT-030 |  | Welder Qualification Test Certificate |  |  | IFA
31 | EI027-DMF-VD-QC-PRO-031 |  | Shop Run Test Procedure |  |  | IFA
32 | EI027-DMF-VD-ME-MNL-032 |  | Installation , Operation & Maintanence (Manual) |  |  | IFA
33 | EI027-DMF-VD-ME-LST-033 |  | Commissioning Spare Part List |  |  | IFA
34 | EI027-DMF-VD-ME-LST-034 |  | 2-Years Spare Part List |  |  | IFA
35 | EI027-DMF-VD-ME-LST-035 |  | Special Tools List |  |  | IFA
36 | EI027-DMF-VD-GE-LST-036 |  | Sub Vendor List |  |  | IFA
37 | EI027-DMF-VD-GE-SCH-037 |  | Time Schedule |  |  | IFA
38 | EI027-DMF-VD-GE-LST-038 |  | Final Data Book Index |  |  | IFA
39 | EI027-DMF-VD-GE-FDB-039 |  | Final Data Book |  |  | IFA
40 | EI027-DMF-VD-ME-LUC-040 |  | Lubricant Chart |  |  | IFA