## REPLY SHEET
CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Comment / Reply Sheet
Comment / Reply Sheet No.: |  | EI027-DMF-VD-ME-DWG-003-R2 |  | Document Description: |  | General Arrangement Drawing
Reply Sheet Date: |  | 2024-08-21 |  | Document No.: |  | EI027-DMF-VD-ME-DWG-003
Transmittal No.: |  | EI027-DMF-TR-0031 |  | Document Revision: |  | R2
Item No. | Comments |  |  |  | Vendor Clarifications
1 | Repetitive comment: Please show the raise of flange, and set the dimension with it. |  |  |  | repeted reply: comment is not clear. the dim lines are set from raised face of flang. It could be checked in native file
2 | On page 3/10 of fan data sheet , fan ring diameter is 2156. on page 4/10 of fan data sheet, fan ring diameter is 2155. please remove the discrepancy and clear it. All related documents to be matched. |  |  |  | It was already explained that the construction process is based on the final engineering drawings. What is in the datasheet is completely approximate. The engineering drawings are completely compatible.
3 | Please add a sketch for lifting the bundle. |  |  |  | lifting will be specified in bundle frame drawing.
4 | Please specify and show the support of cable tray for vibration switch. |  |  |  | Out of scope.It is not mentioned in any part of clarification and MR that the determination of the cable route is the responsibility of Demafin, therefore, the related documents are not included in the VPIS.
Legend of Document Status:
CO: Commented |  |  | AN: Approved as Noted
AP: Approved |  |  | RE : Rejected
NDEC
NDEC