## REPLY SHEET
CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Comment / Reply Sheet
Comment / Reply Sheet No.: |  | EI027-DMF-VD-ME-DWG-005-R1 |  | Document Description: |  | Tube Bundle Drawing
Reply Sheet Date: |  | 2024-07-22 |  | Document No.: |  | EI027-DMF-VD-ME-DWG-005
Transmittal No.: |  | TR-013 |  | Document Revision: |  | R1
Item No. | Comments |  |  |  | Vendor Clarifications
1 | AS PER API MIN & MAX TORQUE TO BE SPECIFIED ALSO. |  |  |  | The plugs are installed by means of a controlled torque wrench.air-cooled heat exchanger standards API 661 do not provide recommended tightening torque values for the plugs. It should be noted that 80 Kgm of force is required to firmly close the plug together with the soft iron gasket.
2 | Please remove the groove. Tube to tube sheet joint to be strength weld only. |  |  |  | Groove should be used to increase the confidence factor.
Legend of Document Status:
CO: Commented |  |  | AN: Approved as Noted
AP: Approved |  |  | RE : Rejected
6
NDEC
NDEC