## Sheet1
TOTAL BUDGET |  | TOTAL INPUT |  | TOTAL OUTPUT |  | TOTAL OBLIGATION |  | REMAINING OBLIGATION |  | REMAINING BUDGET |  | CASH FLOW
1250000 |  | 1250000 |  | 545243.1 |  | 572593.1 |  | 27350 |  | 704756.9 |  | 677406.9
ITEM | Amount | DATE
ADV PAY | 325000 | 2024-01-24
2nd ADV PAY | 300000 | 2024-02-20
2nd PAY | 250000 | 2024-12-30
3rd PAY | 62500
4th PAY | 312500
5th PAY
ITEM | VENDOR | PO NUMBER/Order Confirmation | QTY | PRICE NOT EURO | TOTAL PRICE | BALANCE PAY | %ADV PAY | ADV OR FULL | EXTRA | ADV DATE | %2ND | 2ND PAY | 2ND PAY DATE | %3RD | 3RD PAY | 3D PAY DATE | %4TH | 4TH PAY | 4TH PAY DATE | PURCHASER | Remark
Compressor Skid | MYCOM | ENER-MME-2024-100-002 | 2 |  | 143050 | 0 | 40% | 56000 |  | 2024-03-04 | 60% | 87050 | 2025-01-16 | [6 empty] | ENER TEK | 3050 added for shipping
Motors | HELMKE | DELTA-HELMKE-2024- PO-200 | 4 | 714 add for shipping | 25882.5 | 0 | 50% | 12584.25 |  | 2024-06-05 | 50% | 12584.25 | 2024-09-04 | Shipping | 714 | 2024-09-24 |  |  |  |  | VAT included
LG | Klinger | DELTA-KLINGER-2024- PO-200 | 2 |  | 5119.38 | 0 | 100% | 5119.38 |  | 2024-09-27 | [10 empty] | VAT included
Oil Heater | FATI | DELTA-FATI-2024-PO-200 | 2 |  | 1018.5 | 0 | 50% | 509.25 |  | 2024-07-22 | 50% | 509.25 | 2024-11-25
Condenser | DAMAFIN | ENER-DMF-2024-100-003 | 2 |  | 92000 | 0 | 25% | 20500 |  | 2024-06-05 |  | 30500 |  |  | 20000 | 2025-03-08 |  | 21000
Chiller | Farnikan | Delta-Farnikan-2024-PO-200 | 2 |  | 48000 | 24000 | 50% | 24000 |  | 2024-07-30
Filter Dryer | MYCOM | ENP-MME-2024-PO-200-01 | 1 |  | 4481.05 | 0 | 100% | 4481.05 |  | 2025-01-16
PLC Software | SIMON | DELTA-PLCSV-2024-PO-200 | - |  | 9310 | 0 | 100% | 9310 |  | 2025-05-31
Control Valve | VSI | DELTA-PETROL VALVES-2024-PO-200 | 2 |  | 5972 | 0 | 50% | 2986 |  | 2024-09-01 | 50% | 2986 | 2025-01-13
Safety Valve | Technical | DELTA-TECHNICAL-2024-PO-200 | 4 |  | 4690 | 0 | 30% | 1407 |  | 2024-09-26 | 70% | 3283 | 2025-01-13
Ball valve | Alzerwa | ENP-ALZERWA-2024-PO-200-02 |  | 40110 AED | 10000 | 0 | 100% | 10000 |  | 2024-10-31
FCV | Barthel | DELTA-BARTHEL-2024-PO-200 | 4 |  | 767.55 | 0 | 100% | 767.55 |  | 2024-08-19 | [10 empty] | VAT included
SLV | MYCOM | DELTA-MME-2024-PO-200-01 | 12 |  | 15000 | 0 | 100% | 15000 |  | 2025-01-16
PIT,PG,TIT,POT | WIKA | DELTA-WIKA-2024-PO-200 | 22 |  | 37893.88 | 0 | 100% | 37893.88 |  | 2025-01-06 | [10 empty] | VAT included
GLV, SG, Stainers | Metallum | DELTA-METALLUM-2024-PO-200 | 18 | 7452 USD | 6863 | 0 | 100% | 6863 |  | 2025-09-05
LIT and LS | WIKA | DELTA-WIKA-2024-PO-200-A1 | 4 |  | 14153.69 | 0 | 100% | 14153.69 | 2nd | 2024-04-11
Needle Valves | Alzerwa | EN-ALZERWA-2024-PO-200-01 | 8 | 840 AED | 210 | 0 | 100% | 210 |  | 2024-10-05
Manifold Valve | Alzerwa | EN-ALZERWA-2024-PO-200-01 | 14 | 3381 AED | 868 | 0 | 100% | 868 |  | 2024-11-13
JB&LCP | Cortem | ENP-CORTEM-2024-PO-200 | 8+2 | 42230 AED | 10300 | 0 | 50% | 5150 |  | 2024-11-05 | 50% | 5150 | 2025-01-31
Ejector | Wijbenga | DELTA-WIJBENGA-2024-PO-200 | 2 |  | 667 | 0 | 100% | 667 |  | 2024-11-28
Engineering | MYCOM | ENER-MME-2024-PO-100-001 |  |  | 48000 | 0 | 50% | 24000 |  | 2024-03-11 | 50% | 24000 | 2025-01-16
Cable | Forelind | DELTA-FORELIND-2024-PO-178 |  |  |  | 0
Chiller skid structure | Arkan Sanat | DELTA-ARKAN-2024-PO-200-1 |  |  | 9000 | 0 | 75% | 6000 |  |  |  | 3000 | 2025-07-09
Receiver Header | Arkan Sanat | DELTA-ARKAN-2024-PO-200 |  | 3300 $ paid | 6016 | 0 | 50% | 3000 |  |  |  | 3016 | 2025-07-09 | [7 empty] | 3300 $ paid
Flange | Petro Sanat Adel | - | 242 | 2340574060 | 2785 | 0 | 45% | 1253 |  | 2024-12-18 | 2nd% | 1532 | 2025-03-12
Fitting | Foolad Asa | - | 185 | 4451458000 | 5564 | 0 | 40% | 2500 |  | 2024-12-18 |  | 3064 | 2024-02-09
Gasket | Behta | - | 176 | 392038900 | 500 | 0 | 100% | 500 |  | 2024-12-29
Bolt / Nut | PMS | - | 1290 | 1781098440 | 2120 | 0 | 50% | 848 |  | 2024-12-31 |  | 1272 | 2025-02-26
Tubing material | Pars regulator | - |  | 1073490000 | 1278 | 0 | 100% | 1278 | 2nd | 2024-01-01
cable | Moghan | - | 2000 | 2146196703 | 2543 | 0 | 70% | 1618 | 2nd | 2024-01-04 |  | 925 | 2025-05-05 | [7 empty] | 135.955.680 Tomans Paid
Pipe | AFGH | - | 156 | 1783694000 | 2215 | 0 | 90% | 1890 |  | 2025-01-06 |  | 325 | 2025-01-20
Gland | Electromec- CMP | EN-ELECTOMEC-2024-PO-200 | 95 | 2620.20 AED | 655 | 0 | 100% | 655 |  | 2024-12-25
Johnny | Jen-Joh |  |  |  | 4987.55 | 0 |  | 4987.55 |  | 2024-12-31
Teflon PTFE | AFGH |  |  | 538725000 | 560 | 0 | 100% | 560 |  | 2025-02-15
instrumentation work for compressor | NASH | ENER-NASH-2025-PO-200 |  | 19470 USD | 18614 | 0 | 25% | 4653.5 |  | 2025-04-03 | 25% | 4653.5 | 2025-05-28 | 40% | 7445.6 | 2025-07-03 | 10% | 1861.4 | 2025-07-03
Air freight for LG and CV to Iran | AMD |  |  |  | 2000 | 0 | 100% | 2000 |  | 2025-02-19
Shipment alzerwa ball valves to Iran | AMD |  |  | 700 USD | 669 | 0 | 100% | 669 |  | 2025-02-19 | [10 empty] | 700 USD paid Cash
Fitting Instrumentation | HYLOK-AMAN |  |  | 19849.86 AED | 5166 | 0 | 100% | 5166 |  | 2025-02-18
PLC | PHE | EN-PHE-2025-PO-200 |  |  | 16000 | 0 | 50% | 8000 |  | 2025-03-05 |  | 8000 | 2025-07-09
Tubing remain items | VALVE TECHNICAL | EN-VALVETECHNICAL-2025-PO-200 |  | 3223.93 AED | 806 | 0 | 100% | 806 |  | 2025-03-01
Shipment Hy-Lok Korea to Nash | JBC |  |  | 1680 AED | 404 | 0 | 100% | 404 |  | 2025-05-14
Shipment Fati to Nash | JBC |  |  | 895 AED | 215 | 0 | 100% | 215 |  | 2025-05-14
Shipment Germany to Nash | JBC |  |  | 4200 AED | 1010 | 0 | 100% | 1010 |  | 2025-05-14
Shipment Cortem to Nash | JBC |  |  | 200 AED | 48 | 0 | 100% | 48
Shipment valve technical to Nash | JBC |  |  | 157.50 AED | 38 | 0 | 100% | 38
Fitting shortage | AFGH |  |  | 309760000 | 333 | 0 | 100% | 333 |  | 2025-05-20
Packing and Tarpaulin | SAS | EN-SAS-2025-PO-200 |  | 2388.75 AED | 560 | 0 | 100% | 560 |  | 2025-07-07
Shipping of Compressor Skid | AMD |  |  | 3920 USD | 3350 | 3350
Cable Tray | Ajineh |  |  | 852500000 | 910 | 0 | 70% | 583 |  | 2025-05-13 | 30% | 327 | 2025-06-30
TOTAL | - | - |  |  | 572593.1 | 27350 |  | 302045.1 | 0 |  |  | 192177 |  |  | 28159.6 |  |  | 22861.4