## Sheet1
|  |  |  | VENDOR PRINT INDEX & SCHEDULE |  |  |  | PURCHASER
VENDOR
|  |  |  | Document No.: DPIC9812-000-VD-1002-ME-MDR-0001 |  |  |  | LEGEND OF REVIEW CODE
CODE1 - AP: Approved
PJT NAME |  | DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT |  |  | ISSUE DATE | 2022-02-05 |  | CODE2 - AN: Approved with Minor Comments
P/O NO. |  | DPIC-PO-NEC-299-1002 |  |  | JOB NO.: N-299 |  |  | CODE3 - NF: Approved with Comments
EQUIPMENT |  | REFRIGERATION PACKAGE |  |  | REQUISITION NO. | DPIC98-12-001-000-ME-MR-4150-0001-D1 |  | CODE4 - RJ: Rejected
NAME | [7 empty] | CODE5 - NR : Not Returned
S/R NO | Vendor Doc No. |  | Document Title |  |  | Doc. Category | Forecast Date |  | REMARKS
Purchaser Doc No.
1 | DPIC9812-000-VD-1002-ME-MDR-0001 |  | Vendor Print Index & Schedule (VPIS) |  |  | ENG | 2021-09-18
DPIC9812-000-VD-1002-ME-MDR-0001
2 | DPIC9812-000-VD-1002-ME-PLN-0002 |  | Time Schedule |  |  | GEN | 2021-09-30
DPIC9812-000-VD-1002-ME-PLN-0002
3 | DPIC9812-000-VD-1002-ME-LST-0003 |  | Work Break Down Structure (WBS) |  |  | ENG | 2021-10-01
DPIC9812-000-VD-1002-ME-LST-0003
4 | DPIC9812-000-VD-1002-ME-RP-0004 |  | Project Monthly Report for Refrigeration Package |  |  | GEN | Each Month
DPIC9812-000-VD-1002-ME-RP-0004
5 | DPIC9812-000-VD-1002-ME-LST-0005 |  | Sub Vendor List |  |  | ENG | 2021-09-20
DPIC9812-000-VD-1002-ME-LST-0005
6 | DPIC9812-000-VD-1002-ME-LST-0006 |  | Final Data Book Index |  |  | ENG/INS | 2022-11-30
DPIC9812-000-VD-1002-ME-LST-0006
7 | DPIC9812-000-VD-1002-ME-VDB-0007 |  | Final Data Book |  |  | INS | End of the Project
DPIC9812-000-VD-1002-ME-VDB-0007
8 | DPIC9812-000-VD-1002-ME-ITP-0008 |  | Inspection & Test Plan (ITP) for Refrigeration Unit (PK-6101) |  |  | ENG/INS | 2021-09-30
DPIC9812-000-VD-1002-ME-ITP-0008
9 | DPIC9812-000-VD-1002-ME-ITP-0009 |  | Inspection and Test Plan for Compressor |  |  | ENG/INS | 2021-10-20
DPIC9812-000-VD-1002-ME-ITP-0009
10 | DPIC9812-000-VD-1002-ME-PID-0010 |  | Piping and Instrument Diagram (PID) |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-PID-0010
11 | DPIC9812-000-VD-1002-ME-PFD-0011 |  | Process Flow Diagram |  |  | ENG | 2021-09-20
DPIC9812-000-VD-1002-ME-PFD-0011
12 | DPIC9812-000-VD-1002-ME-GAD-0012 |  | General Arrangement Drawing (Including Loads, Displacement, and Maintenance Info.) |  |  | ENG | 2021-11-01
DPIC9812-000-VD-1002-ME-GAD-0012
13 | DPIC9812-000-VD-1002-ME-DWG-0013 |  | Compressor Drawing |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-DWG-0013
14 | DPIC9812-000-VD-1002-ME-DWG-0014 |  | Main Motor Drawing |  |  | ENG | 2021-10-20
DPIC9812-000-VD-1002-ME-DWG-0014
15 | DPIC9812-000-VD-1002-ME-DWG-0015 |  | Outline Dimensional Drawings (Cabinets Arrangement) |  |  | ENG | 2022-04-30
DPIC9812-000-VD-1002-ME-DWG-0015
16 | DPIC9812-000-VD-1002-ME-DWG-0016 |  | Oil Filter Drawing (F-PK-6101-1A/2A, F-PK-6101-1B/2B) |  |  | ENG | 2021-11-10
DPIC9812-000-VD-1002-ME-DWG-0016
17 | DPIC9812-000-VD-1002-ME-DWG-0017 |  | Oil Cooler Drawing (E-PK6101-1A/B) |  |  | ENG | 2021-11-11
DPIC9812-000-VD-1002-ME-DWG-0017
18 | DPIC9812-000-VD-1002-ME-DWG-0018 |  | Oil Pump Drawing |  |  | ENG | 2021-11-12
DPIC9812-000-VD-1002-ME-DWG-0018
19 | DPIC9812-000-VD-1002-ME-DWG-0019 |  | Oil Separator Drawing |  |  | ENG | 2021-11-13
DPIC9812-000-VD-1002-ME-DWG-0019
20 | DPIC9812-000-VD-1002-ME-DWG-0020 |  | Condenser Drawing (E-PK6101-2) |  |  | ENG | 2021-11-14
DPIC9812-000-VD-1002-ME-DWG-0020
21 | DPIC9812-000-VD-1002-ME-DWG-0021 |  | Liquid Receiver Drawing (D-PK6101-2) |  |  | ENG | 2021-11-15
DPIC9812-000-VD-1002-ME-DWG-0021
22 | DPIC9812-000-VD-1002-ME-DWG-0022 |  | K/O Drum Drawing (D-PK6101-3) |  |  | ENG | 2021-11-16
DPIC9812-000-VD-1002-ME-DWG-0022
23 | DPIC9812-000-VD-1002-ME-DWG-0023 |  | Economizer Drawing (E-PK6101-3) |  |  | ENG | 2021-11-17
DPIC9812-000-VD-1002-ME-DWG-0023
24 | DPIC9812-000-VD-1002-ME-DWG-0024 |  | Oil Pump Motor Drawing |  |  | ENG | 2021-11-18
DPIC9812-000-VD-1002-ME-DWG-0024
25 | DPIC9812-000-VD-1002-ME-DWG-0025 |  | Filter Dryer Drawing (F-PK6101-2) |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DWG-0025
26 | DPIC9812-000-VD-1002-ME-DWG-0026 |  | Instrument Hook up Drawing |  |  | ENG | 2022-04-30
DPIC9812-000-VD-1002-ME-DWG-0026
27 | DPIC9812-000-VD-1002-ME-DWG-0027 |  | LCS Wiring and Drawing |  |  | ENG | 2021-12-29
DPIC9812-000-VD-1002-ME-DWG-0027
28 | DPIC9812-000-VD-1002-ME-DWG-0028 |  | 3D Model |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DWG-0028
29 | DPIC9812-000-VD-1002-ME-DWG-0029 |  | Name Plate Drawing |  |  | ENG | 2022-05-30
DPIC9812-000-VD-1002-ME-DWG-0029
30 | DPIC9812-000-VD-1002-ME-CLN-0030 |  | Mechanical Calculation for Economizer (E-PK6101-3) |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-CLN-0030
31 | DPIC9812-000-VD-1002-ME-DS-0031 |  | Control Valves Calculation and Data sheet |  |  | ENG | 2022-03-15
DPIC9812-000-VD-1002-ME-DS-0031
32 | DPIC9812-000-VD-1002-ME-CLN-0032 |  | Thermal Calculation for Heat Exchangers |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-CLN-0032
33 | DPIC9812-000-VD-1002-ME-MNL-0033 |  | Operating / Control Philosophy |  |  | ENG | 2022-03-30
DPIC9812-000-VD-1002-ME-MNL-0033
34 | DPIC9812-000-VD-1002-ME-MNL-0034 |  | Process Description |  |  | ENG | 2022-10-30
DPIC9812-000-VD-1002-ME-MNL-0034
35 | DPIC9812-000-VD-1002-ME-MNL-0035 |  | Motor Operation & Maintenance Manual |  |  | ENG | 2022-10-30
DPIC9812-000-VD-1002-ME-MNL-0035
36 | DPIC9812-000-VD-1002-ME-MNL-0036 |  | Operating Manual (Including Start up, Shut Down, Pre-Commissioning, Commissioning Procedure) |  |  | ENG | 2022-10-30
DPIC9812-000-VD-1002-ME-MNL-0036
37 | DPIC9812-000-VD-1002-ME-DIA-0037 |  | Cause and Effect Diagram |  |  | ENG | 2022-03-30
DPIC9812-000-VD-1002-ME-DIA-0037
38 | DPIC9812-000-VD-1002-ME-DIA-0038 |  | Junction Box Connection Diagram (Including Wire Schematic to Instruments) |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DIA-0038
39 | DPIC9812-000-VD-1002-ME-DIA-0039 |  | Logic Diagram (Print out PLC Program) |  |  | ENG | 2022-04-30
DPIC9812-000-VD-1002-ME-DIA-0039
40 | DPIC9812-000-VD-1002-ME-DIA-0040 |  | PLC Wiring Diagram |  |  | ENG | 2022-02-28
DPIC9812-000-VD-1002-ME-DIA-0040
41 | DPIC9812-000-VD-1002-ME-DS-0041 |  | Compressor Data Sheet |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-DS-0041
42 | DPIC9812-000-VD-1002-ME-DS-0042 |  | Main Motor Data Sheet and Curve |  |  | ENG | 2021-10-20
DPIC9812-000-VD-1002-ME-DS-0042
43 | DPIC9812-000-VD-1002-ME-DS-0043 |  | Material Safety Data Sheet |  |  | ENG | 2022-03-03
DPIC9812-000-VD-1002-ME-DS-0043
44 | DPIC9812-000-VD-1002-ME-DS-0044 |  | Evaporator Data Sheet (E-6101) |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-DS-0044
45 | DPIC9812-000-VD-1002-ME-DS-0045 |  | PSV Calculation and Data Sheet |  |  | ENG | 25-Feb-2022
DPIC9812-000-VD-1002-ME-DS-0045
46 | DPIC9812-000-VD-1002-ME-DS-0046 |  | Instrument Data Sheet |  |  | ENG | 2022-03-30
DPIC9812-000-VD-1002-ME-DS-0046
47 | DPIC9812-000-VD-1002-ME-DS-0047 |  | Noise Data Sheet |  |  | ENG | 2022-05-30
DPIC9812-000-VD-1002-ME-DS-0047
48 | DPIC9812-000-VD-1002-ME-LST-0048 |  | Utility Consumption List |  |  | ENG | 2021-10-20
DPIC9812-000-VD-1002-ME-LST-0048
49 | DPIC9812-000-VD-1002-ME-LST-0049 |  | Control Narrative (Sequence Description) |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-LST-0049
50 | DPIC9812-000-VD-1002-ME-LST-0050 |  | Equipment List |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-LST-0050
51 | DPIC9812-000-VD-1002-ME-LST-0051 |  | Instrument Index List (Including Alarm & Trip Points) |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-LST-0051
52 | DPIC9812-000-VD-1002-ME-LST-0052 |  | Instrument Cable List |  |  | ENG | 2022-03-30
DPIC9812-000-VD-1002-ME-LST-0052
53 | DPIC9812-000-VD-1002-ME-LST-0053 |  | Line List |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-LST-0053
54 | DPIC9812-000-VD-1002-ME-LST-0054 |  | I/O List |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-LST-0054
55 | DPIC9812-000-VD-1002-ME-LST-0055 |  | IOM (Including Start up, Shut Down, Pre Commissioning, Commissioning Procedure) |  |  | ENG | 2022-10-30
DPIC9812-000-VD-1002-ME-LST-0055
56 | DPIC9812-000-VD-1002-ME-LST-0056 |  | Special Tools List |  |  | ENG | 2021-11-30
DPIC9812-000-VD-1002-ME-LST-0056
57 | DPIC9812-000-VD-1002-ME-LST-0057 |  | PMS for Compressor Package |  |  | ENG | 2021-11-15
DPIC9812-000-VD-1002-ME-LST-0057
58 | DPIC9812-000-VD-1002-ME-LST-0058 |  | Spare Parts List for Commissioning & Start-up |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-LST-0058
59 | DPIC9812-000-VD-1002-ME-LST-0059 |  | Spare Parts List for 2-Year Operation |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-LST-0059
60 | DPIC9812-000-VD-1002-ME-LST-0060 |  | Capital Spare Part |  |  | ENG | 2021-10-15
DPIC9812-000-VD-1002-ME-LST-0060
61 | DPIC9812-000-VD-1002-ME-MTO-0061 |  | MTO of Insulation |  |  | ENG | 2022-05-30
DPIC9812-000-VD-1002-ME-MTO-0061
62 | DPIC9812-000-VD-1002-ME-ISO-0062 |  | Isometric Drawing for Interconnecting Piping |  |  | ENG | 2022-05-30
DPIC9812-000-VD-1002-ME-ISO-0062
63 | DPIC9812-000-VD-1002-ME-WS-0063 |  | Welding Book (WPS, PQR and Welding / NDE Map) |  |  | ENG/INS | 2022-10-30
DPIC9812-000-VD-1002-ME-WS-0063
64 | DPIC9812-000-VD-1002-ME-CER-0064 |  | Certificates (Including Welder Qualification Certificate / NDT Personnel Qualification Certificate, etc.) |  |  | INS | 2022-10-30
DPIC9812-000-VD-1002-ME-CER-0064
65 | DPIC9812-000-VD-1002-ME-PRC-0065 |  | Inspection and Test Procedure for Compressor |  |  | ENG/INS | 2021-11-30
DPIC9812-000-VD-1002-ME-PRC-0065
66 | DPIC9812-000-VD-1002-ME-PRC-0066 |  | Inspection and Test Procedure for Vessel Skids |  |  | ENG/INS | 2022-03-30
DPIC9812-000-VD-1002-ME-PRC-0066
67 | DPIC9812-000-VD-1002-ME-PRC-0067 |  | Painting Procedure |  |  | INS | 2021-09-30
DPIC9812-000-VD-1002-ME-PRC-0067
68 | DPIC9812-000-VD-1002-ME-PRC-0068 |  | Packing, Marking and Shipping Procedure |  |  | INS | 2022-01-02
DPIC9812-000-VD-1002-ME-PRC-0068
69 | DPIC9812-000-VD-1002-ME-PRC-0069 |  | Fat Procedure for Control System |  |  | ENG/INS | 2022-04-30
DPIC9812-000-VD-1002-ME-PRC-0069
70 | DPIC9812-000-VD-1002-ME-PRC-0070 |  | NDE Procedure |  |  | INS | 2022-03-30
DPIC9812-000-VD-1002-ME-PRC-0070
71 | DPIC9812-000-VD-1002-ME-PRC-0071 |  | PMI Procedure |  |  | INS | 2022-03-30
DPIC9812-000-VD-1002-ME-PRC-0071
72 | DPIC9812-000-VD-1002-ME-PRC-0072 |  | Preservation Procedure |  |  | INS | 2022-05-30
DPIC9812-000-VD-1002-ME-PRC-0072
73 | DPIC9812-000-VD-1002-ME-PRC-0073 |  | Hydrostatic Test Procedure |  |  | INS | 2022-05-30
DPIC9812-000-VD-1002-ME-PRC-0073
74 | DPIC9812-000-VD-1002-ME-PRC-0074 |  | Lifting Procedure |  |  | ENG/INS | 2022-06-30
DPIC9812-000-VD-1002-ME-PRC-0074
75 | DPIC9812-000-VD-1002-ME-DS-0075 |  | Condenser Data Sheet (E-PK6101-2) |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-DS-0075
76 | DPIC9812-000-VD-1002-ME-DS-0076 |  | Economizer Data Sheet (E-PK6101-3) |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-DS-0076
77 | DPIC9812-000-VD-1002-ME-DS-0077 |  | Oil Filter Data Sheet (F-PK6101-1A/2A, F-PK6101-1B/2B) |  |  | ENG | 2021-10-20
DPIC9812-000-VD-1002-ME-DS-0077
78 | DPIC9812-000-VD-1002-ME-DS-0078 |  | Oil Cooler Data Sheet (E-PK 6101-1 A/B) |  |  | ENG | 2021-10-21
DPIC9812-000-VD-1002-ME-DS-0078
79 | DPIC9812-000-VD-1002-ME-DS-0079 |  | Oil Pump Data Sheet |  |  | ENG | 2021-10-22
DPIC9812-000-VD-1002-ME-DS-0079
80 | DPIC9812-000-VD-1002-ME-DS-0080 |  | Oil Separator Data Sheet |  |  | ENG | 2021-10-23
DPIC9812-000-VD-1002-ME-DS-0080
81 | DPIC9812-000-VD-1002-ME-DS-0081 |  | Liquid Receiver Data Sheet (D-PK6101-2) |  |  | ENG | 2021-10-25
DPIC9812-000-VD-1002-ME-DS-0081
82 | DPIC9812-000-VD-1002-ME-DS-0082 |  | K/O Drum Data Sheet (D-PK6101-3) |  |  | ENG | 2021-10-26
DPIC9812-000-VD-1002-ME-DS-0082
83 | DPIC9812-000-VD-1002-ME-DS-0083 |  | Oil Pump Motor Data Sheet |  |  | ENG | 2021-10-28
DPIC9812-000-VD-1002-ME-DS-0083
84 | DPIC9812-000-VD-1002-ME-DS-0084 |  | Propylene Filter Dryer Data Sheet (F-PK6101-2) |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DS-0084
85 | DPIC9812-000-VD-1002-ME-DS-0085 |  | ON/OFF Valve Data Sheet |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DS-0085
86 | DPIC9812-000-VD-1002-ME-DWG-0086 |  | Coupling Drawing |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-DWG-0086
87 | DPIC9812-000-VD-1002-ME-DWG-0087 |  | Evaporator Drawing |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-DWG-0087
88 | DPIC9812-000-VD-1002-ME-STD-0088 |  | Standard Support |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-STD-0088
89 | DPIC9812-000-VD-1002-ME-LST-0089 |  | Support List |  |  | ENG | 2021-12-30
DPIC9812-000-VD-1002-ME-LST-0089
90 | DPIC9812-000-VD-1002-ME-CLN-0090 |  | Stress Analysis Report |  |  | ENG | 2021-10-30
DPIC9812-000-VD-1002-ME-CLN-0090
91 | DPIC9812-000-VD-1002-ME-CLN-0091 |  | Mechanical Calculation for Oil Cooler |  |  | ENG | 2021-12-25
DPIC9812-000-VD-1002-ME-CLN-0091
92 | DPIC9812-000-VD-1002-ME-CLN-0092 |  | Mechanical Calculation for Evaporator (E-6101) |  |  | ENG | 2021-12-25
DPIC9812-000-VD-1002-ME-CLN-0092
93 | DPIC9812-000-VD-1002-ME-CLN-0093 |  | Mechanical Calculation for Condenser (E-PK6101-2) |  |  | ENG | 2021-12-25
DPIC9812-000-VD-1002-ME-CLN-0093
94 | DPIC9812-000-VD-1002-ME-CLN-0094 |  | Mechanical Calculation for Liquid Receiver (D-PK6101-2) |  |  | ENG | 2021-12-25
DPIC9812-000-VD-1002-ME-CLN-0094
95 | DPIC9812-000-VD-1002-ME-CLN-0095 |  | Mechanical Calculation for KO Drum (D-PK6101-3) |  |  | ENG | 2021-12-25
DPIC9812-000-VD-1002-ME-CLN-0095
96 | DPIC9812-000-VD-1002-ME-DWG-0096 |  | Control System Configuration |  |  | ENG | 2022-04-05
DPIC9812-000-VD-1002-ME-DWG-0096
97 | DPIC9812-000-VD-1002-ME-DIA-0097 |  | Loop Digram |  |  | ENG | 2022-04-05
DPIC9812-000-VD-1002-ME-DIA-0097
98 | DPIC9812-000-VD-1002-ME-DWG-0098 |  | HMI for PLC System |  |  | ENG | 2022-04-05
DPIC9812-000-VD-1002-ME-DWG-0098
99 | DPIC9812-000-VD-1002-ME-DIA-0099 |  | PLC Serial Mapping |  |  | ENG | 2022-04-05
DPIC9812-000-VD-1002-ME-DIA-0099
100 | N-299-IN-1002 |  | Inspection Notification |  |  | INS
N-299-IN-1002
01
Recode & Renamed
01
Renamed
Added
Renamed
Renamed
01
Renamed
Renamed
Renamed