## Cover Sheet( Att.2)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
Vendor : |  | Kasravand |  |  |  |  | 1 Page of 10
|  | P.O No. : | 299-1002
|  | MR No. : | DPIC9812-001-000-ME-MR-4150-0001 (Rev. D2)
|  | MR Description : | REFRIGERATION UNIT (PK-6101)
|  | PO Effective Date : | 2021-08-11
|  | Project Duration : | 14 Months
|  | MR Tag No.(s) : | PK-6101
Monthly Progress Report MRP 006
Cut off Date: 23-Sep-2023
A5 | 2023-09-23 | Issued for Review |  | M.Kameli | N. Bakhtiari | M.Rezaei
A4 | 2023-07-08 | Issued for Review |  | M.Kameli | N. Bakhtiari | M.Rezaei
A3 | 2022-02-19 | Issued for Review |  | T. Khorsand | N. Bakhtiari | A. Malekinia
A2 | 2022-01-15 | Issued for Review |  | T. Khorsand | N. Bakhtiari | A. Malekinia
A1 | 2021-12-16 | Issued for Review |  | T. Khorsand | N. Bakhtiari | A. Malekinia
A0 | 2021-11-28 | Issued for Review |  | T. Khorsand | N. Bakhtiari | A. Malekinia
Rev | Date | Purpose of Issue |  | Prepared | Checked | Approved

## Overall Report( Att.3)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
OVERALL REPORT
| Weight Factor (%) |  | Plan | [6 empty] | Actual / Forecast
|  |  | Start (Date) |  | Finish (Date) |  | Up to last | This Period | Up to now | Start (Date) |  | Finish (Date) |  | Up to last | This Period | Up to now
Engineering | 5% |  | 2021-08-15 |  | 2022-03-20 |  | 100% | 0% | 100% | 2021-08-15 |  | 2022-03-20 |  | 56.2% | 0% | 56.2%
Raw Material / Supply | 35% |  | 2021-11-14 |  | 2022-09-11 |  | 100% | 0% | 100% | 2021-11-14 |  | 2022-09-11 |  | 28.14% | 0% | 28.14%
Manufacturing | 45% |  | 2022-01-07 |  | 2022-09-28 |  | 100% | 0% | 100% | 2022-01-07 |  | 2022-09-28 |  | 37% | 0% | 37%
Ex-Work & Transportation | 10% |  | 2022-09-28 |  | 2022-09-30 |  | 100% | 0% | 100% | 2022-09-28 |  | 2022-09-30 |  | 0% | 0% | 0%
Final Book | 5% |  | 2022-09-30 |  | 2022-10-04 |  | 100% | 0% | 100% | 2022-09-30 |  | 2022-10-04 |  | 0% | 0% | 0%
Overall | 100% |  | 2021-08-11 |  | 2022-10-04 |  | 100% | 0% | 100% | 2021-08-11 |  | 2022-10-04 |  | 29.31% | 0% | 29.31%
| 2021-08-16 | 2021-09-16 | 2021-10-17 | 2021-11-28 | 2021-12-16 | 2022-01-15 | 2022-02-14 | 2022-03-16 | 2022-04-14 | 2022-05-15 | 2022-06-16 | 2022-07-16 | 2022-08-16 | 2022-09-16 | 2022-10-17 | 2023-07-05 | 2023-09-20
Plan Progress | 0% | 0.21% | 0.43% | 2.38% | 4.1% | 11.99% | 26.64% | 35.54% | 44.56% | 53.01% | 63.12% | 73.64% | 77.17% | 82.58% | 100% | 100% | 100%
Actual Progress | 0% | 0% | 0% | 2.45% | 3.25% | 5.27% | 10.04% | 10.04% | 10.04% | 10.04% | 10.04% | 10.04% | 10.04% | 10.04% | 10.04% | 29.31% | 29.31%
Catch up Progress
*In case of project delay and Nargan request, if there is a permissible duration extention by the client, Replan progress should be mentioned in the above table, otherwise Catch up progress should be mentioned in the above table.

## Narrative( Att.4)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
NARRATIVE REPORT
1. MAJOR ACTIVITIES IN THIS PERIOD :
-Final Manufacturing of Motors and ready for shipment
-finish of Oil Pump Manufacturing
-Final Phase of Manufacturing of 2 sets of MYCOM Compressor Block plus rotor manufacturing
2. MAJOR ACTIVITIES IN NEXT PERIOD :
-inspection of 2 sets of Main Motors manufacturing
3 REMAINING OPEN ITEMS TO BE SELECTED WITH PURCHASER :
-Waiting to receipt the remaining due Invoices which affected projecr costs and schedule
4. PROBLEMS WHICH MAY AFFECT ON QUALITY OF THE PRODUCT OR DELIVERY SCHEDULE :
4-1 EXPLANATION OF PROBLEM :
-Waiting to receipt the remaining due Invoices which affected projecr costs and schedule
4-2 IMPACT ON QUALITY OF PRODUCT AND/OR FABRICATION/DELIVERY SCHEDULE :
5. REQUIRED URGENT INFORMATION OR RETURNING APPROVAL DOCUMENTS BY PURCHASER :

## Document Report( Att.5)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
DOCUMENT STATUS REPORT
No. | Doc. Number | Description | No. Pages | Forecast Issue Date | Weight Factor | Progress | Last Purpose of Issue ( POI ) | REV 0 |  |  |  | REV 1 |  |  |  | Rev 2 |  |  |  | Rev 3 |  |  |  | Rev 4
[8 empty] | Issue Date | Transmittal Number | Received Date From Nargan | Code | Issue Date | Transmittal Number | Received Date From Nargan | Code | Issue Date | Transmittal Number | Received Date From Nargan | Code | Issue Date | Transmittal Number | Received Date From Nargan | Code | Issue Date | Transmittal Number | Received Date From Nargan | Code | Remarks
1 | DPIC9812-000-VD-1002-ME-MDR-0001 | Vendor Print Index & Schedule (VPIS) |  | 2021-08-15 | 4% | 80% | 2 | 2021-11-01 | N299-1002-0003 | 2021-11-15 | 2 | 2022-02-05 | N299-1002-0050 | 2022-02-22 | 2
2 | DPIC9812-000-VD-1002-ME-PLN-0002 | Time Schedule |  | 2021-10-12 | 1% | 100% | 1 | 2021-11-08 | N299-1002-0007 | 2021-11-09 | 3 | 2021-11-28 | N299-1002-0013 | 2021-12-06 | 1
3 | DPIC9812-000-VD-1002-ME-LST-0003 | Work Break Down Structure (WBS) |  | 2021-09-21 | 2% | 100% | 1 | 2021-11-01 | N299-1002-0004 | 2021-11-07 | 1
4 | DPIC9812-000-VD-1002-ME-RP-0004 | Project Monthly Report for Refrigeration Package |  | 2021-11-02 | 1% | 60% | 3 | 2021-11-29 | N299-1002-0014 | 2021-11-30 |  | 2021-12-21 | N299-1002-0021 | 2021-12-21 | 2 | 2022-01-17 | N299-1002-0043 | 2022-01-25 | 3 | 2022-02-20 | N299-1002-0060 | 2022-02-27
5 | DPIC9812-000-VD-1002-ME-LST-0005 | Sub Vendor List |  | 2021-09-20 | 2% | 80% | 2 | 2021-12-11 | N299-1002-0018 | 2021-12-19 | 2
6 | DPIC9812-000-VD-1002-ME-LST-0006 | Final Data Book Index |  | 2022-06-30 | 0.5%
7 | DPIC9812-000-VD-1002-ME-ITP-0008 | Inspection & Test Plan (ITP) for Refrigeration Unit (PK-6101) |  | 2021-11-18 | 2% | 80% | 2 | 2021-11-16 | N299-1002-0009 | 2021-12-04 | 3 | 2022-01-04 | N299-1002-0039 | 2022-01-08 | 2 | 2023-08-27 | N299-1002-0068 | 2023-08-27 | 2
8 | DPIC9812-000-VD-1002-ME-ITP-0009 | Inspection and Test Plan for Compressor |  | 2021-12-29 | 0.4% | 80% | 2 | 2021-11-01 | N299-1002-0005 | 2021-11-17 | 3 | 2022-02-26 | N299-1002-0062 | 2022-03-08 | 2
9 | DPIC9812-000-VD-1002-ME-PID-0010 | Piping and Instrument Diagram (PID) |  | 2021-11-12 | 2% | 80% | 2 | 2021-11-13 | N299-1002-0008 | 2021-12-04 | 3 | 2022-01-03 | N299-1002-0037 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0056 | 2022-03-06 | 2
10 | DPIC9812-000-VD-1002-ME-PFD-0011 | Process Flow Diagram |  | 2021-10-17 | 2% | 80% | 2 | 2021-10-17 | N299-1002-0001 | 2021-10-30 | 2 | 2022-01-09 | N299-1002-0040 | 2022-01-29 | 2 | 2022-02-09 | N299-1002-0054 | 2022-03-06 | 2
11 | DPIC9812-000-VD-1002-ME-GAD-0012 | General Arrangement Drawing (Including Loads, Displacement, and Maintenance Info.) |  | 2021-11-24 | 6% | 80% | 2 | 2021-12-12 | N299-1002-0019 | 2021-12-21 | 3 | 2021-12-28 | N299-1002-0030 | 2022-01-12 | 2
12 | DPIC9812-000-VD-1002-ME-DWG-0013 | Compressor Drawing |  | 2021-10-17 | 1% | 60% | 3 | 2021-10-17 | N299-1002-0001 | 2021-10-18 | 3
13 | DPIC9812-000-VD-1002-ME-DWG-0014 | Main Motor Drawing |  | 2022-02-25 | 0.8% | 60% | 3 | 2022-02-21 | N299-1002-0061 | 2022-03-06 | 3
14 | DPIC9812-000-VD-1002-ME-DWG-0015 | Outline Dimensional Drawings (Cabinets Arrangement) |  | 2022-04-30 | 0.8%
15 | DPIC9812-000-VD-1002-ME-DWG-0016 | Oil Filter Drawing |  | 2021-11-28 | 1% | 80% | 2 | 2022-01-03 | N299-1002-0038 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0057 | 2022-03-07 | 2
16 | DPIC9812-000-VD-1002-ME-DWG-0017 | Oil Cooler Drawing |  | 2021-11-22 | 1% | 80% | 2 | 2021-12-25 | N299-1002-0023 | 2022-01-12 | 2 | 2022-02-09 | N299-1002-0053 | 2022-03-06 | 2
17 | DPIC9812-000-VD-1002-ME-DWG-0018 | Oil Pump Drawing |  | 2022-02-27 | 1% | 80% | 2 | 2021-12-22 | N299-1002-0022 | 2022-01-03 | 2
18 | DPIC9812-000-VD-1002-ME-DWG-0019 | Oil Separator Drawing |  | 2022-02-26 | 0.8%
19 | DPIC9812-000-VD-1002-ME-DWG-0020 | Condenser Drawing |  | 2021-11-21 | 1% | 80% | 2 | 2021-12-26 | N299-1002-0027 | 2022-01-17 | 2 | 2022-02-09 | N299-1002-0053 | 2022-03-06 | 2
20 | DPIC9812-000-VD-1002-ME-DWG-0021 | Liquid Receiver Drawing |  | 2021-11-28 | 1% | 80% | 2 | 2021-12-28 | N299-1002-0033 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0057 | 2022-03-07 | 2
21 | DPIC9812-000-VD-1002-ME-DWG-0022 | K/O Drum Drawing |  | 2021-11-28 | 1% | 80% | 2 | 2021-12-29 | N299-1002-0034 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0057 | 2022-03-07 | 2
22 | DPIC9812-000-VD-1002-ME-DWG-0023 | Economizer Drawing |  | 2021-11-21 | 1% | 80% | 2 | 2021-12-25 | N299-1002-0023 | 2022-01-12 | 2 | 2022-02-09 | N299-1002-0053 | 2022-03-06 | 2
23 | DPIC9812-000-VD-1002-ME-DWG-0024 | Oil Pump Motor Drawing |  | 2022-02-27 | 0.8%
24 | DPIC9812-000-VD-1002-ME-DWG-0025 | Filter Dryer Drawing |  | 2021-11-28 | 1% | 80% | 2 | 2022-01-03 | N299-1002-0038 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0057 | 2022-03-07 | 2
25 | DPIC9812-000-VD-1002-ME-DWG-0026 | Instrument Hook up Drawing |  | 2022-04-30 | 0.8%
26 | DPIC9812-000-VD-1002-ME-DWG-0027 | LCS Wiring and Drawing |  | 2022-02-28 | 0.8%
27 | DPIC9812-000-VD-1002-ME-DWG-0028 | 3D Model |  | 2022-03-01 | 0.8% | 80% | 2 | 2022-02-26 | N299-1002-0062 | 2022-03-06 | 2
28 | DPIC9812-000-VD-1002-ME-DWG-0029 | Name Plate Drawing |  | 2022-05-30 | 0.8%
29 | DPIC9812-000-VD-1002-ME-CLN-0030 | Mechanical Calculation for Economizer (E-PK6101-3) |  | 2021-12-05 | 6% | 80% | 2 | 2021-12-28 | N299-1002-0032 | 2022-01-12 | 2 | 2022-02-09 | N299-1002-0051 | 2022-03-06 | 2
30 | DPIC9812-000-VD-1002-ME-DS-0031 | Control Valves Calculation and Data sheet |  | 2022-03-15 | 0.8%
31 | DPIC9812-000-VD-1002-ME-CLN-0032 | Thermal Calculation for Heat Exchangers |  | 2021-10-31 | 6% | 80% | 2 | 2021-10-31 | N299-1002-0002 | 2021-11-20 | 3 | 2021-12-04 | N299-1002-0016 | 2021-12-12 | 3 | 2021-12-25 | N299-1002-0025 | 2022-01-10 | 2 | 2022-02-09 | N299-1002-0051 | 2022-03-06 | 2
32 | DPIC9812-000-VD-1002-ME-MNL-0033 | Operating / Control Philosophy |  | 2022-03-30 | 0.8%
33 | DPIC9812-000-VD-1002-ME-MNL-0034 | Process Description |  | 2022-07-01 | 0.8%
34 | DPIC9812-000-VD-1002-ME-MNL-0035 | Motor Operation & Maintenance Manual |  | 2022-10-02 | 0.8%
35 | DPIC9812-000-VD-1002-ME-MNL-0036 | Operating Manual (Including Start up, Shut Down, Pre-Commissioning, Commissioning Procedure) |  | 2022-10-02 | 0.8%
36 | DPIC9812-000-VD-1002-ME-DIA-0037 | Cause and Effect Diagram |  | 2022-03-30 | 0.8%
37 | DPIC9812-000-VD-1002-ME-DIA-0038 | Junction Box Connection Diagram (Including Wire Schematic to Instruments) |  | 2022-03-01 | 0.8% | 80% | 2 | 2022-03-05 | N299-1002-0065 | 2022-04-03 | 2
38 | DPIC9812-000-VD-1002-ME-DIA-0039 | Logic Diagram (Print out PLC Program) |  | 2022-04-30 | 0.8%
39 | DPIC9812-000-VD-1002-ME-DIA-0040 | PLC Wiring Diagram |  | 2022-02-28 | 0.8%
40 | DPIC9812-000-VD-1002-ME-DS-0041 | Compressor Data Sheet |  | 2021-10-24 | 0.8% | 80% | 2 | 2022-01-02 | N299-1002-0036 | 2022-01-18 | 2
41 | DPIC9812-000-VD-1002-ME-DS-0042 | Main Motor Data Sheet and Curve |  | 2021-11-28 | 0.8% | 60% | 3 | 2022-01-23 | N299-1002-0045 | 2022-02-01 |  | 2022-02-21 | N299-1002-0061 | 2022-03-06 | 3 | 2022-07-25 | N299-1002-0066 | 2022-08-29
42 | DPIC9812-000-VD-1002-ME-DS-0043 | Material Safety Data Sheet |  | 2022-03-03 | 0.8%
43 | DPIC9812-000-VD-1002-ME-DS-0044 | Evaporator Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2021-10-31 | N299-1002-0002 | 2021-11-20 | 3 | 2021-12-28 | N299-1002-0031 | 2022-01-17 | 2 | 2022-02-09 | N299-1002-0052 | 2022-03-06 | 2
44 | DPIC9812-000-VD-1002-ME-DS-0045 | PSV Calculation and Data Sheet |  | 2022-02-25 | 0.8% | 60% | 3 | 2022-03-02 | N299-1002-0064 | 2022-03-26 | 3
45 | DPIC9812-000-VD-1002-ME-DS-0046 | Instrument Data Sheet |  | 2022-03-30 | 0.8%
46 | DPIC9812-000-VD-1002-ME-DS-0047 | Noise Data Sheet |  | 2022-05-30 | 0.5%
47 | DPIC9812-000-VD-1002-ME-LST-0048 | Utility Consumption List |  | 2021-11-27 | 0.8% | 80% | 2 | 2022-01-09 | N299-1002-0041 | 2022-01-18 | 2 | 2022-03-02 | N299-1002-0064 | 2022-04-16 | 2
48 | DPIC9812-000-VD-1002-ME-LST-0049 | Control Narrative (Sequence Description) |  | 2022-03-01 | 0.8%
49 | DPIC9812-000-VD-1002-ME-LST-0050 | Equipment List |  | 2021-12-24 | 0.8% | 80% | 2 | 2022-01-31 | N299-1002-0049 | 2022-02-19 | 2
50 | DPIC9812-000-VD-1002-ME-LST-0051 | Instrument Index List (Including Alarm & Trip Points) |  | 2021-12-12 | 0.8% | 80% | 2 | 2022-01-11 | N299-1002-0042 | 2022-01-29 | 2 | 2022-03-02 | N299-1002-0063 | 2022-03-26 | 2
51 | DPIC9812-000-VD-1002-ME-LST-0052 | Instrument Cable List |  | 2022-03-30 | 1% | 80% | 2 | 2022-03-05 | N299-1002-0065 | 2022-04-03 | 2
52 | DPIC9812-000-VD-1002-ME-LST-0053 | Line List |  | 2022-01-14 | 0.8% | 80% | 2 | 2022-01-22 | N299-1002-0044 | 2022-02-06 | 2
53 | DPIC9812-000-VD-1002-ME-LST-0054 | I/O List |  | 2022-03-01 | 0.8%
54 | DPIC9812-000-VD-1002-ME-LST-0055 | IOM (Including Start up, Shut Down, Pre Commissioning, Commissioning Procedure) |  | 2022-10-02 | 0.8%
55 | DPIC9812-000-VD-1002-ME-LST-0056 | Special Tools List |  | 2022-03-01 | 0.8%
56 | DPIC9812-000-VD-1002-ME-LST-0057 | PMS for Compressor Package |  | 2022-03-01 | 0.8%
57 | DPIC9812-000-VD-1002-ME-LST-0058 | Spare Parts List for Commissioning & Start-up |  | 2021-12-24 | 0.8% | 60% | 3 | 2021-12-21 | N299-1002-0020 | 2022-01-03 | 3
58 | DPIC9812-000-VD-1002-ME-LST-0059 | Spare Parts List for 2-Year Operation |  | 2021-12-24 | 0.8% | 60% | 3 | 2021-12-21 | N299-1002-0020 | 2022-01-03 | 3
59 | DPIC9812-000-VD-1002-ME-LST-0060 | Capital Spare Part |  | 2021-11-14 | 0.8% | 60% | 3 | 2021-12-21 | N299-1002-0020 | 2022-01-03 | 3
60 | DPIC9812-000-VD-1002-ME-MTO-0061 | MTO of Insulation |  | 2022-05-30 | 0.5%
61 | DPIC9812-000-VD-1002-ME-ISO-0062 | Isometric Drawing for Interconnecting Piping |  | 2022-05-30 | 0.8%
62 | DPIC9812-000-VD-1002-ME-WS-0063 | Welding Book (WPS, PQR and Welding / NDE Map) |  | 2022-10-02 | 0.8%
63 | DPIC9812-000-VD-1002-ME-CER-0064 | Certificates (Including Welder Qualification Certificate / NDT Personnel Qualification Certificate, etc.) |  | 2022-10-02 | 0.8% | 80% | 2 | 2022-01-30 | N299-1002-0048 | 2022-02-01 | 2
64 | DPIC9812-000-VD-1002-ME-PRC-0065 | Inspection and Test Procedure for Compressor |  | 2022-02-08 | 0.8% | 80% | 2 | 2021-11-01 | N299-1002-0005 | 2021-11-20 | 2 | 2022-02-26 | N299-1002-0062 | 2022-04-13 | 2
65 | DPIC9812-000-VD-1002-ME-PRC-0066 | Inspection and Test Procedure for Vessel Skids |  | 2022-03-30 | 0.8%
66 | DPIC9812-000-VD-1002-ME-PRC-0067 | Painting Procedure |  | 2022-03-01 | 0.8%
67 | DPIC9812-000-VD-1002-ME-PRC-0068 | Packing, Marking and Shipping Procedure |  | 2021-12-29 | 0.8% | 80% | 2 | 2022-01-30 | N299-1002-0047 | 2022-02-12 | 2
68 | DPIC9812-000-VD-1002-ME-PRC-0069 | Fat Procedure for Control System |  | 2022-04-30 | 0.8%
69 | DPIC9812-000-VD-1002-ME-PRC-0070 | NDE Procedure |  | 2021-12-29 | 0.8% | 100% | 1 | 2021-11-22 | N299-1002-0011 | 2021-11-27 | 2 | 2022-01-30 | N299-1002-0047 | 2022-02-12 | 1
70 | DPIC9812-000-VD-1002-ME-PRC-0071 | PMI Procedure |  | 2021-12-29 | 0.8% | 100% | 1 | 2022-01-30 | N299-1002-0047 | 2022-02-12 | 2 | 2022-02-13 | N299-1002-0055 | 2022-02-14 | 1
71 | DPIC9812-000-VD-1002-ME-PRC-0072 | Preservation Procedure |  | 2022-05-30 | 0.8%
72 | DPIC9812-000-VD-1002-ME-PRC-0073 | Hydrostatic Test Procedure |  | 2022-05-30 | 0.8%
73 | DPIC9812-000-VD-1002-ME-PRC-0074 | Lifting Procedure |  | 2022-06-30 | 0.8%
74 | DPIC9812-000-VD-1002-ME-DS-0075 | Condenser Data Sheet |  | 2021-10-31 | 0.8% | 80% | 2 | 2021-11-01 | N299-1002-0006 | 2021-11-20 | 3 | 2021-12-28 | N299-1002-0031 | 2022-01-17 | 2 | 2022-02-09 | N299-1002-0052 | 2022-03-06 | 2
75 | DPIC9812-000-VD-1002-ME-DS-0076 | Economizer Data Sheet |  | 2021-10-31 | 0.8% | 80% | 2 | 2021-11-01 | N299-1002-0006 | 2021-11-20 | 3 | 2021-12-26 | N299-1002-0029 | 2022-01-12 | 2 | 2022-02-09 | N299-1002-0052 | 2022-03-06 | 2
76 | DPIC9812-000-VD-1002-ME-DS-0077 | Oil Filter Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2021-11-24 | N299-1002-0012 | 2021-12-06 | 2 | 2021-12-28 | N299-1002-0031 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0058 | 2022-03-07 | 2
77 | DPIC9812-000-VD-1002-ME-DS-0078 | Oil Cooler Data Sheet |  | 2021-11-01 | 0.8% | 80% | 2 | 2021-11-01 | N299-1002-0006 | 2021-11-20 | 3 | 2022-01-02 | N299-1002-0036 | 2022-01-18 | 2 | 2022-02-09 | N299-1002-0052 | 2022-03-06 | 2
78 | DPIC9812-000-VD-1002-ME-DS-0079 | Oil Pump Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2022-01-02 | N299-1002-0035 | 2022-01-17 | 2
79 | DPIC9812-000-VD-1002-ME-DS-0080 | Oil Separator Data Sheet |  | 2022-02-28 | 0.8%
80 | DPIC9812-000-VD-1002-ME-DS-0081 | Liquid Receiver Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2021-11-21 | N299-1002-0010 | 2021-12-12 | 3 | 2021-12-25 | N299-1002-0024 | 2022-01-16 | 2 | 2022-02-20 | N299-1002-0058 | 2022-03-07 | 2
81 | DPIC9812-000-VD-1002-ME-DS-0082 | K/O Drum Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2021-11-21 | N299-1002-0010 | 2021-12-12 | 3 | 2021-12-28 | N299-1002-0031 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0058 | 2022-03-07 | 2
82 | DPIC9812-000-VD-1002-ME-DS-0083 | Oil Pump Motor Data Sheet |  | 2022-02-28 | 0.8%
83 | DPIC9812-000-VD-1002-ME-DS-0084 | Propylene Filter Dryer Data Sheet |  | 2021-11-07 | 0.8% | 80% | 2 | 2021-11-29 | N299-1002-0015 | 2021-12-12 | 2 | 2021-12-28 | N299-1002-0031 | 2022-01-17 | 2 | 2022-02-20 | N299-1002-0058 | 2022-03-07 | 2
84 | DPIC9812-000-VD-1002-ME-DS-0085 | ON/OFF Valve Data Sheet |  | 2022-02-28 | 0.8% | 80% | 2 | 2022-03-05 | N299-1002-0065 | 2022-04-03 | 2
85 | DPIC9812-000-VD-1002-ME-DWG-0086 | Coupling Drawing |  | 2021-12-19 | 0.8% | 80% | 2 | 2022-01-02 | N299-1002-0035 | 2022-01-12 | 2
86 | DPIC9812-000-VD-1002-ME-DWG-0087 | Evaporator Drawing |  | 2021-11-14 | 1% | 80% | 2 | 2021-12-28 | N299-1002-0030 | 2022-01-16 | 2 | 2022-02-09 | N299-1002-0053 | 2022-03-06 | 2
87 | DPIC9812-000-VD-1002-ME-STD-0088 | Standard Support |  | 2022-06-01 | 0.8%
88 | DPIC9812-000-VD-1002-ME-LST-0089 | Support List |  | 2022-06-01 | 0.8%
89 | DPIC9812-000-VD-1002-ME-CLN-0090 | Stress Analysis Report |  | 2022-06-01 | 0.8%
90 | DPIC9812-000-VD-1002-ME-CLN-0091 | Mechanical Calculation for Oil Cooler |  | 2021-12-25 | 0.5% | 80% | 2 | 2021-12-25 | N299-1002-0026 | 2022-01-12 | 2 | 2022-02-09 | N299-1002-0051 | 2022-03-06 | 2
90 | DPIC9812-000-VD-1002-ME-CLN-0092 | Mechanical Calculation for Evaporator (E-6101) |  | 2021-12-25 | 0.5% | 80% | 2 | 2021-12-25 | N299-1002-0026 | 2022-01-16 | 2 | 2022-02-09 | N299-1002-0051 | 2022-03-06 | 2
90 | DPIC9812-000-VD-1002-ME-CLN-0093 | Mechanical Calculation for Condenser (E-PK6101-2) |  | 2021-12-25 | 0.4% | 80% | 2 | 2021-12-25 | N299-1002-0026 | 2022-01-17 | 2 | 2022-02-09 | N299-1002-0051 | 2022-03-06 | 2
90 | DPIC9812-000-VD-1002-ME-CLN-0094 | Mechanical Calculation for Liquid Receiver (D-PK6101-2) |  | 2021-12-25 | 0.4% | 80% | 2 | 2021-12-25 | N299-1002-0026 | 2022-01-16 | 2 | 2022-02-20 | N299-1002-0059 | 2022-03-07 | 2
90 | DPIC9812-000-VD-1002-ME-CLN-0095 | Mechanical Calculation for KO Drum (D-PK6101-3) |  | 2021-12-25 | 0.4% | 80% | 2 | 2021-12-25 | N299-1002-0026 | 2022-01-15 | 2 | 2022-02-20 | N299-1002-0059 | 2022-03-07 | 2
90 | DPIC9812-000-VD-1002-ME-DWG-0096 | Control System Configuration |  | 2022-05-05 | 0.2%
90 | DPIC9812-000-VD-1002-ME-DIA-0097 | Loop Digram |  | 2022-05-05 | 0.1%
90 | DPIC9812-000-VD-1002-ME-DWG-0098 | HMI for PLC System |  | 2022-05-05 | 0.1%
90 | DPIC9812-000-VD-1002-ME-DIA-0099 | PLC Serial Mapping |  | 2022-05-05 | 0.1%
90 | N-299-IN-1002 | Inspection Notification |  | 2021-12-29 | 0%
Total |  |  |  |  | 100% | 56.2%
| CODE | CODE DESCRIPTION | PROGRESS
| 1 | Approved For Fabrication | 100%
| 2 | Approved For Fabrication; Except As Noted | 80%
| 3 | Not Approved | 60%
| - | First Issue | 60%

## Material Status Report( Att.6)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
MATERIAL STATUS REPORT
No. | Description | Unit (Tons / Nos.) | P/O Date |  | Delivery Date |  | Sub-Vendor/Manufacturer | Weight Factor (%) | Progress Rate |  |  |  |  | Remarks
|  |  | Plan | Actual | Plan | Actual |  |  | Purchase Order (10%) | EX Work (40%) | FOB/CFR Custom clearance (30%) | Delivery At Vendor Shop (20%) | Total Progress (%)
1 | Oil pump | 5 & 2 | 2021-12-19 | 2021-12-19 | 2022-05-30 |  | MYCOM | 2.43% | 100% | 100% | 100% | 100% | 2.43%
2 | Oil separator |  | 2021-12-19 | 2021-12-19 | 2022-05-30 |  |  | 2.43% |  |  |  |  | 0%
3 | Compressor | 2 | 2021-11-14 | 2021-12-01 | 2022-07-06 |  | MYCOM | 35.71% | 100% | 75% |  |  | 14.29%
4 | Special Valves |  | 2022-01-02 |  | 2022-01-02 |  |  | 4.857% |  |  |  |  | 0%
5 | Instrument |  | 2022-01-29 |  | 2022-05-09 |  |  | 4.857% |  |  |  |  | 0%
6 | Electro motor | 2 | 2021-12-29 | 2021-12-25 | 2021-09-06 | 2023-03-01 | HELMKE | 14.29% | 100% | 100% | 100% |  | 11.43%
7 | Filter |  | 2021-12-22 |  | 2022-04-01 |  |  | 4.857% |  |  |  |  | 0%
8 | Other material |  | 2021-12-13 |  | 2022-05-22 |  |  | 2% |  |  |  |  | 0%
9 | Pipe |  | 2022-01-24 |  | 2022-02-13 |  |  | 2.857% |  |  |  |  | 0%
10 | Plate |  | 2021-10-13 |  | 2022-01-02 |  |  | 2.857% |  |  |  |  | 0%
11 | Flange & Fitting |  | 2021-12-13 |  | 2022-01-27 |  |  | 2.857% |  |  |  |  | 0%
12 | Gasket |  | 2021-12-13 |  | 2022-01-17 |  |  | 2.857% |  |  |  |  | 0%
13 | Bolt & Nut |  | 2021-12-13 |  | 2022-01-17 |  |  | 2.857% |  |  |  |  | 0%
14 | Electrical |  | 2022-01-12 |  | 2022-02-16 |  |  | 2.857% |  |  |  |  | 0%
15 | Manual valves |  | 2022-01-09 |  | 2022-02-13 |  |  | 2.857% |  |  |  |  | 0%
16 | Instrument |  | 2022-02-15 |  | 2022-03-15 |  |  | 2.857% |  |  |  |  | 0%
17 | PLC |  | 2022-02-11 |  | 2022-03-18 |  |  | 2.857% |  |  |  |  | 0%
18 | Other material |  | 2022-01-04 |  | 2022-02-08 |  |  | 2.857% | 0% | 0% |  |  | 0%
Total | [7 empty] | 100% | 52.43% | 43.5% | 16.72% | 2.43% | 28.14%

## Fabrication Status ( Att.7)
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
[10 empty] | PRE-FABRICATION | [20 empty] | FABRICATION | [14 empty] | TEST |  |  |  |  | FINAL PREPARATION |  | % Completion
[10 empty] | 35% | [20 empty] | 55% | [14 empty] | 5% |  |  |  |  | 5%
SPECIFICATIONS |  |  |  |  | MATERIAL |  |  |  |  | Condensor |  |  | Hexane chiller |  |  | Skid |  |  | Other |  |  | Assembly of packages on skid |  |  | Compressor unit | [5 empty] | Compressor unit |  | Condensor |  | Hexane chiller |  | Skid |  | Other |  | Assembly of packages on skid |  | status for foreign supply |  |  | INSPECTION AND TEST |  |  |  |  | FINAL PREPARATION
TAG NO. | DIMENTION (mm)IDxL | WEIGHT(KG) | WEIGHT FACTOR |  | 0 |  |  |  |  | 7.5% |  |  | 7.5% |  |  | 3% |  |  | 1% |  |  | 4% |  |  | 12% | [5 empty] | 0.5% |  | 0.5% |  | 0.5% |  | 0.5% |  | 0.5% |  | 0.5% |  | 52% |  |  | 5% |  |  |  |  | 5%
[5 empty] | SHELL / PLATE | INTERNAL PIPE | FLANGES | PIPE | LOCALLY SUPPLIED | Condensor (cutting,rolling,casting) | ASSEMBLEY | WELDING | Hexane chiller (cutting,rolling,casting) | ASSEMBLEY | WELDING | Skid (cutting,rolling,casting) | ASSEMBLEY | WELDING | Other (cutting,rolling,casting) | ASSEMBLEY | WELDING | Inter connecting piping | ASSEMBLEY | WELDING | Compressor unit Fabrication | ASSEMBLEY | WELDING | Oil filter | Oil cooler | Filter dryer | ASSEMBLEY | WELDING | ASSEMBLEY | WELDING | ASSEMBLEY | WELDING | ASSEMBLEY | WELDING | ASSEMBLEY | WELDING | ASSEMBLEY | WELDING | Electro motor | Oil pump & Oil Seprator | Compressor | NDT | R . T. | Hydro test | DIMENSIONAL | Final Check | Surface Preparation | PAINTING
[10 empty] | 6% | 1.25% | 0.25% | 6% | 1.25% | 0.25% | 2% | 0.75% | 0.25% | 0.5% | 0.25% | 0.25% | 3% | 0.75% | 0.25% | 3% | 1.5% | 0.5% | 2% | 4% | 1% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 0.25% | 8% | 16% | 28% | 2% | 0.5% | 0.5% | 1.5% | 0.5% | 2.5% | 2.5%
RU (PK-6101) |  |  | 100% | ACTUAL | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 50% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 37%
|  |  |  | PLAN | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
TOTAL |  | 0 | 100% | [47 empty] | ACTUAL |  | 37%
[51 empty] | PLAN |  | 100%
0

## Inspection Report
DEHDASHT HIGH DENSITY POLYETHYLENE PROJECT
INSPECTION REPORT
PO NO.: |  |  | VENDOR: | [13 empty] | DOC. NO.:
DESCRIPTION: |  |  | PO DELIVERY DATE: | [13 empty] | DATE:
|  |  | ESTD SHIPPING DATE: | [13 empty] | PAGE: OF
ITEM NO. | QTY (UNIT) | MR NO. | MATERIAL DESCRIPTION | January | [30 empty] | REMARKS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  |  | E |  |  |  |  | EXPEDITING |  |  |  |  | O |  | OFFICE
|  |  |  | I |  |  |  |  | INSPECTION |  |  |  |  | S E |  | SUBVENDOR EXPEDITING
|  |  |  | E / I |  |  |  |  | EXPEDITING & INSPECTION |  |  |  |  | S I |  | SUBVENDOR INSPECTION
|  |  |  | PIM |  |  |  |  | PRE INSPECTION MEETING |  |  |  |  | SE / SI |  | SUBVENDOR EXPEDITING & INSPECTION
ABBREVIATION FOR INSPECTION AND TEST PLAN
DI | : | DIMENSIONAL CHECK |  | January 1: LT; January 3: :; January 4: LEAK TEST (AIR HELIUM); January 15: ATR; January 17: :; January 18: AIR LEAK TEST ON REINFORCING PAD
VI | : | VISUAL INSPECTION |  | January 1: AT; January 3: :; January 4: PENEUMATIC TEST; January 15: OST; January 17: :; January 18: OVER SPEED TEST
MI | : | MATERIAL IDENTIFICATION |  | January 1: HT; January 3: :; January 4: HYDROSTATIC TEST; January 15: NDT; January 17: :; January 18: NON-DESTRUCTIVE TEST (RT,UT,MT and PT, etc)
MM | : | MATERIAL MECHANICAL TEST |  | January 1: DA; January 3: :; January 4: DISASSEMBLY TEST; January 15: PI; January 17: :; January 18: PAINTING INSPECTION
EP | : | EDGE PREPARATION |  | January 1: FT; January 3: :; January 4: PERFORMANCE TEST (FUNCTIONAL TEST); January 15: SP; January 17: :; January 18: SHIPPING PREPARATION
FU | : | FIT-UP |  | January 1: MRT; January 3: :; January 4: MECHANICAL RUNNING TEST; January 15: H.T; January 17: :; January 18: HARDNESS TEST
BC | : | BACK CHIPPING GAUGING |  | January 1: BAL; January 3: :; January 4: DYNAMIC/STATIC BALANCE; January 15: P.T; January 17: :; January 18: PRODUCTION TEST
WQ | : | WELDING PROCEDURE TEST |  | January 1: ERT; January 3: :; January 4: ELECTRICAL RESISTANCE TEST
WP | : | WELDER PERFORMANCE TEST |  | January 1: ECT; January 3: :; January 4: ELECTRICAL CHARACTERISTIC TEST; January 15: * NOTE: PLEASE SPECIFY ANY INSPECTION AND TEST ITEM WHICH IS NOT LISTED.
WM | : | MECHANICAL TEST FOR WP AND WQ |  | January 1: PWHT; January 3: :; January 4: POST-WELD HEAT TREATMENT

## Financial Report
Financial Information
|  | Report Date: | Page: 9
Advance Payment :
Advance Payment Amount :
Receipt Date of Advance Payment :
Guarranty :
APG :
Type of Advance payment Guaranty :
Advance Payment Guarranty No. :
Advance Payment Guarranty Amount :
Advance Payment Guarranty Issued Date :
Advance Payment Guarranty Expiry date :
PBG :
Type of Performance Guaranty :
Performance Guarranty No. :
Performance Guarranty Amount :
Performance Guarranty Issued Date :
Performance Guarranty Expiry date :

## Payment Status
Project payment summary status
| Project Name: | Refrigeration Unit | Project Number: | DPIC-PO-299-1002 | Client: | NARGAN
| PO No : | DPIC-PO-299-1002 | Purchase Order Date : | 15-Dec-20 | Client Number: | Dehdasht Petrochemical
|  |  | Amount: |  | Initial Volume of the Contract (Kg):
ROW | Description |  | Receivables (EUR) |  | Payment (EUR) | Remaining of the Contract (EUR) | Payment Phase | Date of the Document | Document Number | Cumulative Tonnage Sent (KG) | Percent Cumulative Progress
1 | Down Payment |  | 25% PO |  | 25% PO
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
: (EUR) Total |  |  | 0 |  | 0
account balance (EUR): |  |  | 0

## Photo
Photo
| Report Date: 08-Jul-2023 | Page: 11