## 项目进度计划表A-Schedule A
项目编号： Project No. | KYTL2024111 | 项目进度计划表A 原进度计划，工期11个月 Project Schedule A Existing construction duration of 11 months
项目名称： Project name | TPC公司HDPE干燥项目 TPC-HDPE Project
项目经理 Project manager | 梁国林 Liang Guolin
生效方式： Effective method: | 签字生效 Signature
生效日期： Effective Date: | 2024.12.17
发货日期： Delivery date: | 2025.11.15
序号 SN. | 内容 Content |  |  | 12月 December | [30 empty] | 1月 January | [30 empty] | 2月 February | [27 empty] | 3月 March | [30 empty] | 4月 April | [29 empty] | 5月 May | [29 empty] | 6月 June | [29 empty] | 7月 July | [29 empty] | 8月 August | [30 empty] | 9月 September | [29 empty] | 10月 October | [29 empty] | 11月 November | [29 empty] | 备注 Remarks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | 设计 Engineering
1.1 | 工艺专业 Process discipline |  | 150天 150 days
1.1.1 | 工艺设计 Process engineering | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.2 | 设备设计条件 Equipment condition | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.3 | 仪表设计条件 Instrument condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 31
1.1.4 | 电气设计条件 Electrical condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 31
1.1.5 | 管道三维建模 Piping BIM | 考核分数 Assessment | bar: 3月 March 17 to 5月 May 16
1.1.6 | 管道设计文件 Piping engineering documents | 考核分数 Assessment | bar: 3月 March 17 to 5月 May 16
1.2 | 设备专业 Equipment discipline |  | 30天 30 days
1.2.1 | 流化床干燥机设计 Fluid bed dryer engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.2 | 旋风除尘器设计 Cyclone engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.3 | 喷淋塔设计 Scrubber engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.4 | 风机订货及返资 Blower ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.5 | 卸料阀订货及返资 Discharge valve ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.6 | 己烷泵订货及返资 Hexane pump ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.2.7 | 氮气加热器订货及返资 Nitrogen heater ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 17
1.3 | 仪表专业 Instrument discipline |  | 45天 45 days | bar: 3月 March 31 to 5月 May 16
1.3.1 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 31 to 5月 May 16
1.3.2 | 仪表选型及订货 Instrument selection and ordering | 考核分数 Assessment | bar: 3月 March 31 to 5月 May 16
1.3.3 | 控制系统设计及订货 Control system engineering and ordering | 考核分数 Assessment
1.4 | 电气专业 Electrical discipline |  | 45天 45 days
1.4.1 | 电气选型及订货 Electrical selection and ordering | 考核分数 Assessment | bar: 3月 March 31 to 5月 May 16
2 | 加工制造 Fabrication |  | 225天 225 days
2.1 | 流化床干燥机备料及加工 Fluid bed dryer material preparation and fabricating | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.2 | 旋风除尘器备料及加工 Cyclone material preparation and fabricating | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.3 | 喷淋塔备料及加工 Scrubber material preparation and fabricating | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.4 | 风机 Blower | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.5 | 卸料阀 Discharge valve | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.6 | 己烷泵 Hexane pump | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.7 | 氮气加热器 Nitrogen heater | 考核分数 Assessment | bar: 3月 March 1 to 10月 October 15
2.8 | 管道 Piping | 考核分数 Assessment | bar: 5月 May 16 to 10月 October 15
2.9 | 阀门 Valve | 考核分数 Assessment | bar: 5月 May 16 to 10月 October 15
2.10 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 17 to 10月 October 15
2.11 | 电气 Electrical | 考核分数 Assessment | bar: 3月 March 17 to 10月 October 15
3 | 验收及包装 Inspection and packaging |  | 20天 20 days
3.1 | 验收 Inspection | 考核分数 Assessment | bar: 9月 September 30 to 10月 October 25
3.2 | 包装 Packaging | 考核分数 Assessment | bar: 10月 October 16 to 11月 November 5
4 | 发货 Shipment |  | 10天 10 days
4.1 | 发货 Shipment | 考核分数 Assessment | bar: 11月 November 6 to 11月 November 16
说明： 1.表中红色标识P1为合同款5-1（合同额25%）支付时间，12月17日； 2.表中红色标识P2为合同款5-2（合同额15%）支付时间，原计划时间3月1日； 3.表中红色标识P3为合同款5-3（合同额20%）支付时间，原计划时间3月16日； 4.表中红色标识P4为合同款5-4（合同额25%）支付时间，原计划时间11月16日； Note: 1. The red mark P1 in the table indicates the payment date for contract payment 5-1 (25% of the contract amount), which is December 17th,2024; 2. The red mark P2 in the table indicates the payment date for contract payment 5-2 (15% of the contract amount), and the scheduled payment date is March 1st,2025; 3. The red mark P3 in the table indicates the payment date for contract payment 5-3 (20% of the contract amount), and the scheduled payment date is March 16th,2025; 4. The red mark P4 in the table indicates the payment date for contract payment 5-4 (25% of the contract amount), and the scheduled payment date is November 16th,2025.

## 项目进度计划表B-Schedule B
项目编号： Project No. | KYTL2024111 | 项目进度计划表B 压缩后进度计划，工期10个月 Project Schedule B Compressed construction duration of 10 months
项目名称： Project name | TPC公司HDPE干燥项目 TPC-HDPE Project
项目经理 Project manager | 梁国林 Liang Guolin
生效方式： Effective method: | 签字生效 Signature
生效日期： Effective Date: | 2024.12.17
发货日期： Delivery date: | 2025.10.15
序号 SN. | 内容 Content |  | 12月 December | [30 empty] | 1月 January | [30 empty] | 2月 February | [27 empty] | 3月 March | [30 empty] | 4月 April | [29 empty] | 5月 May | [29 empty] | 6月 June | [29 empty] | 7月 July | [29 empty] | 8月 August | [30 empty] | 9月 September | [29 empty] | 10月 October | [29 empty] | 11月 November | [29 empty] | 备注 Remarks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | 设计 Engineering
1.1 | 工艺专业 Process discipline
1.1.1 | 工艺设计 Process engineering | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.2 | 设备设计条件 Equipment condition | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.3 | 仪表设计条件 Instrument condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 28
1.1.4 | 电气设计条件 Electrical condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 28
1.1.5 | 管道三维建模 Piping BIM | 考核分数 Assessment | 5月 May 7: 设计工期缩短10天 Engineering duration shorten by 10 days
1.1.6 | 管道设计文件 Piping engineering documents | 考核分数 Assessment | bar: 3月 March 14 to 5月 May 6
1.2 | 设备专业 Equipment discipline
1.2.1 | 流化床干燥机设计 Fluid bed dryer engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.2 | 旋风除尘器设计 Cyclone engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.3 | 喷淋塔设计 Scrubber engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.4 | 风机订货及返资 Blower ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.5 | 卸料阀订货及返资 Discharge valve ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.6 | 己烷泵订货及返资 Hexane pump ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.7 | 氮气加热器订货及返资 Nitrogen heater ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.3 | 仪表专业 Instrument discipline | bar: 3月 March 28 to 5月 May 6
1.3.1 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
1.3.2 | 仪表选型及订货 Instrument selection and ordering | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
1.3.3 | 控制系统设计及订货 Control system engineering and ordering | 考核分数 Assessment
1.4 | 电气专业 Electrical discipline
1.4.1 | 电气选型及订货 Electrical selection and ordering | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
2 | 加工制造 Fabrication
2.1 | 流化床干燥机备料及加工 Fluid bed dryer material preparation and fabricating | 考核分数 Assessment | 2月 February 15: P3; 10月 October 16: 整体工期缩短30天 Constrcution duration shorten by 30days in total
2.2 | 旋风除尘器备料及加工 Cyclone material preparation and fabricating | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.3 | 喷淋塔备料及加工 Scrubber material preparation and fabricating | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.4 | 风机 Blower | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.5 | 卸料阀 Discharge valve | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.6 | 己烷泵 Hexane pump | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.7 | 氮气加热器 Nitrogen heater | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.8 | 管道 Piping | 考核分数 Assessment | bar: 5月 May 16 to 9月 September 14
2.9 | 阀门 Valve | 考核分数 Assessment | bar: 5月 May 16 to 9月 September 14
2.10 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 17 to 9月 September 14
2.11 | 电气 Electrical | 考核分数 Assessment | bar: 3月 March 17 to 9月 September 14
3 | 验收及包装 Inspection and packaging
3.1 | 验收 Inspection | 考核分数 Assessment | bar: 8月 August 30 to 9月 September 24
3.2 | 包装 Packaging | 考核分数 Assessment | bar: 9月 September 15 to 10月 October 4
4 | 发货 Shipment
4.1 | 发货 Shipment | 考核分数 Assessment | bar: 10月 October 5 to 10月 October 15
说明： 1.表中红色标识P1为合同款5-1（合同额25%）支付时间，12月17日； 2.表中红色标识P2为合同款5-2（合同额15%）支付时间，请求支付时间2月15日； 3.表中红色标识P3为合同款5-3（合同额20%）支付时间，请求支付时间2月15日； 4.表中红色标识P4为合同款5-4（合同额25%）支付时间，请求支付时间10月16日。 Note: 1. The red mark P1 in the table indicates the payment date for contract payment 5-1 (25% of the contract amount), which is December 17th,2024; 2. The red mark P2 in the table indicates the payment date for contract payment 5-2 (15% of the contract amount), and the scheduled payment date is not later than Feb 15th 2025, the earlier the better. 3. The red mark P3 in the table indicates the payment date for contract payment 5-3 (20% of the contract amount), and the scheduled payment date is not later than Feb 15th 2025, the earlier the better. 4. The red mark P4 in the table indicates the payment date for contract payment 5-4 (25% of the contract amount), and the scheduled payment date is October 16th,2025.

## 项目进度计划表C-Schedule C
项目编号： Project No. | KYTL2024111 | 项目进度计划表B 压缩后进度计划，工期10个月,流化床提前交货 Project Schedule B Compressed construction duration of 10 months，fluid bed dryer advance delivery
项目名称： Project name | TPC公司HDPE干燥项目 TPC-HDPE Project
项目经理 Project manager | 梁国林 Liang Guolin
生效方式： Effective method: | 签字生效 Signature
生效日期： Effective Date: | 2024.12.17
发货日期： Delivery date: | 2025.10.15
序号 SN. | 内容 Content |  | 12月 December | [30 empty] | 1月 January | [30 empty] | 2月 February | [27 empty] | 3月 March | [30 empty] | 4月 April | [29 empty] | 5月 May | [29 empty] | 6月 June | [29 empty] | 7月 July | [29 empty] | 8月 August | [30 empty] | 9月 September | [29 empty] | 10月 October | [29 empty] | 11月 November | [29 empty] | 备注 Remarks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | 设计 Engineering
1.1 | 工艺专业 Process discipline
1.1.1 | 工艺设计 Process engineering | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.2 | 设备设计条件 Equipment condition | 考核分数 Assessment | bar: 12月 December 17 to 2月 February 13
1.1.3 | 仪表设计条件 Instrument condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 28
1.1.4 | 电气设计条件 Electrical condition | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 28
1.1.5 | 管道三维建模 Piping BIM | 考核分数 Assessment | 5月 May 7: 设计工期缩短10天 Engineering duration shorten by 10 days
1.1.6 | 管道设计文件 Piping engineering documents | 考核分数 Assessment | bar: 3月 March 14 to 5月 May 6
1.2 | 设备专业 Equipment discipline
1.2.1 | 流化床干燥机设计 Fluid bed dryer engineering | 考核分数 Assessment | bar: 1月 January 17 to 2月 February 15
1.2.2 | 旋风除尘器设计 Cyclone engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.3 | 喷淋塔设计 Scrubber engineering | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.4 | 风机订货及返资 Blower ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.5 | 卸料阀订货及返资 Discharge valve ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.6 | 己烷泵订货及返资 Hexane pump ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.2.7 | 氮气加热器订货及返资 Nitrogen heater ordering and requirements feedback | 考核分数 Assessment | bar: 2月 February 13 to 3月 March 14
1.3 | 仪表专业 Instrument discipline | bar: 3月 March 28 to 5月 May 6
1.3.1 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
1.3.2 | 仪表选型及订货 Instrument selection and ordering | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
1.3.3 | 控制系统设计及订货 Control system engineering and ordering | 考核分数 Assessment
1.4 | 电气专业 Electrical discipline
1.4.1 | 电气选型及订货 Electrical selection and ordering | 考核分数 Assessment | bar: 3月 March 28 to 5月 May 6
2 | 加工制造 Fabrication
2.1 | 流化床干燥机备料及加工 Fluid bed dryer material preparation and fabricating | 考核分数 Assessment | 2月 February 15: P3; 10月 October 16: 整体工期缩短30天 Constrcution duration shorten by 30days in total
2.2 | 旋风除尘器备料及加工 Cyclone material preparation and fabricating | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.3 | 喷淋塔备料及加工 Scrubber material preparation and fabricating | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.4 | 风机 Blower | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.5 | 卸料阀 Discharge valve | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.6 | 己烷泵 Hexane pump | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.7 | 氮气加热器 Nitrogen heater | 考核分数 Assessment | bar: 2月 February 15 to 9月 September 14
2.8 | 管道 Piping | 考核分数 Assessment | bar: 5月 May 16 to 9月 September 14
2.9 | 阀门 Valve | 考核分数 Assessment | bar: 5月 May 16 to 9月 September 14
2.10 | 仪表 Instrument | 考核分数 Assessment | bar: 3月 March 17 to 9月 September 14
2.11 | 电气 Electrical | 考核分数 Assessment | bar: 3月 March 17 to 9月 September 14
3 | 验收及包装 Inspection and packaging
3.1 | 流化床验收 Fluid bed dryer Inspection | 考核分数 Assessment | bar: 8月 August 16 to 8月 August 26
3.2 | 验收 Inspection | bar: 8月 August 30 to 9月 September 24
3.3 | 流化床包装 Fluid bed dryer Packaging | bar: 8月 August 27 to 9月 September 7
3.4 | 包装 Packaging | 考核分数 Assessment | bar: 9月 September 15 to 10月 October 4
4 | 发货 Shipment
4.1 | 流化床发货 Shipment of Fluid bed dryer |  | 9月 September 16: 流化床作为首批交货，工期再次缩短30天 Fluid bed dryer is the firt delivery,constrcution duration shorten by 30 days again
4.2 | 发货 Shipment | 考核分数 Assessment | bar: 10月 October 5 to 10月 October 15
说明： 1.表中红色标识P1为合同款5-1（合同额25%）支付时间，12月17日； 2.表中红色标识P2为合同款5-2（合同额15%）支付时间，请求支付时间2月15日； 3.表中红色标识P3为合同款5-3（合同额20%）支付时间，请求支付时间2月15日； 4.表中红色标识P4为合同款5-4（合同额25%）支付时间，请求支付时间10月16日。 Note: 1. The red mark P1 in the table indicates the payment date for contract payment 5-1 (25% of the contract amount), which is December 17th,2024; 2. The red mark P2 in the table indicates the payment date for contract payment 5-2 (15% of the contract amount), and the scheduled payment date is not later than Feb 15th 2025, the earlier the better. 3. The red mark P3 in the table indicates the payment date for contract payment 5-3 (20% of the contract amount), and the scheduled payment date is not later than Feb 15th 2025, the earlier the better. 4. The red mark P4 in the table indicates the payment date for contract payment 5-4 (25% of the contract amount), and the scheduled payment date is October 16th,2025.