## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | P&ID | N-278-VD-6019-PR-PID-0002-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 02 |  | The tittle of the document (including package tag Number) on the first page to be provided | Incorporated | Closed
2 | 1 | 02 |  | Symbol and legend shall be added, or project symbol and legend shall be followed | legend and symbol are added (page 3 and 4) symbols are youre standard. | Closed
3 | 1 | 02 |  | Numbering of piping, instruments and equipment Tag Nrs shall be based on project specification | Incorporated (lijkt me standaard | Closed
4 | 3 | 02 |  | It conflicts with our tag numbers, to be corrected. | Incorporated | Closed
5 | 3 | 02 |  | OT: 46° C DT:75 °C | Incorporated | Closed
6 | 3 | 02 |  | The inlet and outlet size of all PSVs to be specified. | They are specified in the document 17735-46 PSV datasheet (the outlet will be vendor to approve) For youre information the inlet is as per piping size 3/4" flanged outlet is atmosferic will be be calculated. | Closed
7 | 3 | 02 |  | LO isolation Valve shall be considered for all PSVs. | This is not aggreed in the contract. It is also not reccomended. It is not needed for this package. | Noted. |  |  | Open
8 |  | 02 |  | Compressor shall not be started at the Low Low suction pressure. I.e. Permissive to start signal shall be generated from NOT low low condition of suction pressure. | PALL means low trip when the suction pressure is below 6,5 bar the compressor will tripp and the package will stop immediately without cooling down. Compressor can be started with the start sequence described in control philosophy. | Trip command shall be shown via relevant interlock no. (IP-920). Refer to below sample shematic
9 |  | 02 |  | Size of all Lines shall be added in PID. | Incorporated It is reccomended to add not to much information to keep a good over vieuw on the P&ID (especially the main lines are 1' or 3/4' | Closed
10 |  | 02 |  | Set = 7 barg | Incorporated | Closed
11 |  | 02 |  | Set point for PCV shall be specified | Incorporated | Closed
12 |  | 02 |  | Positioner for control valve with related alarm in control room will be considered. | Incorporated | Not implemented in PID. Positioner shall be shown such as below:
13 |  | 02 |  | Outlet T shall be specified | Incorporated it is specified at 60ºC | Closed
14 |  | 02 |  | TG and Globe valve shall be considered | A TG and Globe valve are not necessary because of TG 8205. | Separate TG for each exchanger shall be considered. Please relocate TG-8205 for one of the exchangers and add another TG for the 2nd one
15 |  | 02 |  | Cooling rate shall be specified | 1m3/h | Closed
16 |  | 02 |  | P&ID for High Pressure Air Compressor K020 | Incorporated | Closed
17 |  | 02 |  | DP of tube side also shall be specified. 10/13 rule shall be considered or PSV shall be installed | Incorporated | Closed
18 |  | 02 |  | Set = 75 °C | Incorporated | Closed
19 |  | 02 |  | All design temperature shall be checked based on project sizing criteria: - Maximum operating temperature +15 °C - Design temperature shall be rounded up to full 5 °C steps. | Incorporated | Refer to comment on PID
20 |  | 02 |  | Interlock IP922 / IP920 from process for package start / stop shall be shown. | Interlock not required for start stops | Vendor reply is not acceptable. Relevant signals shall be considered for compressor start / stop
21 |  | 02 |  | please recheck the ratio of design pressure to operating pressure to ascertain that PSV does not act during normal operation (because of pressure pulsation in the discharge side of compressor. In other words, Design pressure of inter stage equipment, Instruments and piping shall be rechecked. Distance between design and normal pressure is lower than 10 %”. | Incorporated | For second stage suction pulsation damper, please refer to comment on Pdf file.
22 |  | 02 |  | comment for both coolers: Vent/drain with valve to be considered on both sides. MOM: vent/drain for water side and drain for gas side will be added | A drain and vent on the coolers is not possible by the cooler suplier. There is a vent before and after in the water system. | Please also add drain on Air side (if on cooler not possible, on line) (the shell side can be drained in case of any tube rapture after years.) Please also confirm that water side of cooler can be drained/vented with those considered on water lines
23 |  | 02 |  | All tags, Should be mentioned as per sample | Incorporated
24 |  | 02 |  | Skids should be Considered or move here | Not drawn as per Airpack standard
25 |  | 02 |  | All suffix tag should be start 82XX | Incorporated it is added in the notes
26 |  | 02 |  | All abbreviations should be mentioned in legend page | Incorporated
27 |  | 02 |  | As per VPIS should be renamed to LCP | Incorporated
28 |  | 02 |  | All instruments tag should follow project spec (N278-000-CI-JSD-1500-001-02) | Updated according to e-mails
29 |  | 02 |  | Is it shaft driven?(if motor drive, to be added in consumption list) | It is shaft driven motor | Please add a note to avoid mis-understanding.
30 |  | 02
31 |  | 02
32 |  | 02