## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | P&ID | N-278-VD-6019-PR-PID-0002-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 02 | Closed | The tittle of the document (including package tag Number) on the first page to be provided | Incorporated | Closed
2 | 1 | 02 | Closed | Symbol and legend shall be added, or project symbol and legend shall be followed | legend and symbol are added (page 3 and 4) symbols are youre standard. | Closed
3 | 1 | 02 | Closed | Numbering of piping, instruments and equipment Tag Nrs shall be based on project specification | Incorporated | Closed
4 | 3 | 02 | Closed | It conflicts with our tag numbers, to be corrected. | Incorporated | Closed
5 | 3 | 02 | Closed | OT: 46° C DT:75 °C | Incorporated | Closed
6 | 3 | 02 | Closed | The inlet and outlet size of all PSVs to be specified. | They are specified in the document 17735-46 PSV datasheet (the outlet will be vendor to approve) For youre information the inlet is as per piping size 3/4" flanged outlet is atmosferic will be be calculated. | Closed
7 | 3 | 02 | Closed | LO isolation Valve shall be considered for all PSVs. | This is not aggreed in the contract. It is also not reccomended. It is not needed for this package. | Noted. |  |  |  |  | Open
8 | 3 | 02 | Closed | Compressor shall not be started at the Low Low suction pressure. I.e. Permissive to start signal shall be generated from NOT low low condition of suction pressure. | PALL means low trip when the suction pressure is below 6,5 bar the compressor will tripp and the package will stop immediately without cooling down. Compressor can be started with the start sequence described in control philosophy. | Trip command shall be shown via relevant interlock no. (IP-920). Refer to below sample shematic | Trip command is added with interlock no. IP-920 in the next revision | Closed
9 | 3 | 02 | Closed | Size of all Lines shall be added in PID. | Incorporated It is reccomended to add not to much information to keep a good over vieuw on the P&ID (especially the main lines are 1' or 3/4' | Closed
10 | 3 | 02 | Closed | Set = 7 barg | Incorporated | Closed
11 | 3 | 02 | Closed | Set point for PCV shall be specified | Incorporated | Closed
12 | 3 | 02 | Closed | Positioner for control valve with related alarm in control room will be considered. | Incorporated | Not implemented in PID. Positioner shall be shown such as below: | Positioner is updated. The instrument air to control the valve is taken from the inlet. | Refer to the comment on the PID
13 | 3 | 02 | Closed | Outlet T shall be specified | Incorporated it is specified at 60ºC | Closed
14 | 3 | 02 | Closed | TG and Globe valve shall be considered | A TG and Globe valve are not necessary because of TG 8205. | Separate TG for each exchanger shall be considered. Please relocate TG-8205 for one of the exchangers and add another TG for the 2nd one | Updated | Noted
15 | 3 | 02 | Closed | Cooling rate shall be specified | 1m3/h | Closed
16 | 3 | 02 | Closed | P&ID for High Pressure Air Compressor K020 | Incorporated | Closed
17 | 3 | 02 | Closed | DP of tube side also shall be specified. 10/13 rule shall be considered or PSV shall be installed | Incorporated | Closed
18 | 3 | 02 | Closed | Set = 75 °C | Incorporated | Closed
19 | 3 | 02 | Closed | All design temperature shall be checked based on project sizing criteria: - Maximum operating temperature +15 °C - Design temperature shall be rounded up to full 5 °C steps. | Incorporated | Refer to comment on PID | Inlet Desgin pressure is 75°C as per comment on rev.01 Other is updated as per comment | Closed
20 | 3 | 02 | Closed | Interlock IP922 / IP920 from process for package start / stop shall be shown. | Interlock not required for start stops | Vendor reply is not acceptable. Relevant signals shall be considered for compressor start / stop | Three interlocks are added. START, STOP and ESD. | Refer to the comment on the PID
21 | 3 | 02 | Closed | please recheck the ratio of design pressure to operating pressure to ascertain that PSV does not act during normal operation (because of pressure pulsation in the discharge side of compressor. In other words, Design pressure of inter stage equipment, Instruments and piping shall be rechecked. Distance between design and normal pressure is lower than 10 %”. | Incorporated | For second stage suction pulsation damper, please refer to comment on Pdf file. | Noted
22 | 3 | 02 | Closed | comment for both coolers: Vent/drain with valve to be considered on both sides. MOM: vent/drain for water side and drain for gas side will be added | A drain and vent on the coolers is not possible by the cooler suplier. There is a vent before and after in the water system. | Please also add drain on Air side (if on cooler not possible, on line) (the shell side can be drained in case of any tube rapture after years.) Please also confirm that water side of cooler can be drained/vented with those considered on water lines | Drain on the air side of the cooler is not needed since the gas is instrument air there will be no water in the air piping. Also the pulsation dampenters in line with the cooler have drains. Since the water system on the compressor is very small there is a drain added at the lowest point of the water system. from there the water system can be drained. For maintenance the complete air piping can be closed with valves and the water piping can be closed with valves. Both process lines can be drained In conclusion the air and water piping can be closed and drained to perform maintenance on the compressor. Because it is a very small compressor and almost no piping length this is sufficient for the design. | Noted.
23 | 3 | 02 | Closed | All tags, Should be mentioned as per sample | Incorporated
24 | 3 | 02 | Closed | Skids should be Considered or move here | Not drawn as per Airpack standard
25 | 3 | 02 | Closed | All suffix tag should be start 82XX | Incorporated it is added in the notes
26 | 3 | 02 | Closed | All abbreviations should be mentioned in legend page | Incorporated
27 | 4 | 02 | Closed | As per VPIS should be renamed to LCP | Incorporated |  | Since there is no PLC inside the panel, and therefor no control of the package. It is named LPS, Local Pushbutton Station.
28 | 4 | 02 | Closed | All instruments tag should follow project spec (N278-000-CI-JSD-1500-001-02) | Updated according to e-mails
29 | 4 | 02 | Closed | Is it shaft driven?(if motor drive, to be added in consumption list) | It is shaft driven motor | Please add a note to avoid mis-understanding. | Updated in the next revision
REV. 03
30 | 1 | 03 | Closed | - All previous comment should be implemented and If any comments is not applicable please send reply sheet. - all Tag name in all documents should be same format. no needs "-" after prefix 320. example correct format is 320TT-8201 | - Noted - Please recheck where this is specified. It is a big change to update all the documents tags, and late to comment this in revision 3 | -Noted '- rev 01 : "101-" should be replaced with "320" rev 02: "320-" should be replaced with "320" rev 03:"320-" should be replaced with "320" this comment is repeated form rev 01 to 3 and it is mandatory bacause all tag name plate for all instrument in site is according spec. | noted
31 | 2 | 03 | Closed | Modify to sight glass | Incorporated | Noted.
32 | 2 | 03 | Closed | Battery Limit | All signals, dashed lines is Client scope. Note 9 is added to the P&ID | Noted.
33 | 2 | 03 | Closed | symbol selector switch should be added | Incorporated | Noted.
34 | 3 | 03 | Closed | Line number shall be added in PID According to legend of project.(Attachment#2) | Incorporated | Noted.
35 | 3 | 03 | Closed | All PSV and CV Sizes will be finalized after the approval Instrument calculation sheet document. | Noted. | Noted.
36 | 3 | 03 | Closed | All monitoring signals, shall be shown with battery limit. | All signals, dashed lines is Client scope. Note 9 is added to the P&ID | Noted.
37 | 3 | 03 | Closed | Operating and Design condition for shell and tube side to be specified. | This will be specified in the datasheet | Noted.
38 | 3 | 03 | Closed | should be followed according to legend (Attachment#1) Should be implemented for all PSV | Incorporated | All instrument should be shown with circle | noted
39 | 3 | 03 | Closed | Please clarify. It seems this valve is considered for start the compressor. So, you are requested to recheck the set pressure. In addition please refer to process comment. | It is not a load / unload valve. The PCV is to keep the outlet pressure at 30 bar, as required. The valve opens and closes by a certain percentage the bypass to control the outlet pressure at 30 bar. When starting the package the valve is automatically closed, till the outlet reaches 30 bar. This sequence is also described in the controll philosophy and will be in the logic | Refer to reply for item No. 40
40 | 3 | 03 | Closed | Process: Vendor is requested to clarify PCV requiement. Anyhow, it seems the PCV set pressure to be define a bit more that normal discharge pressrue to prevent valve opening at normal condition | Please refer to the control philosophy and logic for the controlling of the package | Please be informed, copmressor package will be stoped via PAHH (IP-920) from downstream Air vessel. The set pressure of PAHH is 32 barg. Considering set pressure of PCV-8201 as 30 barg, the pressure at the downstream vessel will not reach to 32 barg and no stop signal will be sent to compressor package. | PAHH means a trip at 32bar at the ESD interlock (IP-920). When the package stops from the trip interlock the package stops imediatly (emergency stop) without the stop sequence to protect lifetime of the package. Please clarify the stopping of the package. From the order the compressor discharge pressure is defined at 30bar(g) and the compressor has already been ordered. Please let us know if we seriously need to look at the requested change of pressure. | Noted. No need to change the discharge pressure. | Noted
41 | 3 | 03 | Closed | Re-Comment: Ground!!? Clarify | Updated in the next revision to make it more clear. There is piping connected to direct the water flow down in case of an emergency. | Noted.
42 | 3 | 03 | Closed | Please clarify about this. As per TCL B7, Suction pulsation suppression devices shall be designed for the same design pressure as the discharge pulsation suppression devices except when protected by a relief valve | Updated in the next revision to the design pressure of the pulsation dampener 1st stage discharge | closed.
43 | 3 | 03 | Closed | All monitoring signals, shall be shown with battery limit. | All signals, dashed lines is Client scope. Note 9 is added to the P&ID | Noted.
44 | 3 | 03 | Closed | PCV or PV ? should be clarify . PCV do not receive electrical signals | PCV (pressure control valve) is an electric pneumatic controlled valve so you also need an electric signal. Please find this information in the datasheet | Noted.
45 | 3 | 03 | Closed | As per project specification, thermowells shall be installed at least on 6" line size. | It is not possible to go from 3/4'' to 6'' because of the flow. We discussed this internal and decided we can design it to 4'' as absolute maximum. So thermowells are installed at 4'' piping in the next revision. And most thermowells, where possible are mounted on vessels, since they are bigger than 6". | Noted.
46 | 3 | 03 | Closed | plz clarify and determine status and command signals related to Electric motor/Fan motor/Oil Pump | This is described in the Control philosophy Airpack ref. 17735-21.
47 | 3 | 03 | Closed | plz mention tag for SG | Tag no is provided for piping sight glasses. Sight glass in the oil sump is not replacable, but build in the equipment, so therefor not given any tag | Noted.
48 | 4 | 03 | Closed | Tag name should be modified. 300LP-820 300JDAN-820 | Not incorporated. This is a new tag no, submitted in revision 3. and it is the 2nd time we are changing tags. All the tags are already defined in documents, therefor it is not possible to change. On this package is a JB (junctionbox) and a LPS (Local pushbutton station) It is this name to mention that there is no power or control from the box/station but provided from the DCS. | In all revision , this comment is repeated. (Refer to Item 30) Prefix for JB is 300 and sufix is 3 digit (300LP-820 and 300JDAN820) is accepted | noted
49 | 4 | 03 | Closed | These signals shall be sent from LPS to DCS. Please separate from other | This is not correct the signals must be in line with eachother and will have the same tag as the lights it is connected to. The signal is 24V to power the light XL-xxxx, coming from the DCS, so arrow up. The ESD must be there, it is required on the package. When a trip occurs the package will do an emergency stop. so this is the same sequence. | Refer to comment on PID | noted
50 | 4 | 03 | Closed | As per PID of project, interlocks and tag name (ML/XA/YL) should be modified | Not applicable see comment 49 | Refer to Item 49, Refer to comment on PID | noted
51 | 4 | 03 | Closed | Prefix "320" to be added to all instruments tag Number. | Note is changed to only instruments prefix | refer to Item 30 | noted
52 | 4 | 03 | Closed | Globe valve shall be considered | If there will be a globe valve it will have no function/use. If you design a globe valve in that place you can stop the waterflow in the aftercooler, if the valve fails and reduce the flow it will cause more tripps if the package is running. | Noted.
53 | 3 | 03 | Closed | PZLC 8201 | Incorporated | Refer to comment on PID | (Item 63) Please clarify why we need two signals for the same control of the PCV (PIC and PZLC) According the control philosophy and P&ID there is one signal controlling the PCV. | PIC is controling signal from DCS to PCV. PZLC is signal from Limit switch to DCS that indicate the open/ close status of PCV | Positioner signal from the PCV transmitter is added to the P&ID.
REV. 04
54 | 3 | 04 | Closed | All missing data to be specified. | Please specify or mark the missing data, in our understanding all needed data is on the P&ID. | All data that mentioned "…" instead of information in previous revision. Closed.
55 |  | 04 | Closed | -(refer to reply sheet) should be followed according to legend (Attachment#1) -Should be implemented for all PSV | Noted | Noted.
56 |  | 04 | Closed | Tube rupture scenario shall be considered for this PSV (since low pressure side of exchangers is lower than 10/13 of highpressire side | Please explain the tube rupture scenario. The heat exchangers is different equipment than the PSV. For both inter and after cooler (heat exchangers) combined. The differential pressure is not more than 0,1 bar. | Low pressure side of heat exchanger shall be design at least for 10/13 of design pressure of high pressure side or if the design pressrue of low pressrue side is lower than mentioned value, a PSV shall be considered at the low pressure side. At this case the PSV shall be design for the tube rupture scenario. | Tube rupture will be taken into account when sizing the PSV
57 |  | 04 | Closed | 2.5 | Operating pressure is not 2,5 bar(g). Inlet pressure water system is 4,5bar(g), there is some pressure loss, so updated to 4,4 bar(g) | Noted.
58 |  | 04 | Closed | OT/DT: 46 / 75 °C | Noted | Closed
59 |  | 04 | Closed | 7 | Noted | Closed
60 |  | 04 | Closed | OT/DT: 36 / 75 °C | Noted | Closed
61 |  | 04 | Closed | PIC | Item 63 | Refer to item 53 | Noted
62 |  | 04 | Closed | PZLC-8201 | Item 63 | Refer to item 53 | Noted
63 |  | 04 | Closed | to be checked considering control philosophy and Purchaser P&ID | (Item 53, 61, 62) Please clarify why we need two signals for the same control of the PCV (PIC and PZLC) According the control philosophy and P&ID there is one signal controlling the PCV. | Refer to item 40 | Noted
64 |  | 04 | Closed | Spec of project shall be follow. (refer to previous comment rev01 to 03 | Noted | Noted.
65 |  | 04 | Closed | 300JDAN-820 | Noted | Noted.
66 |  | 04 | Closed | Tag name should be modified. 300LP-820 300JDAN-820 Re-comment | Noted | Noted.
67 |  | 04 | Closed | According to the project specifications and incompatibility with other site equipment all tags should be modified. This comment is mentioned from revision one to the last version | Noted | Noted.
68 |  | 04 | Closed | 300LP-820 | Noted, but be aware this is not a Local Panel with control. This is a pushbutton station consisting of buttons and terminals, located at the package, which can be connected to the DCS for local control at the package | Noted.
69 |  | 04 | Closed | XA | Noted | it is a mistake from us.Please rename to ML(Running) | Noted
70 |  | 04 | Closed | YL | Noted | Noted.
71 |  | 04 | Closed | ML | Noted | it is a mistake from us.Please rename to XA(Fault) | Noted
72 |  | 04 | Closed | if it is push button from LPS, as per spec of project shall be shown as per below figure | At the bottom of page 4 the interlocks have been shown. These are incomming and outgoing signals from the DCS (PLC). The signals are devided in three interlocks sequences. Start (IP-922), Stop (IP-921) and ESD (emergency shut down) (IP-920). The start is to start the K-020 packageand sequence to build up the pressure. Effected PLC signals is the start button and the running light. The stop is to stop the K-020 package in a controlled way. For example the motor will cool down after stopping to prevent continious starting and stopping of the package and shorten the lifetime of the motor. Effected PLC signals is the stop button and the running light. The ESD is to imediatly stop the package in case of an emergency. This interlock will bypass all the timers and cooling down sequences to imediatly stop the package. Effected PLC signals are all the package trips as input (HH or LL), Emergency stop button, Common trip light, running light and operational light. All the signals from Airpack system, which are on the P&ID are noted in this schematic at the botom of page 4. Please let us know if the control is clear on the P&ID or we should have a meeting about this. | Refer to PID Comments(Attachment#1).PLz check and let us know if the control is clear on the Attachment | Thanks for sharing. PID is updated with external signal 8191.
73 |  | 04 | Closed | Remote | Since the button is located at the package you can start the package local. Therefor it is local start button. | The specified legend in PID is related to "remote" push button. | Updated, In the legend it is noted selector switch. On the pushbutton station it is noted that it is to select local mode or remote mode to control the package.
74 |  | 04 | Closed | Remote | Item 73 | The specified legend in PID is related to "remote" push button. | Noted
75 |  | 04 | Closed | 920 | Please explain. Stop (IP-921) can not be the same interlock as emergency stop (IP-920) | 921 is specified for another application at the plant control system. Please refer to comment on PID. | Updated in the next revision. Item 83.
76 |  | 04 | Closed | Should be deleted | All signals need to go to/from the PLC in the DCS to control the package. | Please refer to comment on PID Refer to PID Comments(Attachment#1) | Noted |  | Noted
REV. 05
77 |  | 05 | Closed | Refer to reply sheet for PSV scenario | PSV tube rupture will be taken into account when sizing this, PSV-8204, instrument.
78 |  | 05 | Closed | PZLC 8201 | Positioner is added on to the PCV-8201 instrument. There will be one PIC signal to control te PCV set point and there will be an analog signal from the positioner transmitter to read out the position of the PCV.
79 |  | 05 | Closed | PIC | Updated in the next revision
80 |  | 05 | Closed | ML | Updated in the next revision
81 |  | 05 | Closed | XA | Updated in the next revision
82 |  | 05 | Closed | UY | Updated in the next revision
83 |  | 05 | Closed | To be revised based on Instrument comment | As discussed in the meeting on 31-1-2024. external 8191 signal is on the P&ID.
84
85