## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | ITP CRS | 17735-08
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 1 | 01 |  | Inspection and Test Plan for Air Compressor Package (K-020) | Title is added in the next revision | Noted.
2 | Page 3 | 01 |  | As equipment drawings and data sheets for package have not been issued by vendor till now, final checking of ITP will be done after issuance of above documents. | I see not why equipment drawing and datasheets for package are needed for accepting the ITP. | Noted.
3 | Page 4 | 01 |  | W (Hydrostatic test compressor) | It is not possible to visit the compressor manufacturer from Iran. Therefor it is noted as review | Vendor confirmed at bid stage.
4 | Page 5 | 01 |  | To be added: -Execution of Major Repairs(if any) (H) -NDT -Check of cleanliness after pressure test | -Execution of Major Repairs(if any) (H): Updated in the next revision -NDT : Updated in the next revision -Check of cleanliness after pressure test: Will be added to the hydrotest procedure, since there is no verifying document for this. This is added as note in the ITP | Noted.
5 | Page 5 | 01 |  | +ASME Sec VIII div.1 | Updated accordingly | Noted.
6 | Page 5 | 01 |  | To be added as per agreed ITP: -Execution of Major Repairs(if any) (H) -Check of cleanliness after pressure test | -Execution of Major Repairs(if any) (H): Added to the next revision ITP -Check of cleanliness after pressure test: Added as note to the hydrotest. This will be updated in the hydrotest procedure, since there is no verifying document | Noted.
7 | Page 5 | 01 |  | routine test and type test of motor shall be carried out based on IEC and also mentioned in the ITP | IEC standard is updated in the next revision | Noted. |  |  | Open
8 | Page 8 | 01 |  | R (Nargan, FAT) | Updated in the next revision | Noted. |  |  | Closed
9 | Page 8 | 01 |  | H (LIDCO, FAT) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector.
10 | Page 9 | 01 |  | H (LIDCO, Packing & marking) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector.
11 | Page 9 | 01 |  | H (LIDCO, Release of package) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector.
12 | Page 9 | 01 |  | Please add documents section: Manufacturing Data Book R, R Non conformity / repairs H, H Deviation / concession request H, H | Updated accordingly | Noted and closed.
13
14
15
16
17
18
19
20