## DOC CONTROL (hidden)
VENDOR DOCUMENT SCHEDULE
Project: |  |  | Bushehr MEG Plant Project |  |  |  | IFA: Issued for Approval |  | 1: Approved without Comments
Purchase order: |  |  | MEG20-PO-BP303-021 |  |  |  | IFR: Issued for Review |  | 2: Approved with Minor Comments
Airpack reference: |  |  | 17811-COM |  |  |  | IFI: Issued for Information |  | 3: Approved with Comments
Project manager: |  |  | Kevin Pool/Jeroen Rust |  |  |  | AFC: Approved for Construction |  | 4: Not Approved
Document turn around time: |  |  | 10 | [5 empty] | 5: CRS
Airpack document number | Revision number (00 - 09) | Contractor / Customer Document number | Description | Usage | Document issue date |  | Document return date |  | Aproval Code | Days of delay (5 days = 1 working week) | Transm. nr.
[5 empty] | Planned date | Actual date | Planned date | Actual date
17811-01 | 00 | BU-20-VD-303-DC-DCI-0001 | Vendor print index & schedule | IFA | 2020-11-03 | 2020-11-03 | 2020-11-17 | 2020-11-24 | 2 | 6 | 0002
17811-01 | 01 | BU-20-VD-303-DC-DCI-0001 | Vendor print index & schedule | IFA | 2020-12-08 | 2021-02-16 | 2021-03-02 | 2021-03-09 | 2 | 6 | 0016
17811-01 | 02 | BU-20-VD-303-DC-DCI-0001 | Vendor print index & schedule | IFA | 2021-03-23 | 2021-03-18 | 2021-04-01 |  |  | 22 | 0019
17811-03 | 00 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID | IFA | 2020-10-30 | 2020-10-30 | 2020-11-13 | 2020-11-04 | 2 | -8 | 0001
17811-03 | 00 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID | IFA | 2020-10-30 | 2020-11-16 | 2020-11-19 | 2020-11-19 | 5 | 1 | 0001
17811-03 | 01 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID incl. CRS | IFA | 2020-11-18 | 2020-12-04 | 2020-12-18 |  |  | 96 | 0008
17811-04 | 00 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement | IFA | 2020-10-30 | 2020-10-30 | 2020-11-13 | 2020-11-02 | 2 | -10 | 0001
17811-04 | 01 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement | IFA | 2020-11-16 | 2020-11-23 | 2020-12-07 | 2020-12-01 | 2 | -5 | 0005
17811-04 | 02 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement incl. CRS | IFA | 2020-12-15 | 2021-01-12 | 2021-01-26 |  |  | 69 | 0015
17811-05 | 00 | BU-20-VD-303-IN-DIG-0043 | Wiring Diagram (including Terminal Diagram) incl. junction box LCP wiring diagram and terminal diagram | IFA | 2020-11-24 | 2020-11-24 | 2020-12-08 |  |  | 104 | 0007
17811-06 | 00 | BU-20-VD-303-IN-LST-0034 | I/O list | IFA | 2020-11-27 |  |  |  |  | #VALUE!
17811-07 | 00 | BU-20-VD-303-IN-DWG-0039 | UCP general arrangement drawing & terminal details incl. UCP wiring diagram and BOM | IFA | 2020-12-01 | 2020-11-24 | 2020-12-08 |  |  | 104 | 0007
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | Inspection & test plan (ITP) | IFA |  | 2020-10-30 | 2020-11-13 | 2020-11-09 | 2 | -5 | 0001
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | Inspection & test plan (ITP) | IFA |  | 2020-11-16 | 2020-11-19 | 2020-11-30 | 5 | 8 | 0002
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | Inspection & test plan (ITP) | IFA |  | 2020-12-04 | 2020-12-09 | 2020-12-08 | 5 | -2 | 0004
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | Inspection & test plan (ITP) | IFA |  | 2020-12-04 | 2020-12-09 | 2020-12-15 | 5 | 5 | 0005
17811-08 | 01 | BU-20-VD-303-QC-ITP-0005 | Inspection & test plan (ITP) | IFA | 2020-11-23 | 2020-12-16 | 2020-12-30 |  |  | 88 | 0013
17811-09 | 00 | BU-20-VD-303-PR-LST-0014 | Utility consumption list | IFA | 2020-11-17 |  |  |  |  | #VALUE!
17811-10 | 00 | BU-20-VD-303-EL-DSH-0051 | Compressor motor data sheet | IFA | 2020-11-17 | 2020-12-08 | 2020-12-22 |  |  | 94 | 0010
17811-11A | 00 | BU-20-VD-303-ME-DSH-0022 | Mechanical data sheet for reciprocating compressor | IFA | 2020-11-12 |  |  |  |  | #VALUE!
17811-11B | 00 | BU-20-VD-303-ME-DSH-0017 | After cooler mechanical data sheet | IFA | 2020-11-23 | 2020-12-11 | 2020-12-25 |  |  | 91 | 0012
17811-11C | 00 | BU-20-VD-303-ME-DSH-0027 | Pulsation damper mechanical data sheet | IFA | 2020-11-23 | 2020-12-11 | 2020-12-25 |  |  | 91 | 0012
17811-11D | 00 | BU-20-VD-303-EL-DWG-0021 | Lube oil system heater data sheet and drawing | IFA | 2020-11-24 |  |  |  |  | #VALUE!
17811-11E | 00 | BU-20-VD-303-ME-DSH-0019 | Main oil pump mechanical data sheet | IFA | 2021-03-15 |  |  |  |  | #VALUE!
17811-11F | 00 | BU-20-VD-303-ME-DSH-0020 | Lube oil system filter mechanical data sheet | IFA | 2021-03-15 |  |  |  |  | #VALUE!
17811-12 | 00 | BU-20-VD-303-IN-DSH-0040 | Instrument data sheet | IFA | 2020-11-17 | 2020-11-19 | 2020-12-03 |  |  | 107 | 0004
17811-13 | 00 | BU-20-VD-303-MA-LST-0055 | Commissioning and start-up spare parts list | IFI | 2021-05-14 |  |  |  |  | 49
17811-14 | 00 | BU-20-VD-303-QC-PRC-0009 | Compressor FAT test procedure | IFA | 2021-03-15 |  |  |  |  | 49
17811-15 | 00 | BU-20-VD-303-QC-PRC-0007 | NDE procedure | IFA | 2020-11-07 | 2020-12-08 | 2020-12-22 |  |  | 94 | 0011
17811-16 | 00 | BU-20-VD-303-ME-DWG-0029 | All equipment nameplate drawing | IFA | 2020-12-02 |  |  |  |  | #VALUE!
17811-17 | 00 | BU-20-VD-303-QC-PRC-0006 | Hydrostatic / pneumatic test procedure | IFA | 2020-11-07 | 2020-11-16 | 2020-11-30 |  |  | 110 | 0003
17811-18 | 00 | BU-20-VD-303-PI-DCR-0010 | Surface preparation & painting procedure | IFA | 2020-11-07 | 2020-12-07 | 2020-12-21 |  |  | 95 | 0009
17811-19 | 00 | BU-20-VD-303-DC-INX-0061 | Final data book index | IFA | 2020-11-17 |  |  |  |  | #VALUE!
17811-20 | 00 | BU-20-VD-303-MA-MNL-0012 | Installation, operation & maintenance manual | IFA | after FAT |  |  |  |  | #VALUE!
17811-21 | 00 | BU-20-VD-303-PR-DPH-0046 | Control philosophy | IFA | 2020-01-17 |  |  |  |  | #VALUE!
17811-22 | 00 | BU-20-VD-303-PE-PRC-0008 | Packing, marking shipping & preservation procedure | IFA | 2020-01-07 |  |  |  |  | #VALUE!
17811-23A | 00 | BU-20-VD-303-ME-DWG-0018 | After cooler detail drawing | IFA | 2020-11-23 |  |  |  |  | 115
17811-23B | 00 | BU-20-VD-303-ME-DWG-0028 | Pulsation damper detail drawing | IFA | 2020-11-23 |  |  |  |  | 115
17811-24A | 00 | BU-20-VD-303-ME-CAL-0016 | After cooler mechanical strength calculation | IFI | 2020-11-23 |  |  |  |  | 115
17811-24B | 00 | BU-20-VD-303-ME-CAL-0026 | Pulsation damper mechanical strenght calculation | IFI | 2020-11-23 |  |  |  |  | 115
17811-25 | 00 | BU-20-VD-303-QC-WPS-0011 | PQR / WPS (FOR INFORMATION ONLY) | IFI | 2020-11-07 | 2020-11-16 | 2020-11-30 |  |  | 110 | 0003
17811-27 | 00 | BU-20-VD-303-PR-LST-0042 | Cause & effect chart list | IFA | 2020-11-11 |  |  |  |  | #VALUE!
17811-30 | 00 | BU-20-VD-303-IN-DIG-0036 | Loop diagram | IFA | 2020-12-02 |  |  |  |  | 108
17811-32 | 00 | BU-20-VD-303-IN-DIG-0035 | Logic diagrams -program of UCP - compressor shutdown logic drawing | IFA | 2020-11-17 | 2020-11-24 | 2020-12-08 |  |  | 104 | 0006
17811-36 | 00 | BU-20-VD-303-IN-LST-0037 | Trip & alarm setpoint list | IFA | 2020-01-11 | 2021-01-12 | 2021-01-26 |  |  | 69 | 0015
17811-38 | 00 | BU-20-VD-303-IN-DWG-0033 | Instrument hook-up drawing | IFA | 2020-11-25 | 2020-12-08 | 2020-12-22 |  |  | 94 | 0010
17811-39 | 00 | BU-20-VD-303-EL-DWG-0053 | Compressor motor outline drawing & terminal box wiring diagram | IFA | 2020-01-17 | 2020-12-08 | 2020-12-22 |  |  | 94 | 0011
17811-42 | 00 | BU-20-VD-303-MA-LST-0054 | Two years spare parts list | IFI | 2021-01-31 |  |  |  |  | 65
17811-43 | 00 | BU-20-VD-303-PE-LST-0002 | Sub vendor list | IFI | 2020-11-07 |  |  |  |  | 125
17811-44 | 00 | BU-20-VD-303-ME-DSH-0031 | Data sheet & drawings for strainers | IFA | 2021-02-28 | 2021-02-25 | 2021-03-11 |  |  | 37 | 17
17811-45 | 00 | BU-20-VD-303-IN-DSH-0041 | Calculation & data sheet of control valves/ ON-OFF valves | IFA | 2021-03-17 | 2021-02-25 | 2021-03-11 |  |  | 37 | 0017
17811-46 | 00 | BU-20-VD-303-IN-DIG-0044 | Architecture diagram | IFA | 2021-03-17 | 2021-03-12 | 2021-03-26 |  |  | 26 | 0018
17811-47 | 00 | BU-20-VD-303-IN-DSH-0045 | Workstation drawing and data sheet | IFA | 2021-05-30 |  |  |  |  | -20
17811-48 | 00 | BU-20-VD-303-PR-PRC-0047 | HAZOP and SIL study procedure | IFI | 2021-03-30 |  |  |  |  | 24
17811-49 | 00 | BU-20-VD-303-EL-DIG-0049 | Single line diagram for power distribution panel | IFA | 2021-02-17 |  |  |  |  | 53
17811-50 | 00 | BU-20-VD-303-EL-LST-0050 | Power cable schedule & list | IFA | 2021-02-25 |  |  |  |  | 47
17811-51 | 00 | BU-20-VD-303-ME-LST-0025 | Lubricant list & safety material data sheet | IFA | 2020-11-25 |  |  |  |  | 113
17811-52 | 00 | BU-20-VD-303-IN-DSH-0015 | Calculation & data sheet of safety valve | IFA | 2020-12-01 |  |  |  |  | 109
17811-53 | 00 | BU-20-VD-303-IN-LST-0038 | Instrument cable list & schedule | IFA | 2020-12-05 | 2020-12-16 | 2020-12-30 |  |  | 88 | 0013
17811-54 | 00 | BU-20-VD-303-EL-PUC-0052 | Compressor motor curve | IFA | 2020-12-15 |  |  |  |  | #VALUE!
17811-55 | 00 | BU-20-VD-303-MA-LST-0056 | Special tool list | IFI | 2021-05-30 |  |  |  |  | #VALUE!
17811-56 | 00 | BU-20-VD-303-IN-LST-0057 | Modbus list | IFA | 2021-05-30 |  |  |  |  | #VALUE!
17811-57 | 00 | BU-20-VD-303-EL-DWG-0058 | LV Distribution panel drawing | IFA | 2021-03-10 |  |  |  |  | #VALUE!
17811-59 | 00 | BU-20-VD-303-ME-DWG-0024 | Reciprocating compressor detail drawing with parts list | IFI | 2021-05-30 |  |  |  |  | #VALUE!
17811-65 | 00 | BU-20-VD-303-EL-LST-0048 | Electrical load list | IFA | 2020-11-15 |  |  |  |  | #VALUE!
17811-70 | 00 | BU-20-VD-303-DC-VDR-0062 | Final data book | IFA | after FAT |  |  |  |  | #VALUE!
17811-71 | 00 | BU-20-VD-303-PI-DWG-0030 | 3D model | IFA | with GAD |  |  |  |  | #VALUE!
17811-72 | 00 | BU-20-VD-303-IN-INX-0032 | Instrument index | IFA | 2020-11-15 | 2020-11-24 | 2020-12-08 |  |  | 104 | 0006
17811-73 | 00 | BU-20-VD-303-PC-SCH-0003 | Time schedule | IFA | monthly |  |  |  |  | #VALUE!
17811-74 | 00 | BU-20-VD-303-PC-MRP-0004 | Monthly progress report | IFA | monthly |  |  |  |  | #VALUE!
|  |  |  | IFA | [5 empty] | 31655
Formulas:
IFA: Issued for Approval = IF(ISBLANK([Actual date]),"",WORKDAY([Actual date],D6))
Days of delay (5 days = 1 working week) = IF([Usage]=0,"",IF(AND([Actual date]=0,[IFA: Issued for Approval]=0,[Actual date]=0),NETWORKDAYS([Document issue date],TODAY()),IF(AND([IFA: Issued for Approval]>0,[Actual date]>0),NETWORKDAYS([IFA: Issued for Approval],[Actual date]),IF([IFA: Issued for Approval]>0,NETWORKDAYS([IFA: Issued for Approval],TODAY()),""))))
Document issue date = WORKDAY([Actual date, row above],D6)

## Cover_Sheet
OWNER: |  |  | BUSHEHR PETROCHEMICAL COMPANY MEG PLANT | [6 empty] | CONTRACTOR:
Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors
MC :
|  |  | Project | Area | Phase | Unit | Dis. | Doc. | Seq. | Contract No : 52-98/445
Owner Document Number : |  |  | BU | 20 | VD | 303 | DC | DCI | 0001 | Rev : 00 |  | Page: 1
Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors
00 | 15/04/2021 | Issue For approval |  |  |  |  | MC |  | KP |  | JR
Rev. | Date | Purpose of Issue |  |  |  |  | Prepared |  | Checked |  | Approved |  |  | AC Code
[11 empty] | Class: 1 |  | Phase: P

## Rev_His
Tabulation of Revised Pages
Page | Revision | Page | Revision | Page | Revision
00
1 | *
2 | *
3 | *
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Phase Unit
Dis.
Doc.
Seq.
Vendor Print Index & Schedule(VPIS)
For Reciprocating Compressors
OWNER:
BUSHEHR PETROCHEMICAL COMPANY
MEG PLANT
CONTRACTOR :
Project
Area
Contract No : 52-98/445
Rev. : 00
Page 2
MC :
Owner Document Number :

## VPIS (2)
BUSHEHR PETROCHEMICAL COMPANY
CONTRACTOR:
[11 empty] | PROJECT MANGER | PROJECT COORDINATIOR | PROJECT CONTROL | DCC | PROCESS & SAFETY | MACHINERY | MECHANICAL | CIVIL / STRUCTURE /AR & HVAC | PIPING | ELECTRICAL & TELECOM | INSTRUMENTATION | ENG MANAGER | PROCUREMENT | QC/QA | SITE MANAGER | SITE PLANNING
|  | Document Number |  | Doc. Title: |  |  |  | Rev. | Page: | REV 00
|  | BU-20-VD-303-DC-DCI-0001 |  | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors |  |  |  | 00 |  | PAGE 3
Vendor Name: |  | Air pack Co |  | Order Description: | Reciprocating Compressors
P.O. Number: |  |  |  | Issue Date: | 15/04/2021
No. | Client Document Number | Discipline* | Doc. Size | Document Description | Doc. Class (1/2/3) | MC / Client Class | 1st Issue Date (Sample : 04-Dec-11) | AFC Plan Issue Date (Sample : 04-Dec-11) | Doc Weight% | REMARK
1 | BU-20-VD-303-DC-DCI-0001 | MA/QC | A4 | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors | 1 | 1 |  |  |  |  | I | I | I |  | C | C/R | I | C | C | C | C | I | I | C
2 | BU-20-VD-303-PE-LST-0002 | PE | A4 | SUB VENDOR LIST | 1 | 1 |  |  |  |  | I | I | I |  | I | C | I | I | I | I | I | I | C/R | I
3 | BU-20-VD-303-PC-SCH-0003 | PC | A4 | TIME SCHEDULE | 1 | 2
4 | BU-20-VD-303-PC-MRP-0004 | PC | A4 | MONTHLY PROGRESS REPORT | 2 | 2
5 | BU-20-VD-303-QC-ITP-0005 | QC | A4 | Inspection and Test Plan (ITP) for Reciprocating Compressor-MEG-303 | 1 | 1 |  |  |  |  | I | I | I |  | I | C | I | I | I | C | I | I | I | C/R
6 | BU-20-VD-303-QC-PRC-0006 | QC | A4 | HYDROSTATIC/ PNEUMATIC TEST PROCEDURE | 1 | 2
7 | BU-20-VD-303-QC-PRC-0007 | QC | A4 | NDE PROCEDURE | 1 | 2 |  |  |  | INCLUDING WELDING MAP & N.D.T. TABLE LIST
8 | BU-20-VD-303-PE-PRC-0008 | PE | A4 | PACKING, MARKING , SHIPPING AND PRESERVATION PROCEDURE | 1 | 2
9 | BU-20-VD-303-QC-PRC-0009 | QC | A4 | COMPRESSOR FAT TEST PROCEDURE | 1 | 2
10 | BU-20-VD-303-PI-DCR-0010 | PI | A4 | SURFACE PREPARATION & PAINTING PROCEDURE | 1 | 2
11 | BU-20-VD-303-QC-WPS-0011 | QC | A4 | W.P.S & P.Q.R. | 1 | 2
12 | BU-20-VD-303-MA-MNL-0012 | MA | A4 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | 1 | 2
13 | BU-20-VD-303-PR-DWG-0013 | PR | A3 | COMPRESSOR PACKAGE P &ID | 1 | 1 |  |  |  |  | I | I | I |  | C/R | C/R | I | I | C | C | C | I | I | I
14 | BU-20-VD-303-PR-LST-0014 | PR | A4 | UTILITY CONSUMPTION LIST | 1 | 2
15 | BU-20-VD-303-IN-DSH-0015 | IN | A4 | CALCULATION AND DATA SHEET OF SAFETY VALVE | 1 | 2
16 | BU-20-VD-303-ME-CAL-0016 | ME | A4 | AFTERCOOLER MECHANICAL STRENGTH CALCULATION | 1 | 2
17 | BU-20-VD-303-ME-DSH-0017 | ME | A4 | AFTERCOOLER MECHANICAL DATA SHEET | 1 | 2
18 | BU-20-VD-303-ME-DWG-0018 | ME | A3 | AFTERCOOLER DETAIL DRAWING | 1 | 2
19 | BU-20-VD-303-ME-DSH-0019 | ME | A4 | MAIN OIL PUMP MECHANICAL DATA SHEET | 1 | 2
20 | BU-20-VD-303-ME-DSH-0020 | ME | A4 | LUBE OIL SYSTEM FILTER MECHANICAL DATA SHEET | 1 | 2
21 | BU-20-VD-303-EL-DWG-0021 | EL | A3 | LUBE OIL SYSTEM HEATER DATA SHEET AND DRAWING | 1 | 2
22 | BU-20-VD-303-ME-DSH-0022 | ME | A4 | MECHANICAL DATA SHEET FOR RECIPROCATING COMPRESSOR | 1 | 1 |  |  |  |  | I | I | I |  | C | C/R | I | C | C | C | C | I | I | I
23 | BU-20-VD-303-ME-DWG-0023 | ME | A3 | RECIPROCATING COMPRESSOR GENERAL ARRANGEMENT | 1 | 1 |  |  |  |  | I | I | I |  | I | C/R | I | C | C | C | C | I | I | I
24 | BU-20-VD-303-ME-DWG-0024 | ME | A3 | RECIPROCATING COMPRESSOR DETAIL DRAWING WITH PART LIST | 1 | 2
25 | BU-20-VD-303-ME-LST-0025 | ME | A4 | LUBRICANT LIST AND MATERIAL SAFETY DATA SHEET | 1 | 2
26 | BU-20-VD-303-ME-CAL-0026 | ME | A4 | PULSATION DAMPENERS MECHANICAL STRENGTH CALCULATION | 1 | 2
27 | BU-20-VD-303-ME-DSH-0027 | ME | A4 | PULSATION DAMPENERS MECHANICAL DATA SHEET | 1 | 2
28 | BU-20-VD-303-ME-DWG-0028 | ME | A3 | PULSATION DAMPENERS DETAIL DRAWING | 1 | 2
29 | BU-20-VD-303-ME-DWG-0029 | ME | A3 | ALL EQUIPMENT NAME PLATE DRAWING | 1 | 2
30 | BU-20-VD-303-PI-DWG-0030 | PI | A3 | 3D MODEL | 1 | 1 |  |  |  |  | I | I | I |  | I | C/R | I | C | C/R | C | C | I | I | I
31 | BU-20-VD-303-ME-DSH-0031 | ME | A4 | DATA SHEET & DRAWING FOR STRAINERS | 1 | 2
32 | BU-20-VD-303-IN-INX-0032 | IN | A4 | INSTRUMENT INDEX | 1 | 2
33 | BU-20-VD-303-IN-DWG-0033 | IN | A3 | INSTRUMENT HOOK UP DRAWING | 1 | 2
34 | BU-20-VD-303-IN-LST-0034 | IN | A4 | I/O LIST | 1 | 2
35 | BU-20-VD-303-IN-DIG-0035 | IN | A4 | LOGIC DIAGRAMS -PROGRAM OF UCP-COMPRESSOR SHUTDOWN LOGIC DRAWING | 1 | 2
36 | BU-20-VD-303-IN-DIG-0036 | IN | A4 | LOOP DIAGRAM | 1 | 2
37 | BU-20-VD-303-IN-LST-0037 | IN | A4 | TRIP & ALARM SET POINT LIST | 1 | 2
38 | BU-20-VD-303-IN-LST-0038 | IN | A4 | INSTRUMENT CABLE LIST & SCHEDULE | 1 | 2
39 | BU-20-VD-303-IN-DWG-0039 | IN | A3 | UCP GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS | 1 | 2
40 | BU-20-VD-303-IN-DSH-0040 | IN | A4 | INSTRUMENT DATA SHEET | 1 | 2
41 | BU-20-VD-303-IN-DSH-0041 | IN | A4 | CALCULATION AND DATA SHEET OF CONTROL VALVES/ ON-OFF VALVES | 1 | 2
42 | BU-20-VD-303-PR-LST-0042 | PR | A4 | CAUSE & EFFECT CHARTS LIST | 1 | 2
43 | BU-20-VD-303-IN-DIG-0043 | EL/IN | A4 | WIRING DIAGRAM | 1 | 2
44 | BU-20-VD-303-IN-DIG-0044 | IN | A4 | ARCHITECTURE DIAGRAM | 1 | 2
45 | BU-20-VD-303-IN-DSH-0045 | IN | A4 | WORKSTATION DRAWING AND DATA SHEET | 1 | 2
46 | BU-20-VD-303-PR-DPH-0046 | IN/PR | A4 | CONTROL PHILOSOPHY | 1 | 2
47 | BU-20-VD-303-PR-PRC-0047 | IN/PR | A4 | HAZOP AND SIL STUDY PROCEDURE | 1 | 2
48 | BU-20-VD-303-EL-LST-0048 | EL | A4 | ELECTRICAL LOAD LIST | 1 | 2
49 | BU-20-VD-303-EL-DIG-0049 | EL | A4 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL | 1 | 2
50 | BU-20-VD-303-EL-LST-0050 | EL | A4 | POWER CABLE SCHEDULE & LIST | 1 | 2
51 | BU-20-VD-303-EL-DSH-0051 | EL | A4 | COMPRESSOR MOTOR DATA SHEET | 1 | 1 |  |  |  |  | I | I | I |  | I | C/R | I | I | I | C/R | I | I | I | I
52 | BU-20-VD-303-EL-PUC-0052 | EL | A4 | COMPRESSOR MOTOR CURVE | 1 | 2
53 | BU-20-VD-303-EL-DWG-0053 | EL | A3 | COMPRESSOR MOTOR OUTLINE DRAWING & TERMINAL BOX WIRING DRAWING | 1 | 2
54 | BU-20-VD-303-MA-LST-0054 | MA | A4 | TWO YEARS SPARE PART LIST IN SPLIR FORMAT | 1 | 1 |  |  |  |  | I | I | I |  | I | C/R | I | C | C | C | C | I | C/R | I
55 | BU-20-VD-303-MA-LST-0055 | MA | A4 | COMMISSIONING AND START-UP SPARE PART LIST IN SPLIR FORMAT | 1 | 1 |  |  |  |  | I | I | I |  | I | C/R | I | C | C | C | C | I | C/R | I
56 | BU-20-VD-303-MA-LST-0056 | MA | A4 | SPECIAL TOOLS LIST | 1 | 2
57 | BU-20-VD-303-IN-LST-0057 | IN | A4 | Modbus List | 1 | 2
58 | BU-20-VD-303-EL-DWG-0058 | EL | A3 | LV Distribution panel drawing | 1 | 2
59 | BU-20-VD-303-DC-INX-0061 | MA/QC | A4 | FINAL DATA BOOK INDEX For Reciprocating Compressors | 1 | 1 |  |  |  |  | I | I | I |  | C | C/R | I | C | C | C | C | I | C | C
60 | BU-20-VD-303-DC-VDR-0062 | MA/QC | A4 | FINAL DATA BOOK For Reciprocating Compressors | 1 | 2
*Discipline of documents shall be selected From APPENDIX 2 |  |  |  |  | Document Class: 1: For approval 2: For review 3: For information
Category Type: 1: Client approval is necessary 2: Contractor approval is necessary