## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 06/Jan/2022 | Rev.: 03
|  | Comment Sheet Ref.No.: | Doc Description: TRIP & ALARM SETPOINT LIST FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00075 | Doc. No.: BU-20-VD-303-IN-LST-0037
|  | Transmittal Date: 06/Jan/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CHCE Reply | Vendor Clarification
1 | Prerequisite document such as I/O list shall be issued. |  |  | ok |  |  | I/O list is not issued yet | IO list is issued CES reply : Closed.
2 | 1- Reply sheet of each document shall be sent separately. Pease do not put reply sheet of instrument compressor in nitrogen compressor. 2- Document to be revised based on comments on P&ID. |  |  | 1, Noted. 2, Noted. |  |  | Closed.
3 | Reply sheet shall be submitted by vendor. Please refer to comment on PID for instrument numbering procedure. |  |  | Noted. |  |  | Noted.
4 | To be specified |  |  | Noted. It will be incorporated. |  |  | Noted.
5 | Oc |  |  | Noted. It will be incorporated. |  |  | Noted.
6 | PID no. to be modified as per VPIS |  |  | Noted. It will be incorporated. |  |  | Noted.
7 | Please recheck. |  |  | Noted. It will be checked. |  |  | Closed.
8 | Please send AFC revision of this document after P&ID and I/O list finalized. |  |  | OK. IO List is issued. |  |  | Closed.
9 | Please refer to the comment on DSH. C-1002 is in service continuously. |  |  | Noted |  |  | Closed.