## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 23/Feb/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: P&ID FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00100 | Doc. No.: BU-20-VD-303-PR-DWG-0013
|  | Transmittal Date: 23/Feb/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Suction/Discharge pressure and temperature and design condition of each stage must be reported separately. |  |  | noted and updated CES reply: Closed.
2 | OP and DP shall be rechecked and revised. |  |  | noted and updated CES reply: Closed.
3 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated CES reply: Closed.
4 | All PSVs inlet/outlet size rating and orifice designation as per API letter shall be specified. |  |  | Noted and updated, however calculation is awaited CES reply: Closed.
5 | To be deleted |  |  | noted and updated CES reply: Closed.
6 | Valve type schematic shall be modified (globe) |  |  | noted and updated CES reply: Closed.
7 | Please specify process connection size |  |  | noted and updated CES reply: Closed.
8 | Since compressor discharge pressure is 23.5, The set points shall be checked again. |  |  | noted and updated CES reply: Please refer to latest comment on P&ID.
9 | BU-20-D-100-PR-PID-101 11/2"-NM-1021-539D(H) |  |  | noted and updated CES reply: Closed.
10 | BU-20-D-100-PR-PID-101 2"-CWS-1013-500C(N) |  |  | noted and updated CES reply: Closed.
11 | PG-10161 |  |  | noted and updated CES reply: Closed.
12 | Please be advised that as per above picture cooling water line 2" can be prepared by client in vendor battery limit .AIRPACK is expected to check the cooling water line again and select suitable line size. |  |  | we have checked the calculation and we have updated it to 2" to be on the safe side CES reply: Closed.
13 | BU-20-D-100-PR-PID-101 2"-NL-1002-511C(N) |  |  | noted and updated CES reply: Closed.
14 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated CES reply: Closed.
15 | XCS-108 |  |  | noted and updated CES reply: Closed.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
2