## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 28/Feb/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00104 | Doc. No.: BU-20-VD-303-ME-DSH-0027
|  | Transmittal Date: 28/Feb/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Mechanical items will be checked after sending pulsation dampener calculation. |  |  | Noted, however please confirm datasheet is ok, calculation will be submitted soon CES reply: Closed.
2 | Following items shall be added to data sheet: 1- Dampener thickness. 2- RAL number of pulsation dampener. 3- Maximum Allowable Compressor Cylinder Flange Pressure Pulsation as per clause 7.9.4.2.5.2.1 of API618. 4- Maximum Allowable Pulsation Limits at and Beyond Line-side Nozzles of Pulsation Suppression Devices as per clause 7.9.4.2.5.2.2.1 of API 618. 5- Pulsation dampener design approach shall be added to document. 6- Maximum Allowable Pressure Drop as per clause 7.9.4.2.5.3.1 of API 618. 7- Capacity of pulsation dampener will be checked after specifying cylinder stroke and cylinder diameter. 8- DESIGN APPROACH STUDY SHALL BE ADDED. |  |  | 1.Noted and added CES reply: Closed. 2. Noted and added CES reply: Closed. 3. Noted and added CES reply: Closed. 4. Noted and added CES reply: Closed. 5. Noted and added CES reply: Closed. 6. Noted and added CES reply: Closed. 7. Noted CES reply: Closed. 8. Noted and added CES reply: Closed.
3 | Shall be specified in next revision. |  |  | updated CES reply: Closed.
4 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
5 | 3 mm. |  |  | updated CES reply: Closed.
6 | Discrepancy with PID. |  |  | updated CES reply: Closed.
7 | Discrepancy with PID. On PID DP is reported 21 bara. |  |  | updated CES reply: Closed.
8 | Discrepancy with PID. On PID DP is reported 35.25 bara. |  |  | updated CES reply: Closed.
9 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
10 | 1300#???? |  |  | updated CES reply: Closed.
11 | 3 mm. |  |  | updated CES reply: Closed.
12
13
14
15
16
17
18
19