## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 11/Mar/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00112 | Doc. No.: BU-20-VD-303-ME-DSH-0022
|  | Transmittal Date: 11/Mar/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | LEVELING SCREWS, SUB SOLE PLATES, CHOKE BLOCKS and shims are required. |  |  | Not required for mounting on a foundation, this will be mounted with anchor bolts, levelling is not required. CES REPLY (Dec.18,2021): It is in AIRPACK responsibility to consider all required facilities for safe and reliable installation of compressor. Noted and closed
2 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID CES REPLY (Dec.18,2021): Closed.
3 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used CES REPLY (Dec.18,2021): Closed. But base material of mentioned component shall be specified.
4 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details CES REPLY (Dec.18,2021): We are waiting to receive new data. Added
5 | All Notes shall be revised as per attached file. |  |  | This is what was provided in this format CES REPLY (Dec.18,2021): Notes in page 20 of BU-20-VD-303-ME-DSH-0022 are related to instrument air compressor. Therefor, notes shall be revised as per attached file. See TCL Clause M33.Added
6 | Compressor is V-BELT |  |  | updated CES reply (Mar. 16,2022): Closed.
7 | How it is possible to provide liner with 48 mm thickness for cylinder with 160mm??????? |  |  | because compressor is suitable for much larger piston CES reply (Mar. 16,2022): Closed.
8 | Size shall be added. 1'', 2'', 3''..... |  |  | updated CES reply (Mar. 16,2022): Closed.
9 | Please check it again |  |  | checked and confirmed CES reply (Mar. 16,2022): Closed.
10 | These notes shall be revised as per attached file. |  |  | updated CES reply (Mar. 16,2022): Closed.