## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 11/Mar/2022 | Rev.: 03
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00112 | Doc. No.: BU-20-VD-303-ME-DSH-0075
|  | Transmittal Date: 11/Mar/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to following termodynamic formula T2/T1 = (P2/P1) (K-1/K), Discharge temperature is 148 C in adiabatic condition. |  |  | This comes from our calculation program for this type of compressor, I can’t change it CES reply: Closed.
2 | Mass flow rate does not match with compressor gas power. Gas power= H2 - H1 |  |  | It does as the actual flow is higher then the required flow CES reply: Closed.
3 | Pulsation dampener shall be equipped with moisture removal. |  |  | There will be a manual drain valve, but not automatic as the inlet air is dry CES reply: Closed. Please revie page 16.
4 | Insulation wherever is required, shall be done by AIRPACK. |  |  | Only PP CES reply: Please clarify what is PP? Airpack reply: PP is Personell protection
5 | Perfomance required |  |  | these charts are not available CES reply: Closed.
6 | Remaining data shall be completed. |  |  | Rod packing not cooled CES reply: Selection of suitable material as per API618 is in vendor responsibility. Airpack reply: suitable material is selected
7 | PLAN D ????????? |  |  | What does this comment mean CES reply: Closed.
8 | ent and drain connection shall be considered by vendor. |  |  | Drain will be considerd CES reply: Closed.
9 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID CES reply (Dec.18,2021): Closed.
10 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used CES reply (Dec.18,2021): Closed. But CES comment shall be replied. Airpack Reply: noted as per comments below
11 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details CES REPLY (Dec.18,2021): We are waiting to received new data.
12 | All modification shall be shown cloudy with revision mark |  |  | All modifications are marked yellow CHE REPLY (Mar.16,2022): Closed.
13 | Nozzle class shall be added |  |  | equivalent nozzle classes have been added, since this is a non standard flange CHE REPLY (Mar.16,2022): Closed.
14 | Repetitive comment: 1- Piston rod material shall be specified. 2- Piston rod hardness material shall be specified. |  |  | updated CHE REPLY (Mar.16,2022): Closed.
15 | Repetitive comment: Please clarify about base material of 79RL. |  |  | This is a polymer material CHE REPLY (Mar.16,2022): See the comment in document.
16 | Please clarify about base material of SK703 E. |  |  | This is a polymer material CHE REPLY (Mar.16,2022): Closed.
17 | Compressor is single stage with 2cylinder |  |  | Noted and updated CHE REPLY (Mar.16,2022): Closed.
18 | his document is supposed to be the vendor data sheet. The mentioned switches must be specified. |  |  | Noted and updated CHE REPLY (Mar.16,2022): Closed.
19 | the temperature of cooling water is 35. the approach must be double checked. |  |  | this is correct as per cooler calculation and datashet. CHE REPLY (Mar.16,2022): Closed.
12
12
12
12
12
12
12
12
12
12
12
12
12