## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 26/Apr/2022 | Rev.:00
|  | Comment Sheet Ref.No.: | Doc Description: Workstation drawing and data sheet
|  | Transmittal No.: APCES-V-00125 | Doc. No.: BU-20-VD-303-IN-DSH-0045
|  | Transmittal Date: 26/Apr/2022 | Doc Rev.: 00
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply
1 | Catalogue for industrial workstation and laptop shall be added as attachment. |  |  | Catalogue will not be provided, only datasheet and rawing |  |  | Noted, workstations and laptops shall be industrial type and mentioned in data sheet
2 | Drawing of Laptop and monitor of OWS shall be specified. |  |  | Noted will be specified in next revision |  |  | Noted.
3 | As per project specification for package the following specifications shall be considered for PC: • Processor type core i7 minimum • Main memory (RAM) : 8GB (min) • Hard drive : 500GB (min) • Hard drive redundancy and raid controller : double and raid #1 • Power supply : redundant • keyboards : 104 keys qwerty keyboard and industrial membrane keyboard with at least 20 extra Function keys. • Mouse: Industrial mouse and industrial track ball. |  |  | Please mention where this is mentioned in the specification, we have checked but we have not found this information. |  |  | ESS for Package Instrumentation, 1216-DE-00-IN-ESS-603, page 25 section 3.1.7
4 | High resolution 21 inch LCD color monitor. |  |  | Noted will be added |  |  | Noted.
5 | Licensed software shall be original and provided with the relevant certificates. Original software shall be provided for each engineering and operation function. |  |  | Noted, software details will be added |  |  | Noted.
6 | The workstation set shall be industrial type. |  |  | this workstation is used in desktop and industrial environment. |  |  | Industrial type shall be mentioned in data sheet.
7 | Laptop specification shall be added to this document. |  |  | Noted will be added in next revision |  |  | Noted.
8 | Two industrial work station for compressors (20-C-1002 and 20-C-7080) shall be consider. |  |  | Only one as per the TCL AIRPACK confirms that One set of industrial workstation is to be supplied by AIRPACK as well as One laptop for PLC programing is in AIRPACK scope of supply. |  |  | As per unprice list (part of material requisition) each compressor is equipped with individual laptop and workstation. Therefor, two sets laptop and two sets workstation shall be supplied by vendor.
9
10
11
12