## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 31/Aug/2023 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: Two years spare parts list
|  | Transmittal No.: APCES-V-00220 | Doc. No.: BU-20-VD-303-ME-LST-0054
|  | Transmittal Date: 31/Aug/2023 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | All items mentioned in attached file shall be supplied by AIRPACK for commissioning spare part list. |  |  | noted and completed CES reply (Jul.29,2023): Please see the comment given in document.
2 | Model number of VT, PT, TT, and FT shall be specified. |  |  | noted and completed CES reply (Jul.29,2023): Manufacturer model number as per instrument data sheet shall be written.
3 | DE or NDE shall be specified. Also, code of bearing as per motor data sheet shall be written. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
4 | Pulsation dampeners. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
5 | Relay, barrier and etc. shall be written in individual row. |  |  | noted and completed CES reply (Jul.29,2023): Closed. Please see the document.
614:23B1614:2214:24B1614:2214:261414:51 | Exact quantity shall be written not the percent. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
7 | - Size of all o-ring and gasket shall be specified. - Some items are missing. For example fan of electrical motor, tube of heat exchanger and etc. See general comment in page 1.I16 |  |  | will not be included according to TQ that was received on 20-02-2023 CES reply (Jul.29,2023): Closed, for material of compressor part. However there are some items wich are missing. Please see the document.
8 | Exact material shall be specified. |  |  | will not be included according to TQ that was received on 20-02-2023 CES reply (Jul.29,2023): Closed
9 | Project document for example instrument data sheet or etc. shall be written in reference document column. |  |  | noted and completed CES reply (Jul.29,2023): Please see the comment given in document.
10 | Piston ring and guide ring shall be written in individual row. |  |  | noted and completed CES reply (Jul.29,2023): Closed
11 | - Spar part of each compressor shall be specified in individual page. - Electrical motor, instrumentation, mechanical items, PLC and etc. shall be specified in individual columns of each compressor page. Please see the sample SPLIR form. |  |  | noted and completed CES reply (Jul.29,2023): Please see the explanation given in page there.
12 | Manner of filling SPLIR format shall be same as attached file. |  |  | see above CES reply (Jul.29,2023): Please see the sample file again.
13
14 | Other main equipment of compressor 1002 shall be written here in individual column(Electrical motor, pulsation dampener, heat exchanger, Instrumentation) |  |  | it's al part of the same compressor package, so no need to include as main component, will not be changed CES reply (Sep.10,2023): This is not the manner of fill-in SPLIR form. Please see file attached to REV.01 of spare part list. One sample document of MEG plant has been attached to REV.01. Comment shall be implemented.
15 | Description is hide. |  |  | incorperated CES reply (Sep.10,2023): Closed.
16 | 1 |  |  | incorperated CES reply (Sep.10,2023): Closed.
17 | Two component for one compressor 2x1=2 Above criteria shall be used for all cells. |  |  | Noted and updated CES reply (Sep.10,2023): Closed.
18 | Two, as per compressor data sheet. |  |  | it is only one, total is 2 one suction and one discharge valve CES reply (Sep.10,2023): As per detail drawing and part list of compressor, quantity of suction valve of each stage is two sets and the same for discharge valves.
19 | Stage one or two shall be specified. Please use following description since spring is needed: - Suction valve (complete set) - Discharge valve (complete set) |  |  | noted and incorperated CES reply (Sep.10,2023): Complete set is missing.
20 | 6 as per contract (material requisition) |  |  | 3 is correct per set CES reply (Sep.10,2023): Since there are two sets of valves (in each suction and discharge valves of each stages), based on contract 300% shall be supplied. It means 6 sets.
21 | - Radial oil seal gaskets (893, 840) for compressor 1002 are missing. - Liner of both stages are missing. - Oil gland seal / wiper is missing. - Gland gas (1027) is missing. - Tube, bolts and gaskets for heat exchanger of C-10002 is missing. Interstage and after cooler shall be written separately |  |  | - Radial oil seal gaskets not part of 2 year spare parts list as agreed in P.O. - Liner not part of 2 year spare parts list as agreed in P.O. - Oil gland /seal not part of 2 year spare parts list as agreed in P.O. - Gland gas (1027) - Tube, bolts and gaskets for heat exchanger of C-10002 are not part of this 2 years spare parts lis as agreed in P.O. and only sold as a set. therefore will not be mentioned seperately. CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Comment shall be implemeneted.
22 | Oil pump seal ring is missing. |  |  | Not part of the agreed spare parts list in P.O. CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Comment shall be implemeneted. |  |  | Above list is not a reference. Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL.
23 | Instrumentation related to compressor 1002 shall be written along this row. |  |  | instrumentation is written in the common part, as only one common instrument is supplied CES reply (Sep.10,2023): Closed. However, comment 35 and 36 shall be considered.
24 | There is not such a code in motor data sheet. |  |  | this the complete code for the motor it is correct. CES reply (Sep.10,2023): Closed.
25 | Fan and terminal block of motor is missing. |  |  | Not part of the agreed spare parts list in P.O. CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Comment shall be implemeneted.
26 | Motor data sheet as a reference shall be added. |  |  | noted and incorperated CES reply (Sep.10,2023): Closed.
27 | Inlet and discharge pulsation dampener (each stage) shall be written separately. |  |  | this is only supplied as a set, since we normally do not supply gaskets as a spare. So willl not be updated CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Comment shall be implemeneted.
28 | Unit of gasket shall be changed into PCS. Also, as per contract 200% gasket shall be supplied. |  |  | only as a set, and 200% already included CES reply (Sep.10,2023): Unit shall be reported as a PCS in order to make sure that 200% gasket will be suplied.
29 | Please write spare part of compressor 7080 in individual page. |  |  | No CES reply (Sep.10,2023): Comment shall be implemeneted.
30 | All comments given for compressor 1002 is applicable for compressor 7080. |  |  | please don't give comments like this, give specific comments, also please find our responses as above. CES reply (Sep.10,2023): Since the comments of both compressor are same, extera comment is meaningless. Foe example, total quantity of installed suction valve of compressor 7080 is 2 sets, considering 300% spara, 6 sets suction valves shall be supplied.
31 | Instrumentation related to compressor 7080 shall be written along this row. |  |  | instrumentation is written in the common part, as only one common instrument is supplied CES reply (Sep.10,2023): Closed.
32 | Model, IP and EX class of all transmitters shall be written as per data sheet. One set means that one TT for each model is needed. |  |  | No, they are all the same class, also this is not part of the spare parts list. CES reply (Sep.10,2023): Model, IP and EX class of all transmitters shall be written as per data sheet. One set means that one TT for each model is needed. Model, IP and EX class of all transmitters are needed to make sure that supplied transmitters are same as installed transmitter.
33 | Instrument data sheet shall be written as reference document. |  |  | noted and incorperated CES reply (Sep.10,2023): Closed.
34 | All rows related to common section shall be deleted. Instrument of each compressor shall be written in a row related to that equipment. |  |  | these are supplied as common spare and therefore will not be changes CES reply (Sep.10,2023): Closed. However, comment 35 and 36 shall be considered.
35 | Range of PG and IP shall be specified as per data sheet. One set means that for each range, one PG shall be supplied (For example, with reference to instrument data sheet of C-1002 there are 4PG with different range. Therefore, 4 PG for compressor 1002 shal be supplied by vendor). |  |  | as per P.O. only on PG included in 2 years spare list CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Also, the rest data requested in comment 35 shall be implemented by vendor.
36 | Range and IP of TG shall be written. |  |  | No, they are all the same class, also this is not part of the spare parts list. CES reply (Sep.10,2023): Range is needed to make sure that the supplied instrument is same as installed instrument. Also, this data will be used by inspector. Comment shall be implemeneted.
37 | Reference document of PLC and LV distribution panel shall be written in s |  |  | noted and incorperated CES reply (Sep.10,2023): Closed.
38 | Following items related to instrumentations are missing as per material requisition (MR shall be completely followed by AIRPACK): - Probe of vibration transmitters . - Extension cable for probes of VT. - Resistance thermometer. - I/O cards. - Main cards. - Power supply (AC, DC) as per LV distribution panel document. - Convertor. - Relay of LV distribution panel |  |  | - probe not included in agreed spare parts list CES reply (Sep.10,2023): See material requisition. - extension cables not included in agreed spare parts list CES reply (Sep.10,2023): See material requisition. - TG already included CES reply (Sep.10,2023): Closed. - I/O cards part of spare in panel as agreed - Main card part of spare in panel as agreed - power supply part of spare in panel as agreed - converte is barrier - relay of LV is same as main panel. CES reply (Sep.10,2023): Two years spare part of both compressors is based on list attached to material requsition. Please see clause G14 of TCL. Power supply with model number as per distribution panel drawing and UCP drawing shall be written. IO card and main cards are missing as well.
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56