## DOC CONTROL (hidden)
VENDOR DOCUMENT SCHEDULE
Project: |  |  | Bushehr MEG Plant Project |  |  |  | IFC |  | AP
Purchase order: |  |  | MEG20-PO-BP303-021 |  |  |  | IFA |  | AN
Airpack reference: |  |  | 17811-COM |  |  |  | IFI |  | CM
Project manager: |  |  | Kevin Pool/Jeroen Rust |  |  |  | AFC |  | RE
Document turn around time: |  |  | 10 |  |  |  | AB |  | NC
Airpack document number | Revision number (00 - 09) | Contractor / Customer Document number | Description | Usage | Document issue date |  | Document return date |  | Aproval Code | Days of delay (5 days = 1 working week) | Transm. nr.
[5 empty] | Planned date | Actual date | Planned date | Actual date
17811-01 | 00 | BU-20-VD-303-DC-DCI-0001 | Vendor print index & schedule | IFA | 2020-11-03 | 2020-11-03 | 2020-11-17 | 2020-11-24 | 2 | 6 | 0002
17811-01 | 01 | BU-20-VD-303-DC-DCI-0001 | Vendor print index & schedule | IFA | 2020-12-08 | 2021-02-16 | 2021-03-02 | 2021-03-09 | 2 | 6 | 0016
17811-01 | 00 | BU-20-VD-303-DC-DCI-0001 | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors | IFA | 2021-03-23 | 2021-03-18 | 2021-04-01 | 2021-05-04 | CM | 24 | 0019
17811-01 | 01 | BU-20-VD-303-DC-DCI-0001 | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors | IFA | 2021-06-04 | 2021-06-03 | 2021-06-17 | 2021-07-12 | AN | 18 | 0005
17811-01 | 02 | BU-20-VD-303-DC-DCI-0001 | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors | IFA | 2021-07-26 | 2021-07-22 | 2021-08-05 | 2021-08-30 | AN | 18 | 0013
17811-01 | 03 | BU-20-VD-303-DC-DCI-0001 | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors | IFA | 2021-09-13 |  |  |  |  | #VALUE!
17811-03 | 00 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID | IFA | 2020-10-30 | 2020-10-30 | 2020-11-13 | 2020-11-04 | 2 | -8 | 0001
17811-03 | 00 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID | IFA | 2020-10-30 | 2020-11-16 | 2020-11-19 | 2020-11-19 | 5 | 1 | 0001
17811-03 | 00 | BU-20-VD-303-PR-DWG-0013 | Compressor package P&ID incl. CRS | IFA | 2020-11-18 | 2020-12-04 | 2020-12-18 | 2021-05-19 | CM | 109 | 0008
17811-03A | 01 | BU-20-VD-303-PR-DWG-0013 | P&ID FOR NITROGEN GAS BOOSTER | IFA | 2021-07-31 |  |  |  |  | #VALUE!
17811-03B | 01 | BU-20-VD-303-PR-DWG-0066 | P&ID FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-06-11 | 2021-06-11 | 2021-06-25 | 2021-07-26 | CM | 22 | 0006
17811-03B | 02 | BU-20-VD-303-PR-DWG-0066 | P&ID FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 | 2021-08-10 | 2021-08-24 |  |  | 12 | 0014
17811-04 | 00 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement | IFA | 2020-10-30 | 2020-10-30 | 2020-11-13 | 2020-11-02 | 2 | -10 | 0001
17811-04 | 01 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement | IFA | 2020-11-16 | 2020-11-23 | 2020-12-07 | 2020-12-01 | 2 | -5 | 0005
17811-04 | 02 | BU-20-VD-303-ME-DWG-0023 | Reciprocating compressor general arrangement incl. CRS | IFA | 2020-12-15 | 2021-01-12 | 2021-01-26 | 2021-05-25 | CM | 86 | 0015
17811-04A | 03 | BU-20-VD-303-ME-DWG-0023 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-08-14 |  |  |  |  | #VALUE!
17811-04B | 03 | BU-20-VD-303-ME-DWG-0076 | GENERAL ARRANGEMENT DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-06-18 | 2021-06-30 | 2021-07-14 | 2021-07-27 | CM | 10 | 0010
17811-04B | 04 | BU-20-VD-303-ME-DWG-0076 | GENERAL ARRANGEMENT DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-10 | 2021-08-12 | 2021-08-26 |  |  | 10 | 0015
17811-05 | 00 | BU-20-VD-303-IN-DIG-0043 | UCP/LCP/JB WIRING DIAGRAM | IFA | 2020-11-24 | 2020-11-24 | 2020-12-08 | 2021-05-11 | CM | 111 | 0007
17811-05A | 01 | BU-20-VD-303-IN-DIG-0043 | UCP/LCP/JB WIRING DIAGRAM FOR NITROGEN GAS BOOSTER | IFA | 2021-08-14 |  |  |  |  | #VALUE!
17811-05B | 01 | BU-20-VD-303-IN-DIG-0093 | UCP/LCP/JB WIRING DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-02 | 2021-07-02 | 2021-07-16 | 2021-07-14 | CM | -3 | 0011
17811-05B | 02 | BU-20-VD-303-IN-DIG-0093 | UCP/LCP/JB WIRING DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-28 |  |  |  |  | #VALUE!
17811-06A | 00 | BU-20-VD-303-IN-LST-0034 | I/O LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-08-14 |  |  |  |  | #VALUE!
17811-06B | 00 | BU-20-VD-303-IN-LST-0084 | I/O LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-07 | 00 | BU-20-VD-303-IN-DWG-0039 | UCP/LCP/JB GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS | IFA | 2020-12-01 | 2020-11-24 | 2020-12-08 | 2021-05-11 | CM | 111 | 0007
17811-07A | 01 | BU-20-VD-303-IN-DWG-0039 | UCP/LCP/JB GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS FOR NITROGEN GAS BOOSTER | IFA | 2021-08-14 |  |  |  |  | #VALUE!
17811-07B | 01 | BU-20-VD-303-IN-DWG-0089 | UCP/LCP/JB GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) | IFA |  | 2020-10-30 | 2020-11-13 | 2020-11-09 | 2 | -5 | 0001
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) | IFA |  | 2020-11-16 | 2020-11-19 | 2020-11-30 | 5 | 8 | 0002
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) | IFA |  | 2020-12-04 | 2020-12-09 | 2020-12-08 | 5 | -2 | 0004
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) | IFA |  | 2020-12-04 | 2020-12-09 | 2020-12-15 | 5 | 5 | 0005
17811-08 | 00 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) | IFA | 2020-11-23 | 2020-12-16 | 2020-12-30 | 2021-05-19 | CM | 101 | 0013
17811-08 | 01 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) INCL. CRS | IFA | 2021-06-18 | 2021-06-17 | 2021-07-01 | 2021-08-02 | CM | 23 | 0007
17811-08 | 01 | CRS | INSPECTION & TEST PLAN (ITP) | IFA | 2021-06-18 | 2021-08-11 | 2021-08-13 | X | NC | #VALUE! | 0007
17811-08 | 02 | BU-20-VD-303-QC-ITP-0005 | INSPECTION & TEST PLAN (ITP) INCL. CRS | IFA | 2021-08-16 | 2021-08-31 | 2021-09-14 |  |  | -5 | 0016
17811-09A | 00 | BU-20-VD-303-PR-LST-0014 | UTILITY CONSUMPTION LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-08-25 |  |  |  |  | #VALUE!
17811-09B | 00 | BU-20-VD-303-PR-LST-0067 | UTILITY CONSUMPTION LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-25 |  |  |  |  | #VALUE!
17811-10 | 00 | BU-20-VD-303-EL-DSH-0051 | Compressor motor data sheet | IFA | 2020-11-17 | 2020-12-08 | 2020-12-22 | 2021-05-19 | CM | 107 | 0010
17811-10A | 01 | BU-20-VD-303-EL-DSH-0051 | COMPRESSOR MOTOR DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-18 |  |  |  |  | #VALUE!
17811-10B | 01 | BU-20-VD-303-EL-DSH-0099 | COMPRESSOR MOTOR DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-06-18 | 2021-06-24 | 2021-07-08 | 2021-07-26 | CM | 13 | 0009
17811-10B | 02 | BU-20-VD-303-EL-DSH-0099 | COMPRESSOR MOTOR DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-11A | 00 | BU-20-VD-303-ME-DSH-0022 | MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-11B | 00 | BU-20-VD-303-ME-DSH-0017 | After cooler mechanical data sheet | IFA | 2020-11-23 | 2020-12-11 | 2020-12-25 | 2021-05-04 | CM | 93 | 0012
17811-11B | 01 | BU-20-VD-303-ME-DSH-0017 | AFTER COOLER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-16 |  |  |  |  | #VALUE!
17811-11C | 00 | BU-20-VD-303-ME-DSH-0027 | Pulsation damper mechanical data sheet | IFA | 2020-11-23 | 2020-12-11 | 2020-12-25 | 2021-05-04 | CM | 93 | 0012
17811-11C | 01 | BU-20-VD-303-ME-DSH-0027 | PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-16 |  |  |  |  | #VALUE!
17811-11D | 00 | BU-20-VD-303-EL-DWG-0021 | LUBE OIL SYSTEM HEATER DATA SHEET AND DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-11E | 00 | BU-20-VD-303-ME-DSH-0019 | MAIN OIL PUMP MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-11F | 00 | BU-20-VD-303-ME-DSH-0020 | LUBE OIL SYSTEM FILTER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-11G | 00 | BU-20-VD-303-ME-DSH-0075 | MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 | 2021-08-12 | 2021-08-26 | 2021-08-30 | CM | 3 | 0015
17811-11G | 01 | BU-20-VD-303-ME-DSH-0075 | MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-09-13 |  |  |  |  | #VALUE!
17811-11H | 01 | BU-20-VD-303-ME-DSH-0070 | AFTER COOLER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-16 |  |  |  |  | #VALUE!
17811-11I | 01 | BU-20-VD-303-ME-DSH-0028 | PULSATION DAMPER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-16 |  |  |  |  | #VALUE!
17811-11J | 00 | BU-20-VD-303-EL-DWG-0074 | LUBE OIL SYSTEM HEATER DATA SHEET AND DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-11K | 00 | BU-20-VD-303-ME-DSH-0072 | MAIN OIL PUMP MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-11L | 00 | BU-20-VD-303-ME-DSH-0073 | LUBE OIL SYSTEM FILTER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-23 |  |  |  |  | #VALUE!
17811-12 | 00 | BU-20-VD-303-IN-DSH-0040 | Instrument data sheet | IFA | 2020-11-17 | 2020-11-19 | 2020-12-03 | 2021-05-11 | CM | 114 | 0004
17811-12A | 01 | BU-20-VD-303-IN-DSH-0040 | INSTRUMENT DATA SHEET FOR NITROGEN GAS BOOSTER | IFA | 2021-08-26 |  |  |  |  | #VALUE!
17811-12B | 01 | BU-20-VD-303-IN-DSH-0090 | INSTRUMENT DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-26 |  |  |  |  | #VALUE!
17811-13 | 00 | BU-20-VD-303-ME-LST-0055 | Commissioning and start-up spare parts list | IFI | 2021-11-17 |  |  |  |  | 49
17811-14 | 00 | BU-20-VD-303-QC-PRC-0009 | Compressor FAT test procedure | IFA | 2021-09-30 |  |  |  |  | 49
17811-15 | 00 | BU-20-VD-303-QC-PRC-0007 | NDE procedure | IFA | 2020-11-07 | 2020-12-08 | 2020-12-22 | 2021-06-14 | CM | 125 | 0011
17811-15 | 01 | BU-20-VD-303-QC-PRC-0007 | NDE procedure | IFA | 2021-08-14 |  |  |  |  | #VALUE!
17811-16 | 00 | BU-20-VD-303-ME-DWG-0029 | ALL EQUIPMENT NAME PLATE DRAWING | IFA | 2021-09-07 |  |  |  |  | #VALUE!
17811-17 | 00 | BU-20-VD-303-QC-PRC-0006 | Hydrostatic / pneumatic test procedure | IFA | 2020-11-07 | 2020-11-16 | 2020-11-30 | 2021-06-21 | CM | 146 | 0003
17811-17 | 00 | CRS | Hydrostatic / pneumatic test procedure | IFA | 2020-11-07 | 2021-06-22 | 2021-06-25 |  |  | 54 | 0006
17811-17 | 01 | BU-20-VD-303-QC-PRC-0006 | Hydrostatic / pneumatic test procedure | IFA | 2021-07-30 |  |  |  |  | #VALUE!
17811-18 | 00 | BU-20-VD-303-PI-DCR-0010 | Surface preparation & painting procedure | IFA | 2020-11-07 | 2020-12-07 | 2020-12-21 | 2021-05-04 | CM | 97 | 0009
17811-18 | 01 | BU-20-VD-303-PI-DCR-0010 | Surface preparation & painting procedure | IFA | 2021-07-30 |  |  |  |  | #VALUE!
17811-19 | 00 | BU-20-VD-303-DC-INX-0061 | FINAL DATA BOOK INDEX FOR RECIPROCATING COMPRESSOR &NITROGEN GAS BOOSTER | IFA | 2021-07-30 |  |  |  |  | #VALUE!
17811-20 | 00 | BU-20-VD-303-ME-MNL-0012 | Installation, operation & maintenance manual | IFA | after FAT |  |  |  |  | #VALUE!
17811-21A | 00 | BU-20-VD-303-PR-DPH-0046 | CONTROL PHILOSOPHY FOR NITROGEN GAS BOOSTER | IFA | 2021-09-25 |  |  |  |  | #VALUE!
17811-21B | 00 | BU-20-VD-303-PR-DPH-0095 | CONTROL PHILOSOPHY FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-09-25 |  |  |  |  | #VALUE!
17811-22 | 00 | BU-20-VD-303-PE-PRC-0008 | Packing, marking shipping & preservation procedure | IFA | 2021-09-30 |  |  |  |  | #VALUE!
17811-23A | 00 | BU-20-VD-303-ME-DWG-0018 | AFTER COOLER DETAIL DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-09-03 |  |  |  |  | 4
17811-23B | 00 | BU-20-VD-303-ME-DWG-0071 | AFTER COOLER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-30 |  |  |  |  | 8
17811-23C | 00 | BU-20-VD-303-ME-DWG-0079 | PULSATION DAMPER DETAIL DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | 8
17811-23D | 00 | BU-20-VD-303-ME-DWG-0080 | PULSATION DAMPER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-30 |  |  |  |  | 8
17811-24A | 00 | BU-20-VD-303-ME-CAL-0016 | AFTER COOLER MECHANICAL STRENGHT CALCULATION FOR NITROGEN GAS BOOSTER | IFI | 2021-08-30 |  |  |  |  | 8
17811-24B | 00 | BU-20-VD-303-ME-CAL-0069 | AFTER COOLER MECHANICAL STRENGHT CALCULATION FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFI | 2021-08-30 |  |  |  |  | 8
17811-24C | 00 | BU-20-VD-303-ME-CAL-0026 | PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR NITROGEN GAS BOOSTER | IFI | 2021-08-30 |  |  |  |  | 8
17811-24D | 00 | BU-20-VD-303-ME-CAL-0078 | PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFI | 2021-08-30 |  |  |  |  | 8
17811-25 | 00 | BU-20-VD-303-QC-WPS-0011 | PQR / WPS (FOR INFORMATION ONLY) | IFI | 2020-11-07 | 2020-11-16 | 2020-11-30 | 2021-07-05 | AP | 156 | 0003
17811-27A | 00 | BU-20-VD-303-PR-LST-0042 | CAUSE & EFFECT CHART LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-09-25 |  |  |  |  | #VALUE!
17811-27B | 00 | BU-20-VD-303-PR-LST-0092 | CAUSE & EFFECT CHART LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-09-18 |  |  |  |  | #VALUE!
17811-30A | 00 | BU-20-VD-303-IN-DIG-0036 | LOOP DIAGRAM FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | 8
17811-30B | 00 | BU-20-VD-303-IN-DIG-0086 | LOOP DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-16 |  |  |  |  | 18
17811-32 | 00 | BU-20-VD-303-IN-DIG-0035 | Logic diagrams -program of UCP - compressor shutdown logic drawing | IFA | 2020-11-17 | 2020-11-24 | 2020-12-08 | 2021-05-11 | CM | 111 | 0006
17811-32A | 01 | BU-20-VD-303-IN-DIG-0035 | LOGIC DIAGRAMS-PROGRAM OF UCP - COMPRESSOR SHUTDOWN LOGIC DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-32B | 01 | BU-20-VD-303-IN-DIG-0085 | LOGIC DIAGRAMS-PROGRAM OF UCP - COMPRESSOR SHUTDOWN LOGIC DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-36 | 00 | BU-20-VD-303-IN-LST-0037 | Trip & alarm setpoint list | IFA | 2020-01-11 | 2021-01-12 | 2021-01-26 | 2021-05-11 | CM | 76 | 0015
17811-36A | 01 | BU-20-VD-303-IN-LST-0037 | TRIP & ALARM SETPOINT LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-36B | 01 | BU-20-VD-303-IN-LST-0087 | TRIP & ALARM SETPOINT LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-38 | 00 | BU-20-VD-303-IN-DWG-0033 | Instrument hook-up drawing | IFA | 2020-11-25 | 2020-12-08 | 2020-12-22 | 2021-05-11 | CM | 101 | 0010
17811-38 | 01 | BU-20-VD-303-IN-DWG-0033 | Instrument hook-up drawing | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-39 | 00 | BU-20-VD-303-EL-DWG-0053 | Compressor motor outline drawing & terminal box wiring diagram | IFA | 2020-01-17 | 2020-12-08 | 2020-12-22 | 2021-05-11 | CM | 101 | 0011
17811-39A | 01 | BU-20-VD-303-EL-DWG-0053 | COMPRESSOR MOTOR OUTLINE DRAWING & TERMINAL BOX WIRING DIAGRAM FOR NITROGEN GAS BOOSTER | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-39B | 01 | BU-20-VD-303-EL-DWG-0101 | COMPRESSOR MOTOR OUTLINE DRAWING & TERMINAL BOX WIRING DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-42 | 00 | BU-20-VD-303-ME-LST-0054 | Two years spare parts list | IFI | 2021-10-17 |  |  |  |  | -28
17811-43 | 00 | BU-20-VD-303-PE-LST-0002 | Sub vendor list | IFI | 2021-06-11 | 2021-06-21 | 2021-07-05 |  |  | 48 | 0008
17811-44 | 00 | BU-20-VD-303-ME-DSH-0031 | Data sheet & drawings for strainers | IFA | 2021-02-28 | 2021-02-25 | 2021-03-11 | 2021-05-04 | CM | 39 | 0017
17811-44A | 01 | BU-20-VD-303-ME-DSH-0031 | DATA SHEET & DRAWINGS FOR STRAINERS FOR NITROGEN GAS BOOSTER | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-44B | 01 | BU-20-VD-303-ME-DSH-0082 | DATA SHEET & DRAWINGS FOR STRAINERS FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-45 | 00 | BU-20-VD-303-IN-DSH-0041 | Calculation & data sheet of control valves/ ON-OFF valves | IFA | 2021-03-17 | 2021-02-25 | 2021-03-11 | 2021-05-11 | CM | 44 | 0017
17811-45A | 01 | BU-20-VD-303-IN-DSH-0041 | CALCULATION & DATA SHEET OF CONTROL VALVES / ON-OFF VALVES FOR NITROGEN GAS BOOSTER | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-45B | 01 | BU-20-VD-303-IN-DSH-0091 | CALCULATION & DATA SHEET OF CONTROL VALVES / ON-OFF VALVES FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-09 |  |  |  |  | #VALUE!
17811-46 | 00 | BU-20-VD-303-IN-DIG-0044 | Architecture diagram | IFA | 2021-03-17 | 2021-03-12 | 2021-03-26 | 2021-05-11 | CM | 33 | 0018
17811-46A | 01 | BU-20-VD-303-IN-DIG-0044 | ARCHITECTURE DIAGRAM FOR NITROGEN GAS BOOSTER | IFA | 2021-09-02 |  |  |  |  | #VALUE!
17811-46B | 01 | BU-20-VD-303-IN-DIG-0094 | ARCHITECTURE DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-02 |  |  |  |  | #VALUE!
17811-47 | 00 | BU-20-VD-303-IN-DSH-0045 | WORKSTATION DRAWING AND DATA SHEET | IFA | 2021-08-30 |  |  |  |  | 8
17811-48 | 00 | BU-20-VD-303-PR-PRC-0047 | HAZOP AND SIL STUDY PROCEDURE | IFI | 2021-08-02 |  |  |  |  | 28
17811-49A | 00 | BU-20-VD-303-EL-DIG-0049 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL FOR NITGROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | 8
17811-49B | 00 | BU-20-VD-303-EL-DIG-0097 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-06-25 | 2021-07-02 | 2021-07-16 | 2021-07-14 | CM | -3 | 0011
17811-49B | 01 | BU-20-VD-303-EL-DIG-0097 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-28 |  |  |  |  | #VALUE!
17811-50A | 00 | BU-20-VD-303-EL-LST-0050 | POWER CABLE SCHEDULE & LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-07-25 |  |  |  |  | 33
17811-50B | 00 | BU-20-VD-303-EL-LST-0098 | POWER CABLE SCHEDULE & LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-28 |  |  |  |  | 31
17811-51 | 00 | BU-20-VD-303-ME-LST-0025 | LUBRICANT LIST AND MATERIAL SAFETY DATA SHEET | IFA | 2021-09-17 |  |  |  |  | -8
17811-52A | 00 | BU-20-VD-303-IN-DSH-0015 | CALCULATION & DATA SHEET OF SAFETY VALVE FOR NITROGEN GAS BOOSTER | IFA | 2021-08-16 |  |  |  |  | 18
17811-52B | 00 | BU-20-VD-303-IN-DSH-0068 | CALCULATION & DATA SHEET OF SAFETY VALVE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-16 |  |  |  |  | 18
17811-53 | 00 | BU-20-VD-303-IN-LST-0038 | Instrument cable list & schedule | IFA | 2020-12-05 | 2020-12-16 | 2020-12-30 | 2021-05-11 | CM | 95 | 0013
17811-53A | 01 | BU-20-VD-303-IN-LST-0038 | INSTRUMENT CABLE LIST & SHEDULE FOR NITROGEN GAS BOOSTER | IFA | 2021-07-25 |  |  |  |  | #VALUE!
17811-53B | 01 | BU-20-VD-303-IN-LST-0088 | INSTRUMENT CABLE LIST & SHEDULE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-25 |  |  |  |  | #VALUE!
17811-54A | 00 | BU-20-VD-303-EL-PUC-0052 | COMPRESSOR MOTOR CURVE FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-54B | 00 | BU-20-VD-303-EL-PUC-0100 | COMPRESSOR MOTOR CURVE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-55 | 00 | BU-20-VD-303-ME-LST-0056 | Special tool list | IFI | 2021-09-30 |  |  |  |  | #VALUE!
17811-56 | 00 | BU-20-VD-303-IN-LST-0057 | Modbus list | IFA | 2021-05-30 | 2021-04-16 | 2021-04-30 | 2021-05-04 | CM | 3 | 0003
17811-56A | 01 | BU-20-VD-303-IN-LST-0057 | MODBUS LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-56B | 01 | BU-20-VD-303-IN-LST-0102 | MODBUS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-30 |  |  |  |  | #VALUE!
17811-57A | 00 | BU-20-VD-303-EL-DWG-0058 | LV DISTRIBUTION PANEL DRAWING FOR NITROGEN GAS BOOSTER | IFA | 2021-07-25 |  |  |  |  | #VALUE!
17811-57B | 00 | BU-20-VD-303-EL-DWG-0059 | LV DISTRIBUTION PANEL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-25 |  |  |  |  | #VALUE!
17811-59A | 00 | BU-20-VD-303-ME-DWG-0024 | RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR NITROGEN GAS BOOSTER | IFI | 2021-10-17 |  |  |  |  | #VALUE!
17811-59B | 00 | BU-20-VD-303-ME-DWG-0077 | RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFI | 2021-10-17 |  |  |  |  | #VALUE!
17811-65A | 00 | BU-20-VD-303-EL-LST-0048 | ELECTRICAL LOAD LIST FOR NITROGEN GAS BOOSTER | IFA | 2021-08-25 |  |  |  |  | #VALUE!
17811-65B | 00 | BU-20-VD-303-EL-LST-0096 | ELECTRICAL LOAD LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-07-26 |  |  |  |  | #VALUE!
17811-70 | 00 | BU-20-VD-303-DC-VDR-0062 | FINAL DATA BOOK FOR RECIPROCATING COMPRESSOR &NITROGEN GAS BOOSTER | IFI | after FAT |  |  |  |  | #VALUE!
17811-71A | 00 | BU-20-VD-303-PI-DWG-0030 | 3D MODEL FOR NITROGEN GAS BOOSTER | IFA | with GAD |  |  |  |  | #VALUE!
17811-71B | 00 | BU-20-VD-303-PI-DWG-0081 | 3D MODEL FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | with GAD |  |  |  |  | #VALUE!
17811-72 | 00 | BU-20-VD-303-IN-INX-0032 | Instrument index | IFA | 2020-11-15 | 2020-11-24 | 2020-12-08 | 2021-05-11 | CM | 111 | 0006
17811-72A | 01 | BU-20-VD-303-IN-INX-0032 | INSTRUMENT INDEX FOR NITROGEN GAS BOOSTER | IFA | 2021-07-30 |  |  |  |  | #VALUE!
17811-72B | 01 | BU-20-VD-303-IN-INX-0083 | INSTRUMENT INDEX FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | IFA | 2021-08-07 |  |  |  |  | #VALUE!
17811-73 | 00 | BU-20-VD-303-PC-SCH-0003 | TIME SCHEDULE | IFA | monthly | 2021-07-21 | 2021-08-04 |  |  | 26
17811-74 | 00 | BU-20-VD-303-PC-MRP-0004 | Monthly progress report | IFR | monthly |  |  |  |  | #VALUE!
17811-75 | 00 | BU-20-VD-303-PR-LST-0063 | TIE-IN POINT LIST | IFA | 2021-08-01 |  |  |  |  | 28
17811-76 | 00 | BU-20-VD-303-PR-LST-0064 | PIPING VALVE LIST | IFA | 2021-08-01
17811-77 | 00 | BU-20-VD-303-PR-LST-0065 | PIPING LINE LIST | IFA | 2021-08-01 |  |  |  |  | 28
Formulas:
IFC = IF(ISBLANK([Actual date]),"",WORKDAY([Actual date],D6))
Days of delay (5 days = 1 working week) = IF([Usage]=0,"",IF(AND([Actual date]=0,[IFC]=0,[Actual date]=0),NETWORKDAYS([Document issue date],TODAY()),IF(AND([IFC]>0,[Actual date]>0),NETWORKDAYS([IFC],[Actual date]),IF([IFC]>0,NETWORKDAYS([IFC],TODAY()),""))))
Document issue date = WORKDAY([Actual date, row above],D6)
Note on L13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: opnieuw begonnen met tellen van de transmittals

## VPIS
BUSHEHR PETROCHEMICAL COMPANY
|  | Document Number |  |  | Doc. Title: |  |  |  | Rev. | Page: 3 of 3
|  | BU-20-VD-303-DC-DCI-0001 |  |  | Vendor Print Index & Schedule(VPIS) For Reciprocating Compressors |  |  |  | 02
Vendor Name: |  | Air pack Co |  |  | Order Description: | Reciprocating Compressors
P.O. Number: |  |  |  |  | Issue Date:
No. | Client Document Number | Vendor Document Number | Discipline* | Doc. Size | Document Description | Doc. Class (1/2/3) | MC / Client Class | 1st Issue Date (Sample : 04-Dec-11) | AFC Plan Issue Date (Sample : 04-Dec-11) | Doc Weight% | Remarks
1 | BU-20-VD-303-DC-DCI-0001 | BU-20-VD-303-DC-DCI-0001 | ME/QC | A4 | Vendor Print Index & Schedule (VPIS) For Reciprocating Compressors & NITROGEN GAS BOOSTER For Reciprocating Compressors & NITROGEN GAS BOOSTER | 1 | 1 | 2021-06-04 |  |  |  | 17811-01
2 | BU-20-VD-303-PE-LST-0002 | BU-20-VD-303-PE-LST-0002 | PE | A4 | SUB VENDOR LIST | 1 | 1 | 2021-06-11 |  |  |  | 17811-43
3 | BU-20-VD-303-PC-SCH-0003 | BU-20-VD-303-PC-SCH-0003 | PC | A4 | TIME SCHEDULE | 1 | 2 | MONTHLY |  |  |  | 17811-73
4 | BU-20-VD-303-PC-MRP-0004 | BU-20-VD-303-PC-MRP-0004 | PC | A4 | MONTHLY PROGRESS REPORT | 2 | 2 | MONTHLY |  |  |  | 17811-74
5 | BU-20-VD-303-QC-ITP-0005 | BU-20-VD-303-QC-ITP-0005 | QC | A4 | Inspection and Test Plan (ITP) for Reciprocating Compressor-MEG-303 | 1 | 1 | 2021-06-18 |  |  |  | 17811-08
6 | BU-20-VD-303-QC-PRC-0006 | BU-20-VD-303-QC-PRC-0006 | QC | A4 | HYDROSTATIC/ PNEUMATIC TEST PROCEDURE | 1 | 2 | 2020-11-16 |  |  |  | 17811-17
7 | BU-20-VD-303-QC-PRC-0007 | BU-20-VD-303-QC-PRC-0007 | QC | A4 | NDE PROCEDURE | 1 | 2 | 2020-12-08 |  |  | INCLUDING WELDING MAP & N.D.T. TABLE LIST | 17811-15
8 | BU-20-VD-303-PE-PRC-0008 | BU-20-VD-303-PE-PRC-0008 | PE | A4 | PACKING, MARKING , SHIPPING AND PRESERVATION PROCEDURE | 1 | 2 | 2021-09-30 |  |  |  | 17811-22
9 | BU-20-VD-303-QC-PRC-0009 | BU-20-VD-303-QC-PRC-0009 | QC | A4 | COMPRESSOR FAT TEST PROCEDURE | 1 | 2 | 2021-07-30 |  |  | INCLUDING PERFORMANCE TEST PROCEDURE AND MECHANICAL RUNNING TEST PROCEDURE | 17811-14
10 | BU-20-VD-303-PI-DCR-0010 | BU-20-VD-303-PI-DCR-0010 | PI | A4 | SURFACE PREPARATION & PAINTING PROCEDURE | 1 | 2 | 2021-06-05 |  |  |  | 17811-18
11 | BU-20-VD-303-QC-WPS-0011 | BU-20-VD-303-QC-WPS-0011 | QC | A4 | W.P.S & P.Q.R. | 1 | 2 | 2020-01-16 |  |  |  | 17811-25
12 | BU-20-VD-303-ME-MNL-0012 | BU-20-VD-303-ME-MNL-0012 | ME | A4 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | 1 | 2 | AFTER FAT |  |  |  | 17811-20
13 | BU-20-VD-303-PR-DWG-0013 | BU-20-VD-303-PR-DWG-0013 | PR | A3 | P&ID FOR NITROGEN GAS BOOSTER | 1 | 1 | 2021-06-11 |  |  |  | 17811-03A
14 | BU-20-VD-303-PR-LST-0014 | BU-20-VD-303-PR-LST-0014 | PR | A3 | UTILITY CONSUMPTION LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-25 |  |  |  | 17811-09A
15 | BU-20-VD-303-IN-DSH-0015 | BU-20-VD-303-IN-DSH-0015 | IN | A4 | CALCULATION & DATA SHEET OF SAFETY VALVE FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-16 |  |  |  | 17811-52A
16 | BU-20-VD-303-ME-CAL-0016 | BU-20-VD-303-ME-CAL-0016 | ME | A4 | AFTER COOLER MECHANICAL STRENGHT CALCULATION FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-30 |  |  |  | 17811-24A
17 | BU-20-VD-303-ME-DSH-0017 | BU-20-VD-303-ME-DSH-0017 | ME | A4 | AFTER COOLER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-16 |  |  |  | 17811-11B
18 | BU-20-VD-303-ME-DWG-0018 | BU-20-VD-303-ME-DWG-0018 | ME | A4 | AFTER COOLER DETAIL DRAWING FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-09-02 |  |  |  | 17811-23A
19 | BU-20-VD-303-ME-DSH-0019 | BU-20-VD-303-ME-DSH-0019 | ME | A4 | MAIN OIL PUMP MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-23 |  |  |  | 17811-11E
20 | BU-20-VD-303-ME-DSH-0020 | BU-20-VD-303-ME-DSH-0020 | ME | A4 | LUBE OIL SYSTEM FILTER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-23 |  |  |  | 17811-11F
21 | BU-20-VD-303-EL-DWG-0021 | BU-20-VD-303-EL-DWG-0021 | EL | A4 | LUBE OIL SYSTEM HEATER DATA SHEET AND DRAWING FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-23 |  |  |  | 17811-11D
22 | BU-20-VD-303-ME-DSH-0022 | BU-20-VD-303-ME-DSH-0022 | ME | A4 | MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 1 | 2021-07-16 |  |  |  | 17811-11A
23 | BU-20-VD-303-ME-DWG-0023 | BU-20-VD-303-ME-DWG-0023 | ME | A3 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS BOOSTER | 1 | 1 | 2021-07-30 |  |  |  | 17811-04A
24 | BU-20-VD-303-ME-DWG-0024 | BU-20-VD-303-ME-DWG-0024 | ME | A3 | RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-10-17 |  |  |  | 17811-59A
25 | BU-20-VD-303-ME-LST-0025 | BU-20-VD-303-ME-LST-0025 | ME | A4 | LUBRICANT LIST AND MATERIAL SAFETY DATA SHEET | 1 | 2 | 2021-09-17 |  |  |  | 17811-51
26 | BU-20-VD-303-ME-CAL-0026 | BU-20-VD-303-ME-CAL-0026 | ME | A4 | PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-30 |  |  |  | 17811-24C
27 | BU-20-VD-303-ME-DSH-0027 | BU-20-VD-303-ME-DSH-0027 | ME | A4 | PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-23 |  |  |  | 17811-11C
28 | BU-20-VD-303-ME-DSH-0028 | BU-20-VD-303-ME-DSH-0028 | ME | A4 | PULSATION DAMPER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-16 |  |  |  | 17811-11I
29 | BU-20-VD-303-ME-DWG-0029 | BU-20-VD-303-ME-DWG-0029 | ME | A3 | ALL EQUIPMENT NAME PLATE DRAWING | 1 | 2 | 2021-09-07 |  |  |  | 17811-16
30 | BU-20-VD-303-PI-DWG-0030 | BU-20-VD-303-PI-DWG-0030 | PI | A3 | 3D MODEL FOR NITROGEN GAS BOOSTER | 1 | 1 | 2021-07-23 |  |  |  | 17811-71A
31 | BU-20-VD-303-ME-DSH-0031 | BU-20-VD-303-ME-DSH-0031 | ME | A4 | DATA SHEET & DRAWINGS FOR STRAINERS FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-09 |  |  |  | 17811-44A
32 | BU-20-VD-303-IN-INX-0032 | BU-20-VD-303-IN-INX-0032 | IN | A4 | INSTRUMENT INDEX FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-09 |  |  |  | 17811-72A
33 | BU-20-VD-303-IN-DWG-0033 | BU-20-VD-303-IN-DWG-0033 | IN | A3 | INSTRUMENT HOOK UP DRAWING | 1 | 2 | 2021-06-18 |  |  |  | 17811-38
34 | BU-20-VD-303-IN-LST-0034 | BU-20-VD-303-IN-LST-0034 | IN | A3 | I/O LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-14 |  |  |  | 17811-06A
35 | BU-20-VD-303-IN-DIG-0035 | BU-20-VD-303-IN-DIG-0035 | IN | A3 | LOGIC DIAGRAMS-PROGRAM OF UCP - COMPRESSOR SHUTDOWN LOGIC DRAWING FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-09-17 |  |  |  | 17811-32A
36 | BU-20-VD-303-IN-DIG-0036 | BU-20-VD-303-IN-DIG-0036 | IN | A3 | LOOP DIAGRAM FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-30 |  |  |  | 17811-30A
37 | BU-20-VD-303-IN-LST-0037 | BU-20-VD-303-IN-LST-0037 | IN | A4 | TRIP & ALARM SETPOINT LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-09-17 |  |  |  | 17811-36A
38 | BU-20-VD-303-IN-LST-0038 | BU-20-VD-303-IN-LST-0038 | IN | A4 | INSTRUMENT CABLE LIST & SHEDULE FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-30 |  |  |  | 17811-53A
39 | BU-20-VD-303-IN-DWG-0039 | BU-20-VD-303-IN-DWG-0039 | IN | A4 | UCP/LCP/JB GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-30 |  |  |  | 17811-07A
40 | BU-20-VD-303-IN-DSH-0040 | BU-20-VD-303-IN-DSH-0040 | IN | A4 | INSTRUMENT DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-16 |  |  |  | 17811-12A
41 | BU-20-VD-303-IN-DSH-0041 | BU-20-VD-303-IN-DSH-0041 | IN | A4 | CALCULATION & DATA SHEET OF CONTROL VALVES / ON-OFF VALVES FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-16 |  |  |  | 17811-45A
42 | BU-20-VD-303-PR-LST-0042 | BU-20-VD-303-PR-LST-0042 | PR | A3 | CAUSE & EFFECT CHART LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-09-25 |  |  |  | 17811-27A
43 | BU-20-VD-303-IN-DIG-0043 | BU-20-VD-303-IN-DIG-0043 | EL/IN | A3 | UCP/LCP/JB WIRING DIAGRAM FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-30 |  |  |  | 17811-05A
44 | BU-20-VD-303-IN-DIG-0044 | BU-20-VD-303-IN-DIG-0044 | IN | A3 | ARCHITECTURE DIAGRAM FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-30 |  |  |  | 17811-46A
45 | BU-20-VD-303-IN-DSH-0045 | BU-20-VD-303-IN-DSH-0045 | IN | A3 | WORKSTATION DRAWING AND DATA SHEET | 1 | 2 | 2021-08-30 |  |  |  | 17811-47
46 | BU-20-VD-303-PR-DPH-0046 | BU-20-VD-303-PR-DPH-0046 | IN/PR | A3 | CONTROL PHILOSOPHY FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-09-25 |  |  |  | 17811-21A
47 | BU-20-VD-303-PR-PRC-0047 | BU-20-VD-303-PR-PRC-0047 | IN/PR | A4 | HAZOP AND SIL STUDY PROCEDURE | 1 | 2 | 2021-08-02 |  |  |  | 17811-48
48 | BU-20-VD-303-EL-LST-0048 | BU-20-VD-303-EL-LST-0048 | EL | A4 | ELECTRICAL LOAD LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-25 |  |  |  | 17811-65A
49 | BU-20-VD-303-EL-DIG-0049 | BU-20-VD-303-EL-DIG-0049 | EL | A4 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL FOR NITGROGEN GAS BOOSTER | 1 | 2 | 2021-08-30 |  |  |  | 17811-49A
50 | BU-20-VD-303-EL-LST-0050 | BU-20-VD-303-EL-LST-0050 | EL | A4 | POWER CABLE SCHEDULE & LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-25 |  |  |  | 17811-50A
51 | BU-20-VD-303-EL-DSH-0051 | BU-20-VD-303-EL-DSH-0051 | EL | A3 | COMPRESSOR MOTOR DATA SHEET FOR NITROGEN GAS BOOSTER | 1 | 1 | 2021-07-02 |  |  |  | 17811-10A
52 | BU-20-VD-303-EL-PUC-0052 | BU-20-VD-303-EL-PUC-0052 | EL | A4 | COMPRESSOR MOTOR CURVE FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-09 |  |  |  | 17811-54A
53 | BU-20-VD-303-EL-DWG-0053 | BU-20-VD-303-EL-DWG-0053 | EL | A4 | COMPRESSOR MOTOR OUTLINE DRAWING & TERMINAL BOX WIRING DIAGRAM FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-09 |  |  |  | 17811-39A
54 | BU-20-VD-303-ME-LST-0054 | BU-20-VD-303-ME-LST-0054 | ME | A4 | TWO YEARS SPARE PART LIST IN SPLIR FORMAT | 1 | 1 | 2021-07-09 |  |  |  | 17811-42
55 | BU-20-VD-303-ME-LST-0055 | BU-20-VD-303-ME-LST-0055 | ME | A4 | COMMISSIONING AND START-UP SPARE PART LIST IN SPLIR FORMAT | 1 | 1 | 2021-11-17 |  |  |  | 17811-13
56 | BU-20-VD-303-ME-LST-0056 | BU-20-VD-303-ME-LST-0056 | ME | A4 | SPECIAL TOOLS LIST | 1 | 2 | 2021-09-30 |  |  |  | 17811-55
57 | BU-20-VD-303-IN-LST-0057 | BU-20-VD-303-IN-LST-0057 | IN | A4 | MODBUS LIST FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-16 |  |  |  | 17811-56A
58 | BU-20-VD-303-EL-DWG-0058 | BU-20-VD-303-EL-DWG-0058 | EL | A4 | LV DISTRIBUTION PANEL DRAWING FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-07-25 |  |  |  | 17811-57A
59 | BU-20-VD-303-EL-DWG-0059 | BU-20-VD-303-EL-DWG-0059 | EL | A4 | LV DISTRIBUTION PANEL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-25 |  |  |  | 17811-57B
60 | BU-20-VD-303-DC-INX-0061 | BU-20-VD-303-DC-INX-0061 | ME/QC | A4 | FINAL DATA BOOK INDEX FOR RECIPROCATING COMPRESSOR &NITROGEN GAS BOOSTER | 1 | 1 | 2021-07-30 |  |  |  | 17811-19
61 | BU-20-VD-303-DC-VDR-0062 | BU-20-VD-303-DC-VDR-0062 | ME/QC | A4 | FINAL DATA BOOK FOR RECIPROCATING COMPRESSOR &NITROGEN GAS BOOSTER | 1 | 1 | 2021-06-25 |  |  |  | 17811-70
62 | BU-20-VD-303-PR-LST-0063 | BU-20-VD-303-PR-LST-0063 | PR | A3 | TIE IN POINT LIST | 1 | 2 | 2021-07-02 |  |  |  | 17811-75
63 | BU-20-VD-303-PR-LST-0064 | BU-20-VD-303-PR-LST-0064 | PR | A3 | PIPING VALVE LIST | 1 | 2 | 2021-07-02 |  |  |  | 17811-76
64 | BU-20-VD-303-PR-LST-0065 | BU-20-VD-303-PR-LST-0065 | PR | A4 | PIPING LINE LIST | 1 | 2 | 2021-06-26 |  |  |  | 17811-77
65 | BU-20-VD-303-PR-DWG-0066 | BU-20-VD-303-PR-DWG-0066 | PR | A4 | P&ID FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 1 | 2021-06-26 |  |  |  | 17811-03B
66 | BU-20-VD-303-PR-LST-0067 | BU-20-VD-303-PR-LST-0067 | PR | A4 | UTILITY CONSUMPTION LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-25 |  |  |  | 17811-09B
67 | BU-20-VD-303-IN-DSH-0068 | BU-20-VD-303-IN-DSH-0068 | IN | A4 | CALCULATION & DATA SHEET OF SAFETY VALVE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-16 |  |  |  | 17811-52B
68 | BU-20-VD-303-ME-CAL-0069 | BU-20-VD-303-ME-CAL-0069 | ME | A4 | AFTER COOLER MECHANICAL STRENGHT CALCULATION FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-30 |  |  |  | 17811-24B
69 | BU-20-VD-303-ME-DSH-0070 | BU-20-VD-303-ME-DSH-0070 | ME | A4 | AFTER COOLER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-16 |  |  |  | 17811-11H
70 | BU-20-VD-303-ME-DWG-0071 | BU-20-VD-303-ME-DWG-0071 | ME | A4 | AFTER COOLER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-30 |  |  |  | 17811-23B
71 | BU-20-VD-303-ME-DSH-0072 | BU-20-VD-303-ME-DSH-0072 | ME | A4 | MAIN OIL PUMP MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-23 |  |  |  | 17811-11K
72 | BU-20-VD-303-ME-DSH-0073 | BU-20-VD-303-ME-DSH-0073 | ME | A4 | LUBE OIL SYSTEM FILTER MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-23 |  |  |  | 17811-11L
73 | BU-20-VD-303-EL-DWG-0074 | BU-20-VD-303-EL-DWG-0074 | EL | A4 | LUBE OIL SYSTEM HEATER DATA SHEET AND DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-23 |  |  |  | 17811-11J
74 | BU-20-VD-303-ME-DSH-0075 | BU-20-VD-303-ME-DSH-0075 | ME | A4 | MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 1 | 2021-08-09 |  |  |  | 17811-11G
75 | BU-20-VD-303-ME-DWG-0076 | BU-20-VD-303-ME-DWG-0076 | ME | A4 | GENERAL ARRANGEMENT DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 1 | 2021-06-25 |  |  |  | 17811-04B
76 | BU-20-VD-303-ME-DWG-0077 | BU-20-VD-303-ME-DWG-0077 | ME | A4 | RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-10-17 |  |  |  | 17811-59B
77 | BU-20-VD-303-ME-CAL-0078 | BU-20-VD-303-ME-CAL-0078 | ME | A4 | PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-30 |  |  |  | 17811-24D
78 | BU-20-VD-303-ME-DWG-0079 | BU-20-VD-303-ME-DWG-0079 | ME | A4 | PULSATION DAMPER DETAIL DRAWING FOR NITROGEN GAS BOOSTER | 1 | 2 | 2021-08-30 |  |  |  | 17811-23C
79 | BU-20-VD-303-ME-DWG-0080 | BU-20-VD-303-ME-DWG-0080 | ME | A4 | PULSATION DAMPER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-30 |  |  |  | 17811-23D
80 | BU-20-VD-303-PI-DWG-0081 | BU-20-VD-303-PI-DWG-0081 | PI | A4 | 3D MODEL FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 1 | 2021-06-25 |  |  |  | 17811-71B
81 | BU-20-VD-303-ME-DSH-0082 | BU-20-VD-303-ME-DSH-0082 | ME | A4 | DATA SHEET & DRAWINGS FOR STRAINERS FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-06-25 |  |  |  | 17811-44B
82 | BU-20-VD-303-IN-INX-0083 | BU-20-VD-303-IN-INX-0083 | IN | A4 | INSTRUMENT INDEX FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-06-25 |  |  |  | 17811-72B
83 | BU-20-VD-303-IN-LST-0084 | BU-20-VD-303-IN-LST-0084 | IN | A4 | I/O LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-09 |  |  |  | 17811-06B
84 | BU-20-VD-303-IN-DIG-0085 | BU-20-VD-303-IN-DIG-0085 | IN | A4 | LOGIC DIAGRAMS-PROGRAM OF UCP - COMPRESSOR SHUTDOWN LOGIC DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-06-18 |  |  |  | 17811-32B
85 | BU-20-VD-303-IN-DIG-0086 | BU-20-VD-303-IN-DIG-0086 | IN | A4 | LOOP DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-08-16 |  |  |  | 17811-30B
86 | BU-20-VD-303-IN-LST-0087 | BU-20-VD-303-IN-LST-0087 | IN | A4 | TRIP & ALARM SETPOINT LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-30 |  |  |  | 17811-36B
87 | BU-20-VD-303-IN-LST-0088 | BU-20-VD-303-IN-LST-0088 | IN | A4 | INSTRUMENT CABLE LIST & SHEDULE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-30 |  |  |  | 17811-53B
88 | BU-20-VD-303-IN-DWG-0089 | BU-20-VD-303-IN-DWG-0089 | IN | A3 | UCP/LCP/JB GENERAL ARRANGEMENT DRAWING & TERMINAL DETAILS FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-02 |  |  |  | 17811-07B
89 | BU-20-VD-303-IN-DSH-0090 | BU-20-VD-303-IN-DSH-0090 | IN | A3 | INSTRUMENT DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-02 |  |  |  | 17811-12B
90 | BU-20-VD-303-IN-DSH-0091 | BU-20-VD-303-IN-DSH-0091 | IN | A4 | CALCULATION & DATA SHEET OF CONTROL VALVES / ON-OFF VALVES FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-09-17 |  |  |  | 17811-45B
91 | BU-20-VD-303-PR-LST-0092 | BU-20-VD-303-PR-LST-0092 | PR | A4 | CAUSE & EFFECT CHART LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-09-18 |  |  |  | 17811-27B
92 | BU-20-VD-303-IN-DIG-0093 | BU-20-VD-303-IN-DIG-0093 | EL/IN | A4 | UCP/LCP/JB WIRING DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-30 |  |  |  | 17811-05B
93 | BU-20-VD-303-IN-DIG-0094 | BU-20-VD-303-IN-DIG-0094 | IN | A4 | ARCHITECTURE DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-30 |  |  |  | 17811-46B
94 | BU-20-VD-303-PR-DPH-0095 | BU-20-VD-303-PR-DPH-0095 | IN/PR | A4 | CONTROL PHILOSOPHY FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-09-25 |  |  |  | 17811-21B
95 | BU-20-VD-303-EL-LST-0096 | BU-20-VD-303-EL-LST-0096 | EL | A3 | ELECTRICAL LOAD LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-26 |  |  |  | 17811-65B
96 | BU-20-VD-303-EL-DIG-0097 | BU-20-VD-303-EL-DIG-0097 | EL | A3 | SINGLE LINE DIAGRAM FOR POWER DISTRIBUTION PANEL FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-06-25 |  |  |  | 17811-49B
97 | BU-20-VD-303-EL-LST-0098 | BU-20-VD-303-EL-LST-0098 | EL | A4 | POWER CABLE SCHEDULE & LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-28 |  |  |  | 17811-50B
98 | BU-20-VD-303-EL-DSH-0099 | BU-20-VD-303-EL-DSH-0099 | EL | A4 | COMPRESSOR MOTOR DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 1 | AFTER FAT |  |  |  | 17811-10B
99 | BU-20-VD-303-EL-PUC-0100 | BU-20-VD-303-EL-PUC-0100 | EL | A4 | COMPRESSOR MOTOR CURVE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-01 |  |  |  | 17811-54B
100 | BU-20-VD-303-EL-DWG-0101 | BU-20-VD-303-EL-DWG-0101 | EL | A4 | COMPRESSOR MOTOR OUTLINE DRAWING & TERMINAL BOX WIRING DIAGRAM FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-01 |  |  |  | 17811-39B
101 | BU-20-VD-303-IN-LST-0102 | BU-20-VD-303-IN-LST-0102 | IN | A4 | MODBUS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR | 1 | 2 | 2021-07-01 |  |  |  | 17811-56B
Document Class: 1: For approval 2: For review 3: For information
MC Client Class: 1: Client approval is necessary 2: Contractor approval is necessary * Category Type is the main workflow criteria and Approval for client and MC.