## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 23/Feb/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: P&ID FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00100 | Doc. No.: BU-20-VD-303-PR-DWG-0013
|  | Transmittal Date: 23/Feb/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Suction/Discharge pressure and temperature and design condition of each stage must be reported separately. |  |  | noted and updated
2 | OP and DP shall be rechecked and revised. |  |  | noted and updated
3 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated
4 | All PSVs inlet/outlet size rating and orifice designation as per API letter shall be specified. |  |  | Noted and updated, however calculation is awaited
5 | To be deleted |  |  | noted and updated
6 | Valve type schematic shall be modified (globe) |  |  | noted and updated
7 | Please specify process connection size |  |  | noted and updated
8 | Since compressor discharge pressure is 23.5, The set points shall be checked again. |  |  | noted and updated
9 | BU-20-D-100-PR-PID-101 11/2"-NM-1021-539D(H) |  |  | noted and updated
10 | BU-20-D-100-PR-PID-101 2"-CWS-1013-500C(N) |  |  | noted and updated
11 | PG-10161 |  |  | noted and updated
12 | Please be advised that as per above picture cooling water line 2" can be prepared by client in vendor battery limit .AIRPACK is expected to check the cooling water line again and select suitable line size. |  |  | we have checked the calculation and we have updated it to 2" to be on the safe side
13 | BU-20-D-100-PR-PID-101 2"-NL-1002-511C(N) |  |  | noted and updated
14 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated
15 | XCS-108 |  |  | noted and updated
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
2