## Table 1
1 | 0 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | TR0002 | RT0001
| 1 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | TR0007 | RT0003-10
| 2 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | TR0021 | RT0012
| 3 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | TR0035 | RT0039
| 4 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | TR0050
2 | 0 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0001 | RT0001
| 1 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0003 | RT0004
| 2 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0013 | RT0007
| 3 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0017 | RT0015
| 4 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0030
| 5 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0036 | RT0032
| 6 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0046 | RT0043
| 7 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | TR0058
3 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | TR0013 | RT0009
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | TR0028 | RT0027
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | TR0042 | RT0036
| 3 | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | TR0049 | RT0046
| 4 | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | TR0062 | RT0049
4 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001 / 8005 | TR0023 | RT0016
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001 / 8005 | TR0040 | RT0027
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001 / 8005 | TR0042 | RT0036
| 3 | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001 / 8005 | TR0055 | RT0046
| 4 | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001 / 8005 | TR0062 | RT0050
5 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | TR0023 | RT0016
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | TR0040 | RT0027
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | TR0042 | RT0036
| 3 | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | TR0055 | RT0047
| 4 | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | TR0062 | RT0050
6 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | TR0013 | RT0009
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | TR0029 | RT0030
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | TR0043 | RT0036
| 3 | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | TR0049 | RT0046
| 4 | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | TR0062 | RT0050
7 | 0 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | TR0010 | RT0006
| 1 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | TR0018 | RT0015
| 2 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | TR0039 | RT0029
| 3 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | TR0045 | RT0042
| 4 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | TR0056 | RT0049
8 | 0 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0006 | RT0002
| 1 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0020 | RT0011
| 2 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0024 | RT0016
| 3 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0033 | RT0022
| 4 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0047
| 5 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | TR0057 | RT0051
9 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | TR0012 | RT0006
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | TR0018 | RT0015
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | TR0039 | RT0029
| 3 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | TR0045 | RT0042
| 4 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | TR0056 | RT0049
10 | 0 | 3944-VD-0171-DYP-RE-400-ITP-0120 | Inspection & Test Plan | TR0001 | RT0001
| 1 | 3944-VD-0171-DYP-RE-400-ITP-0120 | Inspection & Test Plan | TR0003 | RT0010
| 2 | 3944-VD-0171-DYP-RE-400-ITP-0120 | Inspection & Test Plan | TR0024 | RT0031
11 | 0 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | TR0009 | RT0005
| 1 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | TR0033
| 2 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | TR0042 | RT0030
| 3 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | TR0047 | RT0038
| 4 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | TR0054 | RT0048
12 | 0 | 3944-VD-0171-DYP-RE-400-DSH-0096 | Main Motor Data Sheets | TR0021 | RT0012
| 1 | 3944-VD-0171-DYP-RE-400-DSH-0096 | Main Motor Data Sheets
13 | 0 | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | TR0038 | RT0024
| 1 | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | TR0042 | RT0030
| 2 | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | TR0047 | RT0038
| 3 | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | TR0053 | RT0048
14 | 0 | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor data sheet | TR0011 | RT0009
| 1 | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor data sheet | TR0022 | RT0015-18
| 2 | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor data sheet | TR0037 | RT0027
| 3 | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor data sheet | TR0042 | RT0036
15 | 0 | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | TR0016 | RT0013
| 1 | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | TR0031 | RT0026
| 2 | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | TR0052
| 3 | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | TR0064
16 | 0 | 3944-VD-0171-DYP-RE-400-DSH-0006 | PSV Data Sheets
17 | 0 | 3944-VD-0171-DYP-RE-400-CAL-0007 | PSV sizing calculations | TR0066 | RT0052
18 | 0 | 3944-VD-0171-DYP-RE-400-CAL-0008 | Thermowell wake frequency calculations
19 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0009 | FAT Procedure | TR0005 | RT0023
| 1 | 3944-VD-0171-DYP-RE-400-PRC-0009 | FAT Procedure | TR0042
| 2 | 3944-VD-0171-DYP-RE-400-PRC-0009 | FAT Procedure | TR0057
20 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0012 | NDE Procedure | TR0004 | RT0028
| 1 | 3944-VD-0171-DYP-RE-400-PRC-0012 | NDE Procedure | TR0057
21 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0013 | Package Nameplate Drawing | TR0044 | RT0048
22 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0128 | Painting Procedure | TR0004 | RT0012
23 | 0 | 3944-VD-0171-DYP-RE-400-LST-0014 | Index of Data Book | TR0061
24 | 0 | 3944-VD-0171-DYP-RE-400-LST-0015 | Index of Instruction and Operating Manual | TR0034 | RT0022
| 1 | 3944-VD-0171-DYP-RE-400-LST-0015 | Index of Instruction and Operating Manual | TR0043 | RT0048
25 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | TR0015 | RT0008
| 1 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy
| 2 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | TR0042 | RT0035
| 3 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | TR0052
| 4 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | TR0063
26 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Narrative | TR0026
| 1 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Narrative | TR0063
| 2 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Narrative
27 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0134 | Preservation, Packing & Shipping Procedure | TR0027 | RT0031
| 1 | 3944-VD-0171-DYP-RE-400-PRC-0134 | Preservation, Packing & Shipping Procedure | TR0047 | RT0048
28 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0017 | PQR / WPS for Skid | TR0014 | RT0024
29 | 0 | 3944-VD-0171-DYP-RE-400-PRC-0018 | WPQ for Skid | TR0014 | RT0025
30 | 0 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | TR0021 | RT0014
| 1 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | TR0032 | RT0029
| 2 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | TR0051
| 3 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | TR0059 | RT0051
31 | 0 | 3944-VD-0171-DYP-RE-400-DIA-0083 | Logic Diagrams | TR0048
| 1 | 3944-VD-0171-DYP-RE-400-DIA-0083 | Logic Diagrams | TR0065
32 | 0 | 3944-VD-0171-DYP-RE--400-CER-0088 | Instrument calibration certificates
33 | 0 | 3944-VD-0171-DYP-RE--400-CER-0089 | ATEX certificates
34 | 0 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | TR0025 | RT0017
| 1 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | TR0043 | RT0034
| 2 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | TR0052
| 3 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | TR0063
35 | 0 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | TR0019
| 1 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | TR0038 | RT0029
| 2 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | TR0052
| 3 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | TR0060 | RT0051
36 | 0 | 3944-VD-0171-DYP-RE-400-DWG-0079 | Instrument hook-up drawing | TR0024 | RT0016
| 1 | 3944-VD-0171-DYP-RE-400-DWG-0079 | Instrument hook-up drawing | TR0042 | RT0037
| 2 | 3944-VD-0171-DYP-RE-400-DWG-0079 | Instrument hook-up drawing | TR0063
37 | 0 | 3944-VD-0171-DYP-RE-400-LST-0005 | Sub vendor list | TR0008 | RT009-10
| 1 | 3944-VD-0171-DYP-RE-400-LST-0005 | Sub vendor list | TR0021
| 2 | 3944-VD-0171-DYP-RE-400-LST-0005 | Sub vendor list | TR0034
38 | 0 | 3944-VD-0171-DYP-RE-400-LST-0146 | Lubricant list | TR0041 | RT0033
| 1 | 3944-VD-0171-DYP-RE-400-LST-0146 | Lubricant list | TR0047 | RT0050
39 |  | 3944-VD-0171-DYP-RE-400-LST-0093 | Instrument UPS/Non UPS power consumption list | TR0042