## VPIS
Item. | Doc. Number | Airpack Doc. No. | Doc. Title | Class | Document Type | PO. Number | PO. Title | Scheduled Issue Date | First Issue Delay | Conditional Logic | Rev. | Doc. Status | Transmittal Number | Transmittal Date | DYPNF Reply Transmittal Number | DYPNF Reply Date | Status Code | DYPNF Reply Due Date | DYPNF Delay Duration | Resubmission Due Date | Resubmission Delay | Remark
1 | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | Vendor Document Schedule | A | INX | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 |  | 3944-VD-0171-DYP-RE-400-INX-0001Y | 04 | IFA | AIR-TR0050 | 2025-10-03 | DY-AIR-RT0058 | 2026-02-13 | RJ | 2025-10-13 | 123 | 0
2 | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | Piping & Instrument Diagram (incl. legend) | A | PID | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-PID-0016Y | 08 | IFA | AIR-TR0072 | 2026-02-04 | 0 | 0 | 0 | 2026-02-14 | No Delay | 0
3 | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | General Arrangement Drawing (incl foundation load details) 40001 | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-DWG-0020Y | 05 | IFA | AIR-TR0070 | 2026-01-30 | 0 | 0 | 0 | 2026-02-09 | No Delay | 0
4 | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | General Arrangement Drawing (incl foundation load details) 80001/8005 | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-DWG-0021Y | 05 | IFA | AIR-TR0080 | 2026-03-27 | 0 | 0 | 0 | 2026-04-15 | No Delay | 0
5 | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | General Arrangement Drawing (incl foundation load details) 80002 | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 |  | 3944-VD-0171-DYP-RE-400-DWG-0022Y | 04 | IFA | AIR-TR0062 | 2025-12-02 | DY-AIR-RT0050 | 2025-12-24 | AN | 2025-12-12 | 12 | 0
6 | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | General Arrangement Drawing (incl foundation load details) 80004 | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 |  | 3944-VD-0171-DYP-RE-400-DWG-0023Y | 04 | IFA | AIR-TR0062 | 2025-12-02 | DY-AIR-RT0050 | 2025-12-24 | AN | 2025-12-12 | 12 | 0
7 | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | Wiring Diagram (including Terminal Diagram) | A | DIA | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 |  | 3944-VD-0171-DYP-RE-400-DIA-0002Y | 05 | IFA | AIR-TR0069 | 2026-01-23 | DY-AIR-RT0056 | 2026-01-28 | AP | 2026-02-03 | No Delay | 0
8 | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | I/O List | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 |  | 3944-VD-0171-DYP-RE-400-LST-0080Y | 07 | IFA | AIR-TR0072 | 2026-02-04 | DY-AIR-RT0057 | 2026-02-06 | AN | 2026-02-14 | No Delay | 0
9 | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | Panel Layout Drawing | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 |  | 3944-VD-0171-DYP-RE-400-DWG-0003Y | 06 | IFA | AIR-TR0087 | 2026-04-30 | 0 | 0 | 0 | 2026-05-10 | No Delay | 0
10 | 3944-VD-0171-DYP-RE-400-ITP-0120 | 23383-08 | Inspection & Test Plan | A | ITP | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-ITP-0120Y | 02 | IFA | AIR-TR0024 | 2025-05-27 | Not Exist | 2025-08-12 | AP | 2025-04-06 | 128 | 0
11 | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | Utility Consumption | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-LST-0011Y | 04 | IFA | AIR-TR0054 | 2025-10-07 | DY-AIR-RT0048 | 2025-12-15 | AP | 2025-10-17 | 59 | 0
12 | 3944-VD-0171-DYP-RE-400-DSH-0096 | 23383-10 | Main Motor Data Sheets | A | DSH | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 |  | 3944-VD-0171-DYP-RE-400-DSH-0096Y | 02 | IFA | AIR-TR0081 | 2026-04-09 | 0 | 0 | 0 | 2026-04-20 | No Delay | 0
13 | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | Equipment List | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 |  | 3944-VD-0171-DYP-RE-400-LST-0010Y | 04 | IFA | AIR-TR0071 | 2026-02-03 | 0 | 0 | 0 | 2026-02-13 | No Delay | 0
14 | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | Compressor Data Sheet | A | DSH | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 |  | 3944-VD-0171-DYP-RE-400-DSH-0019Y | 05 | IFA | AIR-TR0086 | 2026-04-29 | 0 | 0 | 0 | 2026-05-10 | No Delay | 0
15 | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | Instrument Data Sheets | A | DSH | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 |  | 3944-VD-0171-DYP-RE-400-DSH-0077Y | 04 | IFA | AIR-TR0083 | 2026-04-13 | 0 | 0 | 0 | 2026-04-23 | No Delay | 0
16 | 3944-VD-0171-DYP-RE-400-DSH-0006 | 23383-12B | PSV Data Sheets | A | DSH | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 |  | 3944-VD-0171-DYP-RE-400-DSH-0006Y | 01 | IFA | AIR-TR0084 | 2026-04-23 | 0 | 0 | 0 | 2026-05-05 | No Delay | 0
17 | 3944-VD-0171-DYP-RE-400-CAL-0007 | 23383-12D | PSV sizing calculations | I | CAL | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 |  | 3944-VD-0171-DYP-RE-400-CAL-0007Y | 01 | IFI | AIR-TR0085 | 2026-04-24 | 0 | 0 | 0 | 2026-05-05 | No Delay | 0
18 | 3944-VD-0171-DYP-RE-400-CAL-0008 |  | Thermowell wake frequency calculations | I | CAL | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | 227 | 3944-VD-0171-DYP-RE-400-CAL-0008Y | Not Issued | Not Issued | Not Issued | Not Issued | Not Replied | Not Replied | Not Issued | Not Issued
19 | 3944-VD-0171-DYP-RE-400-PRC-0009 | 23383-14 | FAT Procedure | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 |  | 3944-VD-0171-DYP-RE-400-PRC-0009Y | 02 | IFA | AIR-TR0057 | 2025-11-21 | 0 | 0 | 0 | 2025-11-30 | No Delay | 0
20 | 3944-VD-0171-DYP-RE-400-PRC-0012 | 23383-15 | NDE Procedure | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 |  | 3944-VD-0171-DYP-RE-400-PRC-0012Y | 01 | IFA | AIR-TR0057 | 2025-11-21 | 0 | 0 | 0 | 2025-11-30 | No Delay | 0
21 | 3944-VD-0171-DYP-RE-400-DWG-0013 | 23383-16 | Package Nameplate Drawing | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 |  | 3944-VD-0171-DYP-RE-400-DWG-0013Y | 03 | IFA | AIR-TR0086 | 2026-04-29 | 0 | 0 | 0 | 2026-05-10 | No Delay | 0
22 | 3944-VD-0171-DYP-RE-400-PRC-0128 | 23383-18 | Painting Procedure | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 |  | 3944-VD-0171-DYP-RE-400-PRC-0128Y | 00 | IFA | AIR-TR0004 | 2025-03-07 | Not Exist | 2025-05-27 | AP | 2025-03-17 | 71 | 0
23 | 3944-VD-0171-DYP-RE-400-LST-0014 | 23383-19 | Index of Data Book | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 |  | 3944-VD-0171-DYP-RE-400-LST-0014Y | 00 | IFA | AIR-TR0061 | 2025-12-02 | 0 | 0 | 0 | 2025-12-12 | No Delay | 0
24 | 3944-VD-0171-DYP-RE-400-LST-0015 | 23383-20 | Index of Instruction and Operating Manual | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-05 |  | 3944-VD-0171-DYP-RE-400-LST-0015Y | 01 | IFA | Not Exist | 2025-08-13 | DY-AIR-RT0048 | 2025-12-15 | AP | 2025-08-23 | 114 | 0
25 | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | Control Philosophy | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 |  | 3944-VD-0171-DYP-RE-400-PRC-0081Y | 04 | IFA | AIR-TR0063 | 2025-12-08 | 0 | 0 | 0 | 2025-12-18 | No Delay | 0
26 | 3944-VD-0171-DYP-RE-400-PRC-0081-1 | 23383-21 | Control Narrative | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 |  | 3944-VD-0171-DYP-RE-400-PRC-0081-1Y | 00 | IFA | AIR-TR0026 | 2025-06-13 | 0 | 0 | 0 | 2025-06-23 | No Delay | 0
27 | 3944-VD-0171-DYP-RE-400-PRC-0134 | 23383-22 | Preservation, Packing & Shipping Procedure | A | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 |  | 3944-VD-0171-DYP-RE-400-PRC-0134Y | 02 | IFA | AIR-TR0069 | 2026-01-23 | DY-AIR-RT0056 | 2026-01-28 | AP | 2026-02-03 | No Delay | 0
28 | 3944-VD-0171-DYP-RE-400-PRC-0017 | 23383-25 | PQR / WPS for Skid | I | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 |  | 3944-VD-0171-DYP-RE-400-PRC-0017Y | 01 | IFI | Not Exist | Not Exist | Not Exist | 2025-07-23 | AN | Not Exist |  | 0
29 | 3944-VD-0171-DYP-RE-400-PRC-0018 | 23383-26 | WPQ for Skid | I | PRC | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 |  | 3944-VD-0171-DYP-RE-400-PRC-0018Y | 00 | IFI | AIR-TR0014 | 2025-04-16 | DY-AIR-RT0025 | 2025-07-18 | AN | 2025-04-26 | 83 | 0
30 | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | Cause & Effect diagram | A | DIA | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 |  | 3944-VD-0171-DYP-RE-400-DIA-0082Y | 05 | IFA | AIR-TR0081 | 2026-04-09 | 0 | 0 | 0 | 2026-04-20 | No Delay | 0
31 | 3944-VD-0171-DYP-RE-400-DIA-0083 | 23383-32 | Logic Diagrams | A | DIA | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-28 |  | 3944-VD-0171-DYP-RE-400-DIA-0083Y | 01 | IFA | AIR-TR0065 | 2025-12-19 | 0 | 0 | 0 | 2025-12-29 | No Delay | 0
32 | 3944-VD-0171-DYP-RE-400-CER-0088 |  | Instrument calibration certificates | A | CER | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-20 | 163 | 3944-VD-0171-DYP-RE-400-CER-0088Y | Not Issued | Not Issued | Not Issued | Not Issued | Not Replied | Not Replied | Not Issued | Not Issued
33 | 3944-VD-0171-DYP-RE-400-CER-0089 |  | ATEX certificates | A | CER | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | 173 | 3944-VD-0171-DYP-RE-400-CER-0089Y | Not Issued | Not Issued | Not Issued | Not Issued | Not Replied | Not Replied | Not Issued | Not Issued
34 | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | Instrument Index | A | INX | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 |  | 3944-VD-0171-DYP-RE-400-INX-0076Y | 06 | IFA | AIR-TR0089 | 2026-04-30 | 0 | 0 | 0 | 2026-05-10 | No Delay | 0
35 | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | Alarm And Trip Set Point List | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 |  | 3944-VD-0171-DYP-RE-400-LST-0092Y | 06 | IFA | AIR-TR0088 | 2026-04-30 | 0 | 0 | 0 | 2026-05-10 | No Delay | 0
36 | 3944-VD-0171-DYP-RE-400-DWG-0079 | 23383-38 | Instrument hook-up drawing | A | DWG | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-15 |  | 3944-VD-0171-DYP-RE-400-DWG-0079Y | 02 | IFA | AIR-TR0063 | 2025-12-08 | 0 | 0 | 0 | 2025-12-18 | No Delay | 0
37 | 3944-VD-0171-DYP-RE-400-LST-0005 | 23383-43 | Sub vendor list | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 |  | 3944-VD-0171-DYP-RE-400-LST-0005Y | 02 | IFA | AIR-TR0034 | 2025-06-26 | DY-AIR-RT0021 | 2025-06-27 | AP | 2025-07-06 | No Delay | 0
38 | 3944-VD-0171-DYP-RE-400-LST-0146 | 23383-44 | Lubricant list | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 |  | 3944-VD-0171-DYP-RE-400-LST-0146Y | 01 | IFA | AIR-TR0047 | 2025-09-10 | DY-AIR-RT0050 | 2025-12-24 | AP | 2025-09-20 | 95 | 0
39 | 3944-VD-0171-DYP-RE-400-LST-0093 | 23383-45 | Instrument UPS/Non UPS power consumption list | A | LST | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 |  | 3944-VD-0171-DYP-RE-400-LST-0093Y | 00 | IFA | Not Exist | 2024-12-03 | 0 | 0 | 0 | 2024-12-13 | No Delay | 0
Formulas:
First Issue Delay = IF([Rev.]="Not Issued", IF(ISNUMBER([Scheduled Issue Date]), INT(TODAY()-[Scheduled Issue Date]), ""), "")
Transmittal Date = IFERROR(INDIRECT("DB!"&ADDRESS(MATCH([Conditional Logic],DB!H:H,0),15)),"Not Issued")
DYPNF Reply Date = IFERROR(INDIRECT("DB!"&ADDRESS(MATCH([Conditional Logic],DB!H:H,0),19)),"Not Replied")
DYPNF Reply Due Date = IFERROR(INDIRECT("DB!"&ADDRESS(MATCH([Conditional Logic],DB!H:H,0),16)),"Not Issued")
Resubmission Due Date = IFERROR(INDIRECT("DB!"&ADDRESS(MATCH([Conditional Logic],DB!H:H,0),22)),"")
Resubmission Delay = IF(AND(ISNUMBER([Resubmission Due Date]), [Resubmission Due Date]<>DATE(1900,1,0), TODAY()>[Resubmission Due Date]), INT(TODAY()-[Resubmission Due Date]), "")

## DB
Item. | Po. Number | PO. Title | Scheduled Issue Date | Document Type | Doc. Number | Airpack Doc. No. | With Y | Doc. Title | Rev. | Last Rev. | Class | Doc. Status | Transmittal Number | Transmittal Date | DYPNF Reply Due Date | DYPNF Reply Delay Duration | DYPNF Reply Transmittal No. | Reply Date | Reply Status Code | Next Status | Resubmission Due Date | Resubmission Delay | TCL No. | TCL Date | Replied TCL Date by Client | TCL Status | Remark
1 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 | INX | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | 00 |  | A | IFA | AIR-TR0002 | 2025-02-11 | 2025-02-21 | No Delay | DY-AIR-RT0001 | 2025-02-18 | RJ | IFA
2 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 | INX | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | 01 |  | A | IFA | AIR-TR0007 | 2025-03-11 | 2025-03-21 | No Delay | DY-AIR-RT0003 | 2005-03-17 | RJ | IFA
3 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 | INX | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | 02 |  | A | IFA | AIR-TR0021 | 2025-05-13 | 2025-05-23 | No Delay | DY-AIR-RT0010 | 2025-05-23 | RJ | IFA
4 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 | INX | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | 3944-VD-0171-DYP-RE-400-INX-0001 | Vendor Document Schedule | 03 |  | A | IFA | AIR-TR0035 | 2025-06-30 | 2025-07-09 | 76 | DY-AIR-RT0039 | 2025-09-23 | RJ | IFA
5 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-05-18 | INX | 3944-VD-0171-DYP-RE-400-INX-0001 | 23383-01 | 3944-VD-0171-DYP-RE-400-INX-0001Y | Vendor Document Schedule | 04 | Y | A | IFA | AIR-TR0050 | 2025-10-03 | 2025-10-13 | 123 | DY-AIR-RT0058 | 2026-02-13 | RJ | IFA
6 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 00 |  | A | IFA | AIR-TR0001 | 2025-02-06 | 2025-02-16 | 2 | DY-AIR-RT0001 | 2025-02-18 | RJ | IFA
7 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 01 |  | A | IFA | AIR-TR0003 | 2025-02-28 | 2025-03-08 | 11 | DY-AIR-RT0004 | 2025-03-19 | RJ | IFA
8 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 02 |  | A | IFA | AIR-TR0013 | 2025-04-08 | 2025-04-18 | No Delay | DY-AIR-RT0007 | 2025-04-14 | RJ | IFA
9 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 03 |  | A | IFA | Not Exist | Not Exist |  |  | Not Exist | 2025-06-09 | RJ | IFA
10 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 04 |  | A | IFA | AIR-TR0030 | 2025-06-20 | 2025-06-30 | No Delay | DY-AIR-RT0021 | 2025-06-27 | RJ | IFA
11 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 05 |  | A | IFA | AIR-TR0036 | 2025-07-02 | 2025-07-12 | 41 | DY-AIR-RT0032 | 2025-08-22 | RJ | IFA
12 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 06 |  | A | IFA | AIR-TR0046 | 2025-09-10 | 2025-09-20 | 37 | DY-AIR-RT0043 | 2025-10-27 | RJ | IFA
13 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016 | Piping & Instrument Diagram (incl. legend) | 07 |  | A | IFA | AIR-TR0058 | 2025-11-26 | 2025-12-06 | 53 | DY-AIR-RT0056 | 2026-01-28 | RJ | IFA
14 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | 00 |  | A | IFA | AIR-TR0013 | 2025-04-08 | 2025-04-18 | 10 | Not Exist | 2025-04-28 | RJ | IFA
15 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | 01 |  | A | IFA | AIR-TR0028 | 2025-06-17 | 2025-06-27 | 26 | DY-AIR-RT0027 | 2025-07-23 | RJ | IFA
16 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | 02 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 17 | DY-AIR-RT0046 | 2025-09-04 | RJ | IFA
17 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | 03 |  | A | IFA | Not Exist | 2025-10-02 | 2025-10-12 | 43 | Not Exist | 2025-11-24 | RJ | IFA
18 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020 | General Arrangement Drawing (incl foundation load details) 40001 | 04 |  | A | IFA | AIR-TR0062 | 2025-12-02 | 2025-12-12 | 4 | DY-AIR-RT0049 | 2025-12-16 | AN | IFA
19 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001/8005 | 00 |  | A | IFA | AIR-TR0023 | 2025-05-16 | 2025-05-26 | 16 | Not Exist | 2025-06-11 | RJ | IFA
20 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001/8005 | 01 |  | A | IFA | Not Exist | 2025-07-17 | 2025-07-27 | No Delay | DY-AIR-RT0027 | 2025-07-23 | RJ | IFA
21 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001/8005 | 02 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 17 | Not Exist | 2025-09-04 | RJ | IFA
22 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001/8005 | 03 |  | A | IFA | Not Exist | 2025-11-14 | 2025-11-24 | No Delay | DY-AIR-RT0046 | 2025-11-24 | RJ | IFA
23 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021 | General Arrangement Drawing (incl foundation load details) 80001/8005 | 04 |  | A | IFA | AIR-TR0062 | 2025-12-02 | 2025-12-12 | 12 | DY-AIR-RT0050 | 2025-12-24 | AN | IFA
24 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | 00 |  | A | IFA | AIR-TR0023 | 2025-05-16 | 2025-05-26 | 16 | Not Exist | 2025-06-11 | RJ | IFA
25 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | 01 |  | A | IFA | AIR-TR0040 | 2025-07-17 | 2025-07-27 | No Delay | DY-AIR-RT0027 | 2025-07-23 | RJ | IFA
26 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | 02 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 17 | Not Exist | 2025-09-04 | RJ | IFA
27 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | 3944-VD-0171-DYP-RE-400-DWG-0022 | General Arrangement Drawing (incl foundation load details) 80002 | 03 |  | A | IFA | AIR-TR0055 | 2025-10-14 | 2025-10-24 | 33 | DY-AIR-RT0047 | 2025-11-26 | RJ | IFA
28 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0022 | 23383-04C | 3944-VD-0171-DYP-RE-400-DWG-0022Y | General Arrangement Drawing (incl foundation load details) 80002 | 04 | Y | A | IFA | AIR-TR0062 | 2025-12-02 | 2025-12-12 | 12 | DY-AIR-RT0050 | 2025-12-24 | AN | IFA
29 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | 00 |  | A | IFA | AIR-TR0013 | 2025-04-08 | 2025-04-18 | 10 | Not Exist | 2025-04-28 | RJ | IFA
30 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | 01 |  | A | IFA | AIR-TR0029 | 2025-06-17 | 2025-06-27 | 26 | DY-AIR-RT0027 | 2025-07-23 | RJ | IFA
31 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | 02 |  | A | IFA | Not Exist | 2025-08-13 | 2025-08-23 | 12 | Not Exist | 2025-09-04 | RJ | IFA
32 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | 3944-VD-0171-DYP-RE-400-DWG-0023 | General Arrangement Drawing (incl foundation load details) 80004 | 03 |  | A | IFA | AIR-TR0049 | 2025-11-02 | 2025-11-12 | 12 | DY-AIR-RT0046 | 2025-11-24 | RJ | IFA
33 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0023 | 23383-04D | 3944-VD-0171-DYP-RE-400-DWG-0023Y | General Arrangement Drawing (incl foundation load details) 80004 | 04 | Y | A | IFA | AIR-TR0062 | 2025-12-02 | 2025-12-12 | 12 | DY-AIR-RT0050 | 2025-12-24 | AN | IFA
34 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | 00 |  | A | IFA | AIR-TR0010 | 2025-03-17 | 2025-03-27 | 14 | DY-AIR-RT0006 | 2025-04-10 | RJ | IFA
35 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | 01 |  | A | IFA | AIR-TR0018 | 2025-04-28 | 2025-05-08 | 32 | DY-AIR-RT0015 | 2025-06-09 | RJ | IFA
36 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | 02 |  | A | IFA | AIR-TR0039 | 2025-07-16 | 2025-07-26 | 11 | Not Exist | 2025-08-06 | AN | IFA
37 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | 03 |  | A | IFA | Not Exist | 2025-09-03 | 2025-09-13 | 33 | Not Exist | 2025-10-16 | AN | IFA
38 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002 | Wiring Diagram (including Terminal Diagram) | 04 |  | A | IFA | Not Exist | 2025-11-20 | 2025-11-30 | 16 | DY-AIR-RT0049 | 2025-12-16 | AN | IFA
39 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 00 |  | A | IFA | AIR-TR0006 | 2025-03-10 | 2025-03-20 | No Delay | DY-AIR-RT0002 | 2025-03-11 | RJ | IFA
40 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 01 |  | A | IFA | AIR-TR0020 | 2025-05-12 | 2025-05-22 | No Delay | DY-AIR-RT0011 | 2025-05-14 | RJ | IFA
41 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 02 |  | A | IFA | AIR-TR0024 | 2025-05-27 | 2025-06-07 | 4 | Not Exist | 2025-06-11 | RJ | IFA
42 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 03 |  | A | IFA | AIR-TR0033 | 2025-06-26 | 2025-07-06 | 31 | Not Exist | 2025-08-06 | RJ | IFA
43 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 04 |  | A | IFA | AIR-TR0047 | 2025-09-10 | 2025-09-20 | 12 | DY-AIR-RT0041 | 2025-10-02 | AN | IFA
44 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 05 |  | A | IFA | AIR-TR0057 | 2025-11-21 | 2025-11-30 | 36 | DY-AIR-RT0051 | 2026-01-05 | AN | IFA
45 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 00 |  | A | IFA | AIR-TR0012 | 2025-03-25 | 2025-04-05 | 5 | DY-AIR-RT0006 | 2025-04-10 | RJ | IFA
46 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 01 |  | A | IFA | AIR-TR0018 | 2025-04-28 | 2025-05-08 | 32 | DY-AIR-RT0015 | 2025-06-09 | RJ | IFA
47 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 02 |  | A | IFA | AIR-TR0039 | 2025-07-16 | 2025-07-26 | 11 | Not Exist | 2025-08-06 | AN | IFA
48 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 03 |  | A | IFA | AIR-TR0045 | 2025-09-03 | 2025-09-13 | 33 | Not Exist | 2025-10-16 | AN | IFA
49 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 04 |  | A | IFA | AIR-TR0056 | 2025-11-20 | 2025-11-30 | 16 | DY-AIR-RT0049 | 2025-12-16 | AN | IFA
50 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | ITP | 3944-VD-0171-DYP-RE-400-ITP-0120 | 23383-08 | 3944-VD-0171-DYP-RE-400-ITP-0120 | Inspection & Test Plan | 00 |  | A | IFA | AIR-TR0001 | 2025-02-06 | 2025-02-16 | 2 | DY-AIR-RT0001 | 2025-02-18 | RJ | IFA
51 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | ITP | 3944-VD-0171-DYP-RE-400-ITP-0120 | 23383-08 | 3944-VD-0171-DYP-RE-400-ITP-0120 | Inspection & Test Plan | 01 |  | A | IFA | AIR-TR0003 | 2025-02-28 | 2025-03-08 | 62 | DY-AIR-RT0010 | 2025-05-09 | RJ | IFA
52 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | ITP | 3944-VD-0171-DYP-RE-400-ITP-0120 | 23383-08 | 3944-VD-0171-DYP-RE-400-ITP-0120Y | Inspection & Test Plan | 02 | Y | A | IFA | AIR-TR0024 | 2025-05-27 | 2025-04-06 | 128 | Not Exist | 2025-08-12 | AP
53 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | LST | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | 00 |  | A | IFA | AIR-TR0009 | 2025-03-17 | 2025-03-27 | No Delay | DY-AIR-RT0005 | 2025-03-26 | RJ | IFA
54 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | LST | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | 01 |  | A | IFA | AIR-TR0033 | 2025-06-26 | 2025-07-05 | No Delay | DY-AIR-RT0021 | 2025-06-27 | AN | IFA
55 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | LST | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | 02 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | No Delay | Not Exist | 2025-08-11 | AN | IFA
56 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | LST | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | 3944-VD-0171-DYP-RE-400-LST-0011 | Utility Consumption | 03 |  | A | IFA | AIR-TR0047 | 2025-09-10 | 2025-09-20 | No Delay | Not Exist | 2025-09-11 | RJ | IFA
57 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | LST | 3944-VD-0171-DYP-RE-400-LST-0011 | 23383-09 | 3944-VD-0171-DYP-RE-400-LST-0011Y | Utility Consumption | 04 | Y | A | IFA | AIR-TR0054 | 2025-10-07 | 2025-10-17 | 59 | DY-AIR-RT0048 | 2025-12-15 | AP
58 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0096 | 23383-10 | 3944-VD-0171-DYP-RE-400-DSH-0096 | Main Motor Data Sheets | 00 |  | A | IFA | AIR-TR0021 | 2025-05-13 | 2025-05-23 | 4 | Not Exist | 2025-05-27 | RJ | IFA
59 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | LST | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | 00 |  | A | IFA | AIR-TR0038 | 2025-07-14 | 2025-07-24 | No Delay | DY-AIR-RT0024 | 2025-07-16 | AN | IFA
60 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | LST | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | 01 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | No Delay | Not Exist | 2025-08-11 | AN | IFA
61 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | LST | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | 02 |  | A | IFA | AIR-TR0047 | 2025-09-10 | 2025-09-20 | No Delay | Not Exist | 2025-09-11 | RJ | IFA
62 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | LST | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | 3944-VD-0171-DYP-RE-400-LST-0010 | Equipment List | 03 |  | A | IFA | AIR-TR0053 | 2025-10-07 | 2025-10-17 | 59 | DY-AIR-RT0048 | 2025-12-15 | RJ | IFA
63 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor Data Sheet | 00 |  | A | IFA | AIR-TR0011 | 2025-03-18 | 2025-03-28 | 31 | Not Exist | 2025-04-28 | RJ | IFA
64 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor Data Sheet | 01 |  | A | IFA | AIR-TR0022 | 2025-05-15 | 2025-05-25 | 22 | DY-AIR-RT0018 | 2025-06-16 | RJ | IFA
65 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor Data Sheet | 02 |  | A | IFA | AIR-TR0037 | 2025-07-04 | 2025-07-14 | 9 | DY-AIR-RT0027 | 2025-07-23 | AN | IFA
66 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor Data Sheet | 03 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 17 | Not Exist | 2025-09-04 | AN | IFA
67 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | 00 |  | A | IFA | AIR-TR0016 | 2025-04-23 | 2025-05-03 | 39 | Not Exist | 2025-06-11 | RJ | IFA
68 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | 01 |  | A | IFA | AIR-TR0031 | 2025-06-20 | 2025-06-30 | 21 | DY-AIR-RT0026 | 2025-07-21 | AN | IFA
69 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | 02 |  | A | IFA | AIR-TR0052 | 2025-10-06 | 2025-10-16 |  | Not Exist | Not Exist | Not Exist | IFA
70 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | 3944-VD-0171-DYP-RE-400-DSH-0077 | Instrument Data Sheets | 03 |  | A | IFA | AIR-TR0064 | 2025-12-11 | 2025-12-21
71 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | CAL | 3944-VD-0171-DYP-RE-400-CAL-0007 | 23383-12D | 3944-VD-0171-DYP-RE-400-CAL-0007 | PSV sizing calculations | 00 |  | I | IFI | AIR-TR0066 | 2025-12-24 | 2026-01-04 | 2 | DY-AIR-RT0052 | 2026-01-06 | RJ | IFI
72 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0009 | 23383-14 | 3944-VD-0171-DYP-RE-400-PRC-0009 | FAT Procedure | 00 |  | A | IFA | AIR-TR0005 | 2025-03-07 | 2025-03-17 | 115 | DY-AIR-RT0023 | 2025-07-10 | RJ | IFA
73 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0009 | 23383-14 | 3944-VD-0171-DYP-RE-400-PRC-0009 | FAT Procedure | 01 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 |  | Not Exist | Not Exist | Not Exist | IFA
74 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0009 | 23383-14 | 3944-VD-0171-DYP-RE-400-PRC-0009Y | FAT Procedure | 02 | Y | A | IFA | AIR-TR0057 | 2025-11-21 | 2025-11-30
75 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0012 | 23383-15 | 3944-VD-0171-DYP-RE-400-PRC-0012 | NDE Procedure | 00 |  | A | IFA | AIR-TR0004 | 2025-03-07 | 2025-03-17 | 136 | DY-AIR-RT0028 | 2025-07-31 | AN | IFA
76 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0012 | 23383-15 | 3944-VD-0171-DYP-RE-400-PRC-0012Y | NDE Procedure | 01 | Y | A | IFA | AIR-TR0057 | 2025-11-21 | 2025-11-30
77 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0013 | 23383-16 | 3944-VD-0171-DYP-RE-400-DWG-0013 | Package Nameplate Drawing | 00 |  | A | IFA | AIR-TR0044 | 2025-08-13 | 2025-08-23 | 114 | DY-AIR-RT0048 | 2025-12-15 | RJ | IFA
78 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0128 | 23383-18 | 3944-VD-0171-DYP-RE-400-PRC-0128Y | Painting Procedure | 00 | Y | A | IFA | AIR-TR0004 | 2025-03-07 | 2025-03-17 | 71 | Not Exist | 2025-05-27 | AP
79 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0014 | 23383-19 | 3944-VD-0171-DYP-RE-400-LST-0014Y | Index of Data Book | 00 | Y | A | IFA | AIR-TR0061 | 2025-12-02 | 2025-12-12
80 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-05 | LST | 3944-VD-0171-DYP-RE-400-LST-0015 | 23383-20 | 3944-VD-0171-DYP-RE-400-LST-0015 | Index of Instruction and Operating Manual | 00 |  | A | IFA | AIR-TR0034 | 2025-06-26 | 2025-07-06 | No Delay | DY-AIR-RT0022 | 2025-07-02 | RJ | IFA
81 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-05 | LST | 3944-VD-0171-DYP-RE-400-LST-0015 | 23383-20 | 3944-VD-0171-DYP-RE-400-LST-0015Y | Index of Instruction and Operating Manual | 01 | Y | A | IFA | Not Exist | 2025-08-13 | 2025-08-23 | 114 | DY-AIR-RT0048 | 2025-12-15 | AP
82 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | 00 |  | A | IFA | AIR-TR0015 | 2025-04-16 | 2025-04-26 | No Delay | DY-AIR-RT0008 | 2025-04-18 | RJ | IFA
83 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | 01 |  | A | IFA | Not Exist | Not Exist | Not Exist | Not Exist | Not Exist | Not Exist | Not Exist | IFA
84 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | 02 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 16 | DY-AIR-RT0035 | 2025-09-03 | RJ | IFA
85 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081 | Control Philosophy | 03 |  | A | IFA | AIR-TR0052 | 2025-10-06 | 2025-10-16 | Not Exist | Not Exist | Not Exist | Not Exist | IFA
86 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081Y | Control Philosophy | 04 | Y | A | IFA | AIR-TR0063 | 2025-12-08 | 2025-12-18
87 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0081-1 | 23383-21 | 3944-VD-0171-DYP-RE-400-PRC-0081-1Y | Control Narrative | 00 | Y | A | IFA | AIR-TR0026 | 2025-06-13 | 2025-06-23
88 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0134 | 23383-22 | 3944-VD-0171-DYP-RE-400-PRC-0134 | Preservation, Packing & Shipping Procedure | 00 |  | A | IFA | AIR-TR0027 | 2025-06-13 | 2025-06-23 | 50 | Not Exist | 2025-08-12 | AN | IFA
89 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0134 | 23383-22 | 3944-VD-0171-DYP-RE-400-PRC-0134 | Preservation, Packing & Shipping Procedure | 01 |  | A | IFA | AIR-TR0047 | 2025-09-10 | 2025-09-20 | 86 | DY-AIR-RT0048 | 2025-12-15 | AN | IFA
90 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0017 | 23383-25 | 3944-VD-0171-DYP-RE-400-PRC-0017 | PQR / WPS for Skid | 00 |  | I | IFI | AIR-TR0014 | 2025-04-16 | 2025-04-26 | 233 | AIR-TR0014 | 2025-12-15 | AN | IFI
91 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0017 | 23383-25 | 3944-VD-0171-DYP-RE-400-PRC-0017Y | PQR / WPS for Skid | 01 | Y | I | IFI | Not Exist | Not Exist | Not Exist |  | Not Exist | 2025-07-23 | AN | IFI
92 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0018 | 23383-26 | 3944-VD-0171-DYP-RE-400-PRC-0018Y | WPQ for Skid | 00 | Y | I | IFI | AIR-TR0014 | 2025-04-16 | 2025-04-26 | 83 | DY-AIR-RT0025 | 2025-07-18 | AN | IFI
93 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | 00 |  | A | IFA | AIR-TR0021 | 2025-05-13 | 2025-05-23 | 7 | DY-AIR-RT0014 | 2025-05-30 | RJ | IFA
94 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | 01 |  | A | IFA | AIR-TR0032 | 2025-06-25 | 2025-07-05 | 32 | Not Exist | 2025-08-06 | RJ | IFA
95 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | 02 |  | A | IFA | AIR-TR0051 | 2025-10-03 | 2025-10-13 |  | Not Exist | Not Exist | Not Exist | IFA
96 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | 3944-VD-0171-DYP-RE-400-DIA-0082 | Cause & Effect diagram | 03 |  | A | IFA | AIR-TR0059 | 2025-11-27 | 2025-12-07 | 29 | DY-AIR-RT0051 | 2026-01-05 | RJ | IFA
97 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-28 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0083 | 23383-32 | 3944-VD-0171-DYP-RE-400-DIA-0083 | Logic Diagrams | 00 |  | A | IFA | AIR-TR0048 | 2025-10-01 | 2025-10-11 |  | Not Exist | Not Exist | Not Exist | IFA
98 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-28 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0083 | 23383-32 | 3944-VD-0171-DYP-RE-400-DIA-0083Y | Logic Diagrams | 01 | Y | A | IFA | AIR-TR0065 | 2025-12-19 | 2025-12-29 |  |  |  |  | IFA
99 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | 00 |  | A | IFA | AIR-TR0025 | 2025-06-02 | 2025-06-12 | No Delay | DY-AIR-RT0017 | 2025-06-12 | RJ | IFA
100 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | 01 |  | A | IFA | Not Exist | 2025-08-13 | 2025-08-23 | 6 | DY-AIR-RT0034 | 2025-08-29 | RJ | IFA
101 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | 02 |  | A | IFA | AIR-TR0052 | 2025-10-06 | 2025-10-16 |  | Not Exist | Not Exist | Not Exist | IFA
102 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | 03 |  | A | IFA | AIR-TR0063 | 2025-12-08 | 2025-12-18 | 50 | DY-AIR-RT0057 | 2026-02-06 | AN | IFA
103 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | 00 |  | A | IFA | AIR-TR0019 | 2025-05-07 | 2025-05-17 | No Delay | DY-AIR-RT0010 | 2025-05-09 | RJ | IFA
104 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | 01 |  | A | IFA | AIR-TR0038 | 2025-07-14 | 2025-07-24 | 13 | Not Exist | 2025-08-06 | RJ | IFA
105 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | 02 |  | A | IFA | AIR-TR0052 | 2025-10-06 | 2025-10-16 |  | Not Exist | Not Exist | Not Exist | IFA
106 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | 03 |  | A | IFA | AIR-TR0060 | 2025-11-28 | 2025-12-08 | 28 | DY-AIR-RT0051 | 2026-01-05 | RJ | IFA
107 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-15 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0079 | 23383-38 | 3944-VD-0171-DYP-RE-400-DWG-0079 | Instrument hook-up drawing | 00 |  | A | IFA | AIR-TR0024 | 2025-05-27 | 2025-06-07 | 4 | Not Exist | 2025-06-11 | RJ | IFA
108 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-15 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0079 | 23383-38 | 3944-VD-0171-DYP-RE-400-DWG-0079 | Instrument hook-up drawing | 01 |  | A | IFA | Not Exist | 2025-08-08 | 2025-08-18 | 22 | DY-AIR-RT0037 | 2025-09-09 | RJ | IFA
109 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-15 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0079 | 23383-38 | 3944-VD-0171-DYP-RE-400-DWG-0079Y | Instrument hook-up drawing | 02 | Y | A | IFA | AIR-TR0063 | 2025-12-08 | 2025-12-18
110 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | LST | 3944-VD-0171-DYP-RE-400-LST-0005 | 23383-43 | 3944-VD-0171-DYP-RE-400-LST-0005 | Sub vendor list | 00 |  | A | IFA | AIR-TR0008 | 2025-03-11 | 2025-03-21 | 49 | DY-AIR-RT0010 | 2025-05-09 | RJ | IFA
111 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | LST | 3944-VD-0171-DYP-RE-400-LST-0005 | 23383-43 | 3944-VD-0171-DYP-RE-400-LST-0005 | Sub vendor list | 01 |  | A | IFA | AIR-TR0021 | 2025-05-13 | 2025-05-23 | 25 | DY-AIR-RT0019 | 2025-06-17 | RJ | IFA
112 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | LST | 3944-VD-0171-DYP-RE-400-LST-0005 | 23383-43 | 3944-VD-0171-DYP-RE-400-LST-0005Y | Sub vendor list | 02 | Y | A | IFA | AIR-TR0034 | 2025-06-26 | 2025-07-06 | No Delay | DY-AIR-RT0021 | 2025-06-27 | AP
113 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | LST | 3944-VD-0171-DYP-RE-400-LST-0146 | 23383-44 | 3944-VD-0171-DYP-RE-400-LST-0146 | Lubricant list | 00 |  | A | IFA | AIR-TR0041 | 2025-07-22 | 2025-08-02 | 25 | DY-AIR-RT0033 | 2025-08-27 | RJ | IFA
114 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-30 | LST | 3944-VD-0171-DYP-RE-400-LST-0146 | 23383-44 | 3944-VD-0171-DYP-RE-400-LST-0146Y | Lubricant list | 01 | Y | A | IFA | AIR-TR0047 | 2025-09-10 | 2025-09-20 | 95 | DY-AIR-RT0050 | 2025-12-24 | AP
115 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 | LST | 3944-VD-0171-DYP-RE-400-LST-0093 | 23383-45 | 3944-VD-0171-DYP-RE-400-LST-0093Y | Instrument UPS/Non UPS power consumption list | 00 | Y | A | IFA | Not Exist | 2024-12-03 | 2024-12-13
116 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-10 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0002 | 23383-05 | 3944-VD-0171-DYP-RE-400-DIA-0002Y | Wiring Diagram (including Terminal Diagram) | 05 | Y | A | IFA | AIR-TR0069 | 2026-01-23 | 2026-02-03 | No Delay | DY-AIR-RT0056 | 2026-01-28 | AP
117 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003 | Panel Layout Drawing | 05 |  | A | IFA | AIR-TR0069 | 2026-01-23 | 2026-02-03 | No Delay | DY-AIR-RT0056 | 2026-01-28 | AN | IFA
118 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-23 | PRC | 3944-VD-0171-DYP-RE-400-PRC-0134 | 23383-22 | 3944-VD-0171-DYP-RE-400-PRC-0134Y | Preservation, Packing & Shipping Procedure | 02 | Y | A | IFA | AIR-TR0069 | 2026-01-23 | 2026-02-03 | No Delay | DY-AIR-RT0056 | 2026-01-28 | AP
119 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0020 | 23383-04A | 3944-VD-0171-DYP-RE-400-DWG-0020Y | General Arrangement Drawing (incl foundation load details) 40001 | 05 | Y | A | IFA | AIR-TR0070 | 2026-01-30 | 2026-02-09
120 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080 | I/O List | 06 |  | A | IFA | Not Exist | Not Exist | Not Exist |  | Not Exist | Not Exist
121 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | LST | 3944-VD-0171-DYP-RE-400-LST-0080 | 23383-06 | 3944-VD-0171-DYP-RE-400-LST-0080Y | I/O List | 07 | Y | A | IFA | AIR-TR0072 | 2026-02-04 | 2026-02-14 | No Delay | DY-AIR-RT0057 | 2026-02-06 | AN | IFA
122 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | PID | 3944-VD-0171-DYP-RE-400-PID-0016 | 23383-03 | 3944-VD-0171-DYP-RE-400-PID-0016Y | Piping & Instrument Diagram (incl. legend) | 08 | Y | A | IFA | AIR-TR0072 | 2026-02-04 | 2026-02-14
123 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | LST | 3944-VD-0171-DYP-RE-400-LST-0010 | 23383-11A | 3944-VD-0171-DYP-RE-400-LST-0010Y | Equipment List | 04 | Y | A | IFA | AIR-TR0071 | 2026-02-03 | 2026-02-13
124 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0021 | 23383-04B | 3944-VD-0171-DYP-RE-400-DWG-0021Y | General Arrangement Drawing (incl foundation load details) 80001/8005 | 05 | Y | A | IFA | AIR-TR0080 | 2026-03-27 | 2026-04-15
125 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-28 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0096 | 23383-10 | 3944-VD-0171-DYP-RE-400-DSH-0096Y | Main Motor Data Sheets | 02 | Y | A | IFA | AIR-TR0081 | 2026-04-09 | 2026-04-20
126 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-15 | DIA | 3944-VD-0171-DYP-RE-400-DIA-0082 | 23383-27 | 3944-VD-0171-DYP-RE-400-DIA-0082Y | Cause & Effect diagram | 05 | Y | A | IFA | AIR-TR0081 | 2026-04-09 | 2026-04-20
127 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092 | Alarm And Trip Set Point List | 05 |  | A | IFA | AIR-TR0082 | 2026-04-10 | 2026-04-20
128 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076 | Instrument Index | 05 |  | A | IFA | AIR-TR0083 | 2026-04-13 | 2026-04-23
129 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019 | Compressor Data Sheet | 04 |  | A | IFA | AIR-TR0083 | 2026-04-13 | 2026-04-23
130 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0077 | 23383-12A | 3944-VD-0171-DYP-RE-400-DSH-0077Y | Instrument Data Sheets | 04 | Y | A | IFA | AIR-TR0083 | 2026-04-13 | 2026-04-23
131 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0006 | 23383-12B | 3944-VD-0171-DYP-RE-400-DSH-0006 | PSV Data Sheets | 00 |  | A | IFA | AIR-TR0083 | 2026-04-13 | 2026-04-23
132 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | CAL | 3944-VD-0171-DYP-RE-400-CAL-0007 | 23383-12D | 3944-VD-0171-DYP-RE-400-CAL-0007Y | PSV sizing calculations | 01 | Y | I | IFI | AIR-TR0085 | 2026-04-24 | 2026-05-05
133 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0006 | 23383-12B | 3944-VD-0171-DYP-RE-400-DSH-0006Y | PSV Data Sheets | 01 | Y | A | IFA | AIR-TR0084 | 2026-04-23 | 2026-05-05
134 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-09-17 | DSH | 3944-VD-0171-DYP-RE-400-DSH-0019 | 23383-11B | 3944-VD-0171-DYP-RE-400-DSH-0019Y | Compressor Data Sheet | 05 | Y | A | IFA | AIR-TR0086 | 2026-04-29 | 2026-05-10
135 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-05 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0013 | 23383-16 | 3944-VD-0171-DYP-RE-400-DWG-0013Y | Package Nameplate Drawing | 03 | Y | A | IFA | AIR-TR0086 | 2026-04-29 | 2026-05-10
136 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-10-29 | DWG | 3944-VD-0171-DYP-RE-400-DWG-0003 | 23383-07 | 3944-VD-0171-DYP-RE-400-DWG-0003Y | Panel Layout Drawing | 06 | Y | A | IFA | AIR-TR0087 | 2026-04-30 | 2026-05-10
137 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | LST | 3944-VD-0171-DYP-RE-400-LST-0092 | 23383-36 | 3944-VD-0171-DYP-RE-400-LST-0092Y | Alarm And Trip Set Point List | 06 | Y | A | IFA | AIR-TR0088 | 2026-04-30 | 2026-05-10
138 | PO-PC2312-08 | Screw Compressor & Roots Blower Package | 2025-11-10 | INX | 3944-VD-0171-DYP-RE-400-INX-0076 | 23383-35 | 3944-VD-0171-DYP-RE-400-INX-0076Y | Instrument Index | 06 | Y | A | IFA | AIR-TR0089 | 2026-04-30 | 2026-05-10
139 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
140 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
141 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
142 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
143 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
144 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
145 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
146 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
147 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
148 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
149 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
150 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
151 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
152 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
153 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
154 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
155 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
156 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
157 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
158 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
159 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
160 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
161 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
162 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
163 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
164 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
165 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
166 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
167 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
168 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
169 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
170 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
171 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
172 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
173 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
174 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
175 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
176 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
177 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
178 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
179 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
180 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
181 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
182 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
183 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
184 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
185 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
186 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
187 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
188 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
189 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
190 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
191 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
192 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
193 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
194 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
195 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
196 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
197 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
198 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
199 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
200 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
201 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
202 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
203 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
204 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
205 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
206 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
207 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
208 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
209 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
210 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
211 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
212 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
213 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
214 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
215 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
216 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
217 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
218 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
219 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
220 | Not Exist | Not Exist | Not Exist | Not Exist |  | Not Exist |  | Not Exist |  |  | Not Exist
Formulas:
Scheduled Issue Date = IFERROR(VLOOKUP([Doc. Number],VPIS!B:R,8,0),"Not Exist")
Resubmission Delay = IF(AND([Last Rev.]="Y", ISNUMBER([Resubmission Due Date]), TODAY()>[Resubmission Due Date]), TEXT(TODAY()-[Resubmission Due Date],"0"), "")