## 44W-80008 PELLET
VENDOR PRINT INDEX AND SCHEDULE
P.O NO: | [5 empty] | PAGE |  | DATE OF APPROVAL | [29 empty] | FOR FINAL |  |  | AS BUILT | REMARK
SN | KEY VP | ITEM NO/ TAG NO | DOCUMENT NO. | DOCUMENT TITLE | PUR. |  |  | 1st Issue |  |  | 2nd Issue |  |  | 3rd Issue |  |  | 4th Issue |  |  | 5th Issue |  |  | 6th Issue |  |  | 7th Issue |  |  | 8th Issue |  |  | 9th Issue |  |  | 10th Issue
[8 empty] | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | ISSUE | RETURN | RST | IN
1 |  |  | 3944-VD-0180-DYP-RE-800-INX-0001 | VENDOR PRINT INDEX & SCHEDULE | IFCA |  | S | 00
A
2 |  |  | 3944-VD-0180-DYP-RE-800-SCH-0002 | TIME SCHEDULE | IFCA |  | S | 00
A
3 |  |  | 3944-VD-0180-DYP-RE-800-LST-0005 | SUB-VENDOR LIST | IFCA |  | S | 00
A
4 |  |  | 3944-VD-0180-DYP-RE-800-LST-0006 | SPARE PARTS LIST FOR ERECTION & COMMISSIONING | IFCA |  | S | 00
A
5 |  |  | 3944-VD-0180-DYP-RE-800-LST-0007 | SPARE PARTS LIST FOR TWO (2) YEARS OPERATION | IFCA |  | S | 00
A
6 |  |  | 3944-VD-0180-DYP-RE-800-LST-0008 | SPARE PARTS LIST FOR CAPITAL | IFCA |  | S | 00
A
7 |  |  | 3944-VD-0180-DYP-RE-800-LST-0009 | SPECIAL TOOLS LIST (IF APPLICABLE) | IFCA |  | S | 00
A
8 |  |  | 3944-VD-0180-DYP-RE-800-LST-0010 | EQUIPMENT LIST |  |  | S | 00
A
9 |  |  | 3944-VD-0180-DYP-RE-800-LST-0011 | UTILITY CONSUMPTION LIST | IFCA |  | S | 00
A
10 |  |  | 3944-VD-0180-DYP-RE-800-LST-0012 | LUBRICANT LIST | IFCA |  | S | 00
A
11 |  |  | 3944-VD-0180-DYP-RE-800-MNL-0013 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | IFCA |  | S | 00
A
12 |  |  | 3944-VD-0180-DYP-RE-800-PID-0016 | PID FOR PNEUMATIC CONVEYING SYSTEM | IFCA |  | S | 00
A
13 |  |  | 3944-VD-0180-DYP-RE-800-PFD-0017 | PFD FOR PNEUMATIC CONVEYING SYSTEM | IFCA |  | S | 00
A
14 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0019 | EQUIPMENT DATA SHEET OF CONVEYING AIR COMPRESSOR (44C-80001A/B) | IFCA |  | S | 00
A
15 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0020 | GA DRAWING FOR CONVEYING AIR COMPRESSOR WITH PART LIST (44C-80001A/B) |  |  | S | 00
A
16 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0021 | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIALS OF COMPRESSORS INCLUDE PART LISTS (44C-80001A/B) |  |  | S | 00
A
17 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0022 | CROSS SECTIONAL DRAWING OF COMPRESSORS WITH PART LISTS (44C-80001A/B) |  |  | S | 00
A
18 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0023 | EQUIPMENT DATA SHEET OF CONVEYING AIR BLOWER (44C-80002A/B) |  |  | S | 00
A
19 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0024 | GA DRAWING FOR CONVEYING AIR BLOWER WITH PART LIST (44C-80002A/B) |  |  | S | 00
A
20 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0025 | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIALS OF BLOWER INCLUDE PART LISTS (44C-80002A/B) |  |  | S | 00
A
21 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0026 | CROSS SECTIONAL DRAWING OF AIR BLOWER WITH PART LISTS (44C-80002A/B) |  |  | S | 00
A
22 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0027 | EQUIPMENT DATA SHEET OF CONVEYING AIR COMPRESSOR (44C-80003A/B) |  |  | S | 00
A
23 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0028 | GA DRAWING FOR CONVEYING AIR COMPRESSOR WITH PART LIST (44C-80004A/B) |  |  | S | 00
A
24 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0029 | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIALS OF COMPRESSORS INCLUDE PART LISTS (44C-80003A/B) |  |  | S | 00
A
25 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0030 | CROSS SECTIONAL DRAWING OF COMPRESSORS WITH PART LISTS (44C-80003A/B) |  |  | S | 00
A
26 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0031 | EQUIPMENT DATA SHEET OF CONVEYING AIR COMPRESSOR (44C-80004A~C) |  |  | S | 00
A
27 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0032 | GA DRAWING FOR CONVEYING AIR COMPRESSOR WITH PART LIST (44C-80005A~C) |  |  | S | 00
A
28 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0033 | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIALS OF COMPRESSORS INCLUDE PART LISTS (44C-80004A~C) |  |  | S | 00
A
29 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0034 | CROSS SECTIONAL DRAWING OF COMPRESSORS WITH PART LISTS (44C-80005A~C) |  |  | S | 00
A
30 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0035 | EQUIPMENT DATA SHEET OF CONVEYING AIR (44C-80006 A/B) WITH PERFORMANCE CURVE, INCLUDE ALL AUXILIARTIES (e.g SUCTION FILTER & OTHERS) DATA |  |  | S | 00
A
31 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0097 | FOUNDATION PLAN DRAWING AND LOADING DATA |  |  | S | 00
A
32 |  |  | 3944-VD-0180-DYP-RE-800-LST-0098 | ANCHOR BOLT AND SETTING BOLT LIST |  |  | S | 00
A
33 |  |  | 3944-VD-0180-DYP-RE-800-INX-0099 | INSTRUMENT INDEX |  |  | S | 00
A
34 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0100 | INSTRUMENT DATA SHEET(W/Catalog) |  |  | S | 00
A
35 |  |  | 3944-VD-0180-DYP-RE-800-DIA-0101 | E&I SYSTEM CONFIGURATION DIAGRAM |  |  | S | 00
A
36 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0102 | INSTRUMENT HOOK UP DRAWING |  |  | S | 00
A
37 |  |  | 3944-VD-0180-DYP-RE-800-LST-0103 | I/O LIST |  |  | S | 00
A
38 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0104 | CONTROL NARRATIVE |  |  | S | 00
A
39 |  |  | 3944-VD-0180-DYP-RE-800-DIA-0105 | CAUSE AND EFFECT DIAGRAM |  |  | S | 00
A
40 |  |  | 3944-VD-0180-DYP-RE-800-DIA-0106 | LOGIC DIAGRAM |  |  | S | 00
A
41 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0108 | INSTRUMENT LOCATION DRAWING (INSTRUMENT LOCATION LAYOUT) |  |  | S | 00
A
42 |  |  | 3944-VD-0180-DYP-RE-800-CER-0111 | INSTRUMENT CALIBRATION CERTIFICATE |  |  | S | 00
A
43 |  |  | 3944-VD-0180-DYP-RE-800-CER-0112 | INSTREMENT EXPLOSTION PROTECTION CERTIFICATE |  |  | S | 00
A
44 |  |  | 3944-VD-0180-DYP-RE-800-CER-0113 | INSTRUMENT SIL CERTIFICATE |  |  | S | 00
A
45 |  |  | 3944-VD-0180-DYP-RE-800-CSH-0114 | INSTRUMENT SIZING CALCULATION (INCLUDING PSV, PCV, RO, CONTROL VALVE,WAKE FREQUENCY ETC.) |  |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-CSH-0114 | INSTRUMENT SIZING CALCULATION (INCLUDING PSV, PCV, RO, CONTROL VALVE,WAKE FREQUENCY ETC.) |  |  | A
46 |  |  | 3944-VD-0180-DYP-RE-800-LST-0115 | ALARM AND TRIP SET POINT LIST |  |  | S | 00
A
47 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0118 | INSTRUMENT ARRANGMENT DRAWING OF COMPRESSOR |  |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-DWG-0118 | INSTRUMENT ARRANGMENT DRAWING OF COMPRESSOR |  |  | A
48 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0119 | MV MOTOR DATA SHEET AND PERFORMANCE CURVES |  |  | S | 00
A
49 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0120 | LV MOTOR DATA SHEET AND PERFORMANCE CURVES |  |  | S | 00
A
50 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0121 | MV MOTORS OUTLINE DRAWING WITH NAME PLATES |  |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-DWG-0122 | LV MOTORS OUTLINE DRAWING |  |  | A
51 |  |  | 3944-VD-0180-DYP-RE-800-DWG-0122 | LV MOTORS OUTLINE DRAWING WITH NAME PLATES |  |  | S | 00
A
52 |  |  | 3944-VD-0180-DYP-RE-800-LST-0123 | ELECTRICAL LOAD LIST |  |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-LST-0123 | ELECTRICAL LOAD LIST |  |  | A
53 |  |  | 3944-VD-0180-DYP-RE-800-ITP-0143 | INSPECTION & TEST PLAN | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-ITP-0143 | INSPECTION & TEST PLAN |  |  | A
54 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0144 | INSPECTION & TEST PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0145 | HYDROSTATIC AND LEAK TEST PROCEDURE |  |  | 22
55 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0150 | PICKLING AND PASSIVATION PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0151 | PAINTING PROCEDURE |  |  | A
56 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0151 | PAINTING PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0151 | PAINTING PROCEDURE |  |  | A
57 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0157 | PACKING, MARKING & SHIPPING PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0159 | PRE-COMMISSIONING, COMMISSIONING PROCEDURE |  |  | A
58 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0158 | RUST PRESERVATION PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0158 | RUST PRESERVATION PROCEDURE |  |  | A
59 |  |  | 3944-VD-0180-DYP-RE-800-PRC-0159 | PRE-COMMISSIONING, COMMISSIONING & START-UP PROCEDURE | IFCA |  | S | 00
|  |  | 3944-VD-0180-DYP-RE-800-PRC-0159 | PRE-COMMISSIONING, COMMISSIONING PROCEDURE |  |  | A
60 |  |  | 3944-VD-0180-DYP-RE-800-LST-0167 | PACKING LIST | IFCA |  | S | 00
A
61 |  |  | 3944-VD-0180-DYP-RE-800-DSH-0173 | NOISE DATA SHEET FOR COMPRESSOR/BLOWER/ROTARY VALVE/FAN | IFCA |  | S | 00
A
JOB NO. |  | PC2312 |  |  | DESCRIPTION |  |  |  | 44W-80008 PELLET | [10 empty] | ISSUED |  |  | 1 |  | 3
Ref No. |  |  |  |  | VENDOR | [14 empty] | 0 |  |  | 2 |  | 4
1. PURPOSE |  | AP: Approved AN: Approved as Noted CO: Commented (Fabricaiton shall not proceed) RE: Rejected
2. RESULT |  | ISSUE: ISSUED DATE TO DY, RETURN: RECEIVED DATE FROM DY, RST: RESULT OF V/P REVIEW, S: SCHEDULE, A: ACTUAL
3. OTHERS