## TCS (hidden)
Additional Outstanding
▶Project : Iran LNG - Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0003 | 26.Jan.2011
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Lurgi's Response
[5 empty] | TC-1 |  | Confirmation during meeting
Open | 1-1 | D-1101 | page.7 Comment for Calculation rev.1 | Bottom Skirt Length: 4800 -> 3458 | The skirt length in PV-elite shall include the basering thickness because of the distance from base elevation to bottom T.L. Therefore, we changed the bottom skirt length from 3458mm to 3500mm. |  | OK
Open | 1-2 | D-1101 | page.7 Comment for Calculation rev.1 | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 1-3 | D-1101 | Comment for General assembly rev.1 | To change of off-centered distance of nozzle: V(4") nozzle : C.L.+1200 P(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2")(C.L.+1100) and B(46") The Centerline Dist. is 375.36 while the sum of the ins. Radii is 559.60. - V(4")(C.L.+1200) and B(46") The Centerline Dist. is 411.43 while the sum of the ins. Radii is 580.25. To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V nozzle shall be over C.L.+2000. Please confirm whether the nozzle locations will be changed or keep the locations. |  | TO BE INFORMED
Open | 1-4 | D-1101 | Comment for Manhole detail rev.1 | To avoid any changes of cracking/shearing, weld overlay on face of the flange shall be done by providing an under cut in the flange thk. And thus increasing the flange overall thk. by approx.2mm. | We normally perform weld overlay on face of the flange with overlay thickness min.4.5mm and there is no change of cracking/shearking. The weld overlay detail shown on the revised drawing in rev.2 is enough to meet spec. requirement and avoid any change. Therefore, we will proceed the weld overlay of flange same as revised drawing in rev.2. |  | OK
Open | 1-5 | D-1101 | Comment for Manhole detail rev.1 | Please check the material "SA350-LF2 CL.1". If "class" is applicable in 'Div.2'. | According to Sec.VIII Div.2 2004 ED.+2006 ADD., the class of SA350-LF2 is not indicated and also in Sec.II Part.D table.2A. However, according to Sec.II Part.A SA350, SA350-LF2 is shall be indicate the class of material to purchase. SA350-LF2 class.1 and class.2 have same mechanical and chemical property and the impact test requirement is different. (Standard impact test temperature - Class.1: -46℃, Class.2 -18℃) Therefore, we will use class.1 of SA350-LF2 because MDMT is -30℃. |  | OK
Open | 1-6 | D-1101 | Comment for nozzle detail (2/3) rev.1 | Nozzle size 3" and below, weld overlay not required - S.S. SA350-LF2 CL.1+316 SS W.O. -> SA182-F316 | We will weld overlay for all nozzles except for liquid outlet nozzle C(3"). On the specification, there is no requirement that nozzles 3" and below shall be solid alloy nozzle. Therefore, we would like to perform the weld overlay for all nozzles except for C nozzle. If solid alloy nozzle shall be used by your requirement, the cost impact will occur. |  | OK
| Attachments: |  |  | N/A
TC-2
Open | 2-1 | ALL ITEMS | Comment for G/A drawing | Design of internal and detail drawings including supports. | We will submit the calculation and detail drawing later.
Open | 2-2 | ALL ITEMS | Comment for Body drawing | Vendor to confirm the orientation of all L/S seams in next revision. | The weld seam orientation can be fixed after receiving the orientation of nozzles. Please inform us the orientation of nozzle.
Open | 2-3 | ALL ITEMS |  | Vendor to ensure that welding of nozzles should not clash with any L/seam and C/seam of shell and D/end (submit development drawing) | We will try to avoid the clash of nozzle and weld seam, but we will inform you if there is no method in our side. For clash of L/seam, we can check after receiving the nozzle orientation. After receiving the orientation, we will submit the development drawing.
Open | 2-4 | ALL ITEMS |  | Weld size of washer in anchor chair | There is no standard of size of washer. We assume the weld size as 6mm. Please confirm. |  | 8mm
Open | 2-5 | ALL ITEMS |  | Weld size of Lifting, tailing or Trunnion lug | The weld size is verified by calculation, but your comment is too bigger than the calculation. Therefore, we would like to set the weld size of lifting, tailing or trunnion lug according to calculation. |  | As per comment
Open | 2-6 | ALL ITEMS |  | TRUNNION Provide two nos. cross stiffeners. | According to calculation, the trunnion is satisfactory without the stiffener. Therefore, we would like to leave the design of trunnion as is. If you have a standard of trunnion based on your comment, please send. |  | Required
Open | 2-7 | ALL ITEMS |  | REINFORCEMENT OF SKIRT OPENING Provide pad and Calculate the skirt considering opening | All skirt opening except skirt vent are provided the reinforcement pad. The area of reinf. pad and sleeve pipe is larger than opening area, so we think that the calculation of skirt opening is not needed. Therefore, we would like to except the calculation for skirt opening. |  | OK
Open | 2-8 | ALL ITEMS |  | HEIGHT OF MONKEY LADDER To change the spacing between ladder rung as 300 | If the spacing between ladder rung as 300, the vertical heights of each items are different because of angle of ladder. The different vertical height of ladder rung make user inconvenience, so, we will keep the vertical height between ladder rung as 300mm. |  | As per comment
Open | 2-9 | ALL ITEMS | Comment for Nozzle drawing | Flange face thickness for 600# flange | Flange face thickness is 7mm according to B16.5 2003ED and 6.4mm according to B16.47 1996ED. We will consider flange face thickness as 7mm because it can acceptable for tolerance.
Open | 2-10 | ALL ITEMS | Comment for Calculation -Fireproofing | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 2-11 | ALL ITEMS | Comment for Calculation -Nozzle Orientation | Nozzle orientation = 0 deg. | We assumed the nozzle orientation and incorporated in calculation. After receiving the orientation, we will revise the calculation. The change of nozzle orientation is no meaning, so we will leave the orientation as is at this stage.
| Attachments: |  |  | N/A
TC-3
Open | 3-1 | T-1201 | Comment for G/A drawing | DEMISTER Arrangement of demister is not correct. Please show demister arrangement as shown in Lurgi MDS rev.00. Also Provide detail and design of demister support beam(If required) | On MDS, the size of demister is under hold. Please confirm the size of demister. We will submit the detail drawing later. |  | By internal vendor
Open | 3-2 |  |  | TOP DAVIT 2500kg(Hold). Provide detail | The capacity is under hold. Please release the hold. The capacity as 2500kg is not mentioned on spec. S-00-1351-001 attachment-20, so please confirm the size of L and S mentioned on the spec. After receiving the size, we will calculate the top davit based on standard drawing. |  | To be informed
Open | 3-3 |  |  | ANCHOR BOTL ORIENTATION Please remove this detail. It is already covered in body detail. | We would like to leave the anchor bolt orientation on G/A drawing to indicate the anchor bolt size and quantity on G/A drawing. The other duplicated details are removed on the G/A drawing. |  | OK
Open | 3-4 |  | Comment for G/A drawing attached on calculation | TOLERANCE Sungjin to indicate general tolerance on dimension, Projection of nozzles, Location of nozzles, overall tolerance, verticality etc. as per Tolerance standard. | For tolerance, the note is indicated on general note as " vessel fabrication tolerances shall be in accordance with ASME code & ATTACHMENT-1 on 69815-01-06035 REV. 01. We think that the indication of tolerance on the drawing duplicately is not needed, so we would like to not indicate the tolerance on the drawing. |  | OK
Open | 3-5 |  |  | PLATFORM/LADDER DETAIL Sungjin to refer attached revised platform / ladder details on equipments. | We cannot find the platform / ladder detail. Please inform us. |  | OK
Open | 3-6 |  |  | NOZZLE ELEVATION Nozzle elevation for all process nozzles to be confirmed by equipment vendor based on feed back from column internal vendor. | After design of internal by internal vendor, we will inform if there is a change of nozzle elevation by process requirement. |  | OK
Open | 3-7 |  | Comment for Body drawing attached on calculation | ANCHOR BOLT DETAIL Details of provided anchor bolt of M72(SA193 Gr.B7) as it is in sungjin scope of supply | We will indicate the detail of anchor bolt on the template drawing in next revision. |  | Not Applicable
Open | 3-8 | T-1201 | Comment for Manhole detail (1/2) | TAPPED HOLES 3-M24 tapped holes @ 120 deg. Apart: 60 deg, 180 deg, 300 deg when top of flange is 0 deg. | We will provide 3-M24 tapped holes @ 120 deg. Apart: 0 deg, 120 deg, 240 deg when top of flange is 0 deg. Please confirm. |  | OK
Open | 3-9 |  | Comment for Nozzle detail (3/4) | INTERNAL PIPE OF A2 Also show internal plate flange pipe with elbow in dotted lines, thought it is in scope of column internal vendor | All internals by column internal vendor will be supplied by Sungjin. The detail of internal pipe of A2 nozzle will be indicated on separated drawing, so we will mention the drawing no. of internal pipe of A2 on nozzle drawing. |  | OK
Open | 3-10 |  | Comment for Nozzle detail (4/4) | VORTEX BREAKER Kindly note that this I s perforated plate vortex breaker. Vendor to ensure that free area perforated plate >> nozzle area. Therefore, vendor is requested provide details of perforated area considered. | We designed the hole size as 25 dia - 362 EA as shown on the drawing. The free area is 1776.96cm^2 and nozzle area is 1720.21cm^2, so the free area of perforated plate is larger than nozzle area. Please confirm the size and quantity of holes on perforated plate. |  | To be informed
Open | 3-11 |  | Comment for Calculation - inserted page | WEIGHT OF INTERNAL Consider weight of internals after getting confirmation form column internal vendor as column internals are in sungjin scope | The current calculation consider assumed weight of internal. After design of internal, we will incorporate the weight of internal in the calculation. |  | OK
Open | 3-12 |  | Comment for Calculation - inserted page | ANCHOR BOLT Sungjin to provide detail drawings and design of anchor bolt including length | According to e-mail on 30.Apr.2010, Lurgi mentioned that Lurgi can provide the details provide the vendor assures following the same as it is for SA193 Gr B7 anchor bolts. We request detail of anchor bolt by e-mail on 18.May.2010, but we did not received the detail. After receiving the detail of anchor bolt, we will submit the calculation of anchor bolt. |  | Not Applicable
Open | 3-13 | T-1301 | Comment for G.A. drawing | GENERAL NOTE All removable internals shall pass through manhole I.D. except nozzle(A1), as internal pipe of nozzle(A1) is 36". So, shall be placed before the closing seam. | This note is not applied to this item. Please confirm. |  | OK
Open | 3-14 | T-1301 | Comment for Body drawing | Lifting Trunnion, not required.(Refer design calculation pg.20) Please provide lifting lug. | We will be revise in next revision. |  | OK
Open | 3-15 | T-1301 | Comment for Manhole drawing | To mark "shell" under R2235 | The inside diameter without the note is shell inside diameter, the inside diameter is shell I.D. If the nozzle locate on head, the note "2:1 ELL. HEAD" or "HEMI. HEAD" is indicate. Therefore, we do not indicate the note "SHELL". |  | OK
Open | 3-16 | D-1201 D-1202 | Comment for G.A. drawing | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-17 | D-1201 D-1202 | Comment for G.A. drawing | MATERIAL OF GASKET SS316 SPWG FILLED WITH SS316 INNER RING & CS OUTER RING | The material of gasket is mentioned on general note 8 on G.A. drawing (2/2). |  | OK
Open | 3-18 | D-1201 D-1202 | Comment for Nozzle detail (2/3) | To change of off-centered distance of nozzle: V1(4") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") The Centerline Dist. is 371.11 while the sum of the ins. Radii is 462.60 - V1(3") and B1(36") The Centerline Dist. is 405.81 while the sum of the ins. Radii is 469.65 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1500. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-19 | D-1301 | Comment for G.A. drawing (1/2) | To change of off-centered distance of nozzle: V1(2") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1200 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 - V1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1700. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-20 | D-1301 | Comment for G.A. drawing (1/2) | TOLERANCE Tolerance on instrument pair nozzle shall be ±1. | According to spec., the tolerance of the distance between nozzles for level instruments is ±2. Please confirm whether ±1 tolerance is special requirement. |  | As per comment
Open | 3-21 | D-1301 | Comment for G.A. drawing (1/2) | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-22 | D-1301 | Comment for G.A. drawing (2/2) | ORIENTATION Please show all nozzles with impingement baffle as applicable. | On the orientation, one LT nozzle between 1 set of LT nozzle have impingement baffle. So, it may make a confusion for applied nozzle of baffle. We will indicate baffle elevation and detail of nozzle which have the baffle. |  | OK
Open | 3-23 | D-1311 | Comment for Body drawing | ANCHOR BOLT HOLE SIZE 5mm between straight part of hole | The comment is different from MDS. Please confirm.
Open | 3-24 | D-1401 | Comment for G.A drawing | To change of off-centered distance of nozzle: K1(2") nozzle : C.L.+1000 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - K1(2") and M(36") . The Centerline Dist. is 342.86 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1480. Please confirm whether the nozzle locations will be changed or keep the locations. |  | OK
Open | 3-25 | D-1401 | Supplementary Comment for G.A drawing | K2 NOZZLE To change K2 nozzle size to 18" | Opening of K2 nozzle is welded to straight flange part of shell. Please confirm the detail of K2 nozzle. |  | To be informed
Open | 3-26 | T1901 | Comment for Body drawing | SHELL THICKNESS Vendor has considered 18mm thickness in design calculation. Vendor is requested to check and confirm the thickness of shell based on WRC107 analysis of nozzle A1 | We calculate the nozzle A1 by design pressure, the nozzle thickness and shell and nozzle thickness are changed to same as MDS(t16). |  | OK
Open | 3-27 | D1901 D1902 | Comment for G.A. drawing | RECTANGULAR TUBES Show rectangular tubes tentatively | The rectangular tubes are indicated on section "Z-Z". We think that it is enough to express the rectangular tube. |  | OK
Open | 3-28 | D1901 D1902 | Comment for Body drawing | ANCHOR BOLT SLOT HOLE Straight section: 40mm | According to standard drawing attach.35, the straight section will be 60mm because the max. temp. difference is over 280℃.(Ope. Temp. 317℃ - AMB. Temp.(About 20℃)). Please confirm. |  | OK, but D1902 is 40mm
| Attachments: |  |  | N/A
TC-4
Closed | 4-1 | D1904 | Strength calculation | Calculation concept | We would like to inform you the concept of calculation as following: 1. Design pressure/temperature of shell - Int.: 4 bar+1.033 bar at 350 deg - Ext.: 8.5 bar at 195 deg - Ext.: Shop&Filed hydrotest pressure at AMB. 2. Nozzle - Only internal pressure will effect on The nozzles and body flange. - Only the opened area of jacket will be applied as a reinforcement area. In this area, the external C.A. is 0 and internal C.A. is 3. Please refer to the submitted calculation. | F.V (1.033 bar) is not applicable for shell & is applicable to jacket only. Ok, noted
Closed | 4-2 | D1904 | G.A. and jacket detail drawing | Jacket closure | According to MDS, the jacket closure is type (c) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. In this case, for nozzle, the shape of jacket closure is a shape transforming the cone and it cannot be made by rolling of plate. So, it is very difficult to forming plate and the installation also. Therefore, we would like to change the shape of jacket closure type (d-1) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. | If vendor feels problem in fabrication and installation. So, he may opt for closure type (d-1) of Fig.9-5, provided all the requirements as per Appendix. 9 of ASME Sec. VIII Div.1 are met with.
Closed | 4-3 | D1904 | G.A. and jacket detail drawing | Stiff. ring of jacket | According to MDS, there are two stiff. ring for jacket. We think that the space to locate the shipping saddle is not enough and the vessel is small, so we deleted the stiff. Ring and increase the jacket thickness from min. 10mm to 12mm. Please confirm. | Ok, Noted
Closed | 4-2 | D1904 | G.A. and body detail drawing | Lifting lug at top head | According to MDS, the lifting lug at top head is welded on inside head. However, the weight of top part is about 2.2 tons, and the covering of jacket head which cut off the area for lifting lug is difficult. Therefore, we would like to weld the lifting lug at jacket head. | If suppose lifting lug is welded to jacket, then there may have the chances that jacket to jacket or jacket to shell weld can come in shear stress. So, it is advisable to weld lifitng lug on shell & sungjin can increase the opening in jacket (for lifting lug) suitably.
Attachments:
TC-5
Open | 5-1 | D1101 | G.A. drawing | Nozzle orientation | When we submit the drawings, we did not received the nozzle orientation. There are many change on the drawing, so we submit the drawings without change of nozzle orientation and L-seam orientation. In the next revision, we will incorporate the nozzle and L-seam orientation on the drawing. If you require, we will resubmit the drawing indicated orientation in same revision to replace the drawing.
Open | 5-2 | D1101 | Manhole and Nozzle detail drawings | Hub height | We revise all drawing and calculation for hub height based on nozzle projection.
Open | 5-3 | D1101 | Manhole detail drawing | Elevation of top ladder rung | On the commented drawing, the top ladder rung is located under 900mm from bottom of demister. But, according to standard drawing(attachment-2 of pressure vessel spec.), the top ladder rung shall be located under 805mm from bottom of demister as shown on the drawing. Please confirm.
Open | 5-4 | D1101 | Nozzle detail drawing | Material of small size nozzes except for C nozzle | On the drawing in rev.2, the material of small size nozzles(2"&3") except for C nozzle is SA182-F316. As discussed during meeting in India, all nozzles except for C nozzles will be SA350-LF2-CL1 + 316L W.O.
Open | 5-5 | D1101 | Nozzle detail drawing | Reinf. pad of skirt opening | As discussed during meeting in India, the reinf. pads of skirt opening for C nozzle and skirt access are deleted. (All reinf. pads of skirt opening for all drum will be deleted.)
Open | 5-6 | D1101 D1201 D1202 D1301 | Internal ass'y & detail drawing | Type of demister | On the MDS, the type of demister is TYPE "V-b". However, the demister of Type V is for equipment which manhole is located on the top head. It means that the demister cannot remove after installation because demister fixed by bolting and the nut on lower side is tack welded and the manhole in located under demister. We think that "TYPE II-A-b" is suitable for these equipments, we applied on the drawing. Please confirm.
Open | 5-7 | D1101 D1201 D1202 D1301 | Internal drawings and calculation | Revision of drawing and calculation | The drawing and calculation is first submission, but the revision number is "1". It is because internal vendor submit all drawings in rev.0 to us before receiving Lurgi's datasheet but there are some revision because of change of MDS. So, internal vendor issued all documents in rev.1. We would like to leave the revision number as "1" considering document control of internal vendor. Please confirm.
Attachments:
TC-6
Open | 6-1 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Reference elevation | According to Lurgi standard for platform, the reference elevation is TOS. So. we designed the platform for all items based on TOS elevation. However, on the nozzle orientation for 1/2T-1201, the elevation is based on TOG. Please confirm the basis of reference elevation. | In nozzle orientation, elevation referred is TOG. (Typ. For all unless otherwise specified) & TOS = TOG - [Grating th'k(25)+TOE angle th'k(10)] => TOS = TOG-35.
Open | 6-2 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Hillside location of W1 nozzle | On the nozzle orientation, the hillside location of W1 nozzle is 1820mm. In this case, the welding of HB-01 seam and W1 nozzle are overlapped. Therefore, we would like to leave the hillside location of W1 as 1600mm same as latest drawing. | 1600 FOR W1 is OK.
Open | 6-3 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Difference from standard drawing for ladder | On the nozzle orientation, there are some difference from standard drawing for ladder. Please find the example as below: 1. On the plan from el.130000 to el.133000, the distance between center of ladder at 5° and platform at right side is 400mm. However, according to standard details 69815-01-29108, the distance is 380mm. 2. On the plan from EL.130000 to EL.133000, the distance between ladder rung from vessel center is 2950mm. However, according to standard details 69815-01-29108, the distance is 3030mm(vessel O.D./2 (2740mm) + insul. th'k (30mm) + 260mm). Therefore, we would like to follow the standard drawing if the standard drawing and platform information are different. | 1. 380 is OK as per standard drg. 400 will be deleted from orientation plan. 2. Follow standard drg. Dimention form orientation plan will be deleted.
Open | 6-4 | T1201 | Nozzle orientation 69815-01-28292 rev.0 | A01 orientation | On the plan from EL.100000 to EL.106500, there are two access opening as A02. Please confirm. | Consider A02 at 0 degree as A01.
Open | 6-5 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | L3A/B, L4A/B orientation | L3A/B, L4A/B orientation is not mentioned on nozzle orientation drawing. Please confirm. | Orientation - L3A/B: 60, L4a/b : 135°
Open | 6-6 | T1301 | Nozzle orientation 69815-01-27530 rev.0 | The location of D1 nozzle on B2 nozzle | On the latest drawing, D1 nozzle is located bottom of neck pipe of B2 nozzle. However, on the nozzle orientation, the D1 nozzle looks like using elbow. If it is correct, D1 nozzle shall be changed from long welding neck flange to welding neck flange + elbow + pipe. Please confirm. | D1 nozzle is with elbow i.e. WN flange +elbow+pipe.
Open | 6-7 | D1301 | Nozzle orientation 69815-01-27522 rev.0 | The top platform elevation | On the nozzle orientation, the elevation of top platform is T.L+ 8170mm. In this case, the bracket of top platform is interfered with top head. Therefore, we would like to increase the elevation of top platform from T.L+8170mm to T.L+8520mm. | Change top platform elevation to 112850(instead of 112470) i.e. 8550 from B.T.L
Open | 6-8 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Off-centered dimention of S1&S2 nozzle | As per nozzle orientation, off-centered dimention of S1&S2 nozzle is 1900mm, but the nozzles are interfered with circ. seam of head as mentioned on meeting in India. The location of S1&S2 nozzle have been confirmed by comments received on 7.7.2010, so the location of S1&S2 nozzle will be following the comments as 1950mm from center line. Please confirm. | OK. 1950 acceptable.
Open | 6-9 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Projection of L3B&L8B nozzle | As per nozzle orientation, the projection of L3B&L8B nozzle is 3720mm. In this case, the beveled transition of forged neck is located under surface of vessel. Therefore, we increased nozzle projection from 3720mm to 3800mm same as last revision. Please confirm. | OK. 3800 acceptable.
Open | 6-10 | D1401 | Nozzle orientation 69815-01-28151 rev.0 | Off-centered dimention of K1 nozzle | As per nozzle orientation, off-centered dimention of K1 nozzle is 990mm, but the nozzles are too closed with M manhole under ASME code as mentioned on meeting in India. The location of K1 nozzle have been confirmed by comments received on 19.7.2010, so the location of K1 nozzle will be following the comments as 1480mm from center line. Please confirm. | OK. 1480 acceptable. Already cleared in dwg. 698150131096 rev.3.
Attachments:
TC-7
Open | 7-1 | T1201 D1201 D1202 D1301 | - | Material of external bolt/nut under sour service | According to MDS, the material of external bolt/nut is SA193-B7/SA194-2H. Also, as per NACE MR 0103, the bolt/nut material exposed to sour environments shall be used SA193-B7M/SA194-2HM. We think that the external bolt/nuts are not contacted with sour contents, so it is not required to apply NACE MR 0103. Please confirm. | Acceptable
Open | 7-2 | T1301 | Body detail(1/2) 698150131085 | The material of Y-ring | According to comment, the material of Y-ring shall be SA266-2 instead of SA105N. There was a mistake for purchacing of material, so the Y-ring material was according to SA105 instead of SA266-2. Even though, the material is over the limitation of SA105, but we think that the most important factor of material is mechanical property and the mechanical property of SA105 is same between SA105 and SA266-2. We calculated the y-ring by FEA and the result was satisfactory. The material was verified by simulation test as attached mill certification. Now, we had purchased the forging material and welded into the shell. Therefore, we would like to use the forging material in SA105. | Material of y-ring to be changed from SA105 to SA266-2 in detail drawing. => 도면상 SA266-6으로 변경 및 Mill certi. 변경 예정
Open | 7-3 | T1301 | Body detail(2/2) 698150131086 | Trunnion lug | According to comment, the trunnion lug is not required and is changed to lifting lug as discussed during meeting. However, we had purchased the material for trunnion lugs, so we would like to use the trunnion lugs. | Acceptable, subjected to approval of design calculation.
Open | 7-4 | T1301 | Nozzle detail (1/2) 698150131088 | Raised face for filler flange | According to comment, the thickness of raised face for filler flange shall be 6.35mm. 7mm thickness of raised face is based on B16.47 2003 edition. The flange is non-standard flange, thickness of raised face is not effect on the strength calculation and we check the flange thickness(191mm) by calculation and there is no problem for flange. Also, the difference is very small as 0.65mm, so we would like to use the rased face for filler flange as 7mm. | Accepted
Open | 7-5 | D1301 | Nozzle detail (3/3) 698150131069 | The reinf. pad for access opening | According to comment, the reinf. pad for access opening shall be full penetration welding. However, as discussed during meeting, the reinf. pad will be deleted for drums. For information, the skirt and opening will be full penetration welding. | Accepted
Open | 7-6 | D1401 | Nozzle detail (4/4) 698150131099 | The material of skirt vent | According to comment, the material of skirt vent shall be SA106-B as in earlier revision. However, the skirt vent is welded to non-pressure part, so we think that it is not required to use SA106-B. Therefore, we would like to change the material of skirt vent from SA106-B to SA53-B. | Not accpeted, Sungjin to consider SA106 gr.B for skirt vent.
Open | 7-7 | ALL ITEMS | - | Location of monkey ladders | The location of monkey ladders are commented, but all monkey ladders are interfered with the skirt bracing beam. In current design, the orientation of monkey ladder shall be in same or +/- 10 deg of lifting trunnion/lugs. | Sungjin to adjust location of monkey ladder accordingly to avoid fouling with skirt bracking beam & access opening.
END OF DOCUMENT
Open | 7-4 | D1301 |  |  | MANHOLE & 노즐 간섭
Open | 7-5 | D1401 |  |  | VENT와 SEAM 간섭
Open | 7-8 | T1901 |  |  | 구매폭 때문에 단동길이 바뀐다

## 1st 추가 (hidden)
Additional Outstanding
▶Project : Iran LNG - Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0003 | 26.Jan.2011
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Lurgi's Response
[5 empty] | TC-1 |  | Confirmation during meeting
Open | 1-1 | D-1101 | page.7 Comment for Calculation rev.1 | Bottom Skirt Length: 4800 -> 3458 | The skirt length in PV-elite shall include the basering thickness because of the distance from base elevation to bottom T.L. Therefore, we changed the bottom skirt length from 3458mm to 3500mm. |  | OK
Open | 1-2 | D-1101 | page.7 Comment for Calculation rev.1 | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 1-3 | D-1101 | Comment for General assembly rev.1 | To change of off-centered distance of nozzle: V(4") nozzle : C.L.+1200 P(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2")(C.L.+1100) and B(46") The Centerline Dist. is 375.36 while the sum of the ins. Radii is 559.60. - V(4")(C.L.+1200) and B(46") The Centerline Dist. is 411.43 while the sum of the ins. Radii is 580.25. To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V nozzle shall be over C.L.+2000. Please confirm whether the nozzle locations will be changed or keep the locations. |  | TO BE INFORMED
Open | 1-4 | D-1101 | Comment for Manhole detail rev.1 | To avoid any changes of cracking/shearing, weld overlay on face of the flange shall be done by providing an under cut in the flange thk. And thus increasing the flange overall thk. by approx.2mm. | We normally perform weld overlay on face of the flange with overlay thickness min.4.5mm and there is no change of cracking/shearking. The weld overlay detail shown on the revised drawing in rev.2 is enough to meet spec. requirement and avoid any change. Therefore, we will proceed the weld overlay of flange same as revised drawing in rev.2. |  | OK
Open | 1-5 | D-1101 | Comment for Manhole detail rev.1 | Please check the material "SA350-LF2 CL.1". If "class" is applicable in 'Div.2'. | According to Sec.VIII Div.2 2004 ED.+2006 ADD., the class of SA350-LF2 is not indicated and also in Sec.II Part.D table.2A. However, according to Sec.II Part.A SA350, SA350-LF2 is shall be indicate the class of material to purchase. SA350-LF2 class.1 and class.2 have same mechanical and chemical property and the impact test requirement is different. (Standard impact test temperature - Class.1: -46℃, Class.2 -18℃) Therefore, we will use class.1 of SA350-LF2 because MDMT is -30℃. |  | OK
Open | 1-6 | D-1101 | Comment for nozzle detail (2/3) rev.1 | Nozzle size 3" and below, weld overlay not required - S.S. SA350-LF2 CL.1+316 SS W.O. -> SA182-F316 | We will weld overlay for all nozzles except for liquid outlet nozzle C(3"). On the specification, there is no requirement that nozzles 3" and below shall be solid alloy nozzle. Therefore, we would like to perform the weld overlay for all nozzles except for C nozzle. If solid alloy nozzle shall be used by your requirement, the cost impact will occur. |  | OK
| Attachments: |  |  | N/A
TC-2
Open | 2-1 | ALL ITEMS | Comment for G/A drawing | Design of internal and detail drawings including supports. | We will submit the calculation and detail drawing later.
Open | 2-2 | ALL ITEMS | Comment for Body drawing | Vendor to confirm the orientation of all L/S seams in next revision. | The weld seam orientation can be fixed after receiving the orientation of nozzles. Please inform us the orientation of nozzle.
Open | 2-3 | ALL ITEMS |  | Vendor to ensure that welding of nozzles should not clash with any L/seam and C/seam of shell and D/end (submit development drawing) | We will try to avoid the clash of nozzle and weld seam, but we will inform you if there is no method in our side. For clash of L/seam, we can check after receiving the nozzle orientation. After receiving the orientation, we will submit the development drawing.
Open | 2-4 | ALL ITEMS |  | Weld size of washer in anchor chair | There is no standard of size of washer. We assume the weld size as 6mm. Please confirm. |  | 8mm
Open | 2-5 | ALL ITEMS |  | Weld size of Lifting, tailing or Trunnion lug | The weld size is verified by calculation, but your comment is too bigger than the calculation. Therefore, we would like to set the weld size of lifting, tailing or trunnion lug according to calculation. |  | As per comment
Open | 2-6 | ALL ITEMS |  | TRUNNION Provide two nos. cross stiffeners. | According to calculation, the trunnion is satisfactory without the stiffener. Therefore, we would like to leave the design of trunnion as is. If you have a standard of trunnion based on your comment, please send. |  | Required
Open | 2-7 | ALL ITEMS |  | REINFORCEMENT OF SKIRT OPENING Provide pad and Calculate the skirt considering opening | All skirt opening except skirt vent are provided the reinforcement pad. The area of reinf. pad and sleeve pipe is larger than opening area, so we think that the calculation of skirt opening is not needed. Therefore, we would like to except the calculation for skirt opening. |  | OK
Open | 2-8 | ALL ITEMS |  | HEIGHT OF MONKEY LADDER To change the spacing between ladder rung as 300 | If the spacing between ladder rung as 300, the vertical heights of each items are different because of angle of ladder. The different vertical height of ladder rung make user inconvenience, so, we will keep the vertical height between ladder rung as 300mm. |  | As per comment
Open | 2-9 | ALL ITEMS | Comment for Nozzle drawing | Flange face thickness for 600# flange | Flange face thickness is 7mm according to B16.5 2003ED and 6.4mm according to B16.47 1996ED. We will consider flange face thickness as 7mm because it can acceptable for tolerance.
Open | 2-10 | ALL ITEMS | Comment for Calculation -Fireproofing | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 2-11 | ALL ITEMS | Comment for Calculation -Nozzle Orientation | Nozzle orientation = 0 deg. | We assumed the nozzle orientation and incorporated in calculation. After receiving the orientation, we will revise the calculation. The change of nozzle orientation is no meaning, so we will leave the orientation as is at this stage.
| Attachments: |  |  | N/A
TC-3
Open | 3-1 | T-1201 | Comment for G/A drawing | DEMISTER Arrangement of demister is not correct. Please show demister arrangement as shown in Lurgi MDS rev.00. Also Provide detail and design of demister support beam(If required) | On MDS, the size of demister is under hold. Please confirm the size of demister. We will submit the detail drawing later. |  | By internal vendor
Open | 3-2 |  |  | TOP DAVIT 2500kg(Hold). Provide detail | The capacity is under hold. Please release the hold. The capacity as 2500kg is not mentioned on spec. S-00-1351-001 attachment-20, so please confirm the size of L and S mentioned on the spec. After receiving the size, we will calculate the top davit based on standard drawing. |  | To be informed
Open | 3-3 |  |  | ANCHOR BOTL ORIENTATION Please remove this detail. It is already covered in body detail. | We would like to leave the anchor bolt orientation on G/A drawing to indicate the anchor bolt size and quantity on G/A drawing. The other duplicated details are removed on the G/A drawing. |  | OK
Open | 3-4 |  | Comment for G/A drawing attached on calculation | TOLERANCE Sungjin to indicate general tolerance on dimension, Projection of nozzles, Location of nozzles, overall tolerance, verticality etc. as per Tolerance standard. | For tolerance, the note is indicated on general note as " vessel fabrication tolerances shall be in accordance with ASME code & ATTACHMENT-1 on 69815-01-06035 REV. 01. We think that the indication of tolerance on the drawing duplicately is not needed, so we would like to not indicate the tolerance on the drawing. |  | OK
Open | 3-5 |  |  | PLATFORM/LADDER DETAIL Sungjin to refer attached revised platform / ladder details on equipments. | We cannot find the platform / ladder detail. Please inform us. |  | OK
Open | 3-6 |  |  | NOZZLE ELEVATION Nozzle elevation for all process nozzles to be confirmed by equipment vendor based on feed back from column internal vendor. | After design of internal by internal vendor, we will inform if there is a change of nozzle elevation by process requirement. |  | OK
Open | 3-7 |  | Comment for Body drawing attached on calculation | ANCHOR BOLT DETAIL Details of provided anchor bolt of M72(SA193 Gr.B7) as it is in sungjin scope of supply | We will indicate the detail of anchor bolt on the template drawing in next revision. |  | Not Applicable
Open | 3-8 | T-1201 | Comment for Manhole detail (1/2) | TAPPED HOLES 3-M24 tapped holes @ 120 deg. Apart: 60 deg, 180 deg, 300 deg when top of flange is 0 deg. | We will provide 3-M24 tapped holes @ 120 deg. Apart: 0 deg, 120 deg, 240 deg when top of flange is 0 deg. Please confirm. |  | OK
Open | 3-9 |  | Comment for Nozzle detail (3/4) | INTERNAL PIPE OF A2 Also show internal plate flange pipe with elbow in dotted lines, thought it is in scope of column internal vendor | All internals by column internal vendor will be supplied by Sungjin. The detail of internal pipe of A2 nozzle will be indicated on separated drawing, so we will mention the drawing no. of internal pipe of A2 on nozzle drawing. |  | OK
Open | 3-10 |  | Comment for Nozzle detail (4/4) | VORTEX BREAKER Kindly note that this I s perforated plate vortex breaker. Vendor to ensure that free area perforated plate >> nozzle area. Therefore, vendor is requested provide details of perforated area considered. | We designed the hole size as 25 dia - 362 EA as shown on the drawing. The free area is 1776.96cm^2 and nozzle area is 1720.21cm^2, so the free area of perforated plate is larger than nozzle area. Please confirm the size and quantity of holes on perforated plate. |  | To be informed
Open | 3-11 |  | Comment for Calculation - inserted page | WEIGHT OF INTERNAL Consider weight of internals after getting confirmation form column internal vendor as column internals are in sungjin scope | The current calculation consider assumed weight of internal. After design of internal, we will incorporate the weight of internal in the calculation. |  | OK
Open | 3-12 |  | Comment for Calculation - inserted page | ANCHOR BOLT Sungjin to provide detail drawings and design of anchor bolt including length | According to e-mail on 30.Apr.2010, Lurgi mentioned that Lurgi can provide the details provide the vendor assures following the same as it is for SA193 Gr B7 anchor bolts. We request detail of anchor bolt by e-mail on 18.May.2010, but we did not received the detail. After receiving the detail of anchor bolt, we will submit the calculation of anchor bolt. |  | Not Applicable
Open | 3-13 | T-1301 | Comment for G.A. drawing | GENERAL NOTE All removable internals shall pass through manhole I.D. except nozzle(A1), as internal pipe of nozzle(A1) is 36". So, shall be placed before the closing seam. | This note is not applied to this item. Please confirm. |  | OK
Open | 3-14 | T-1301 | Comment for Body drawing | Lifting Trunnion, not required.(Refer design calculation pg.20) Please provide lifting lug. | We will be revise in next revision. |  | OK
Open | 3-15 | T-1301 | Comment for Manhole drawing | To mark "shell" under R2235 | The inside diameter without the note is shell inside diameter, the inside diameter is shell I.D. If the nozzle locate on head, the note "2:1 ELL. HEAD" or "HEMI. HEAD" is indicate. Therefore, we do not indicate the note "SHELL". |  | OK
Open | 3-16 | D-1201 D-1202 | Comment for G.A. drawing | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-17 | D-1201 D-1202 | Comment for G.A. drawing | MATERIAL OF GASKET SS316 SPWG FILLED WITH SS316 INNER RING & CS OUTER RING | The material of gasket is mentioned on general note 8 on G.A. drawing (2/2). |  | OK
Open | 3-18 | D-1201 D-1202 | Comment for Nozzle detail (2/3) | To change of off-centered distance of nozzle: V1(4") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") The Centerline Dist. is 371.11 while the sum of the ins. Radii is 462.60 - V1(3") and B1(36") The Centerline Dist. is 405.81 while the sum of the ins. Radii is 469.65 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1500. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-19 | D-1301 | Comment for G.A. drawing (1/2) | To change of off-centered distance of nozzle: V1(2") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1200 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 - V1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1700. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-20 | D-1301 | Comment for G.A. drawing (1/2) | TOLERANCE Tolerance on instrument pair nozzle shall be ±1. | According to spec., the tolerance of the distance between nozzles for level instruments is ±2. Please confirm whether ±1 tolerance is special requirement. |  | As per comment
Open | 3-21 | D-1301 | Comment for G.A. drawing (1/2) | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-22 | D-1301 | Comment for G.A. drawing (2/2) | ORIENTATION Please show all nozzles with impingement baffle as applicable. | On the orientation, one LT nozzle between 1 set of LT nozzle have impingement baffle. So, it may make a confusion for applied nozzle of baffle. We will indicate baffle elevation and detail of nozzle which have the baffle. |  | OK
Open | 3-23 | D-1311 | Comment for Body drawing | ANCHOR BOLT HOLE SIZE 5mm between straight part of hole | The comment is different from MDS. Please confirm.
Open | 3-24 | D-1401 | Comment for G.A drawing | To change of off-centered distance of nozzle: K1(2") nozzle : C.L.+1000 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - K1(2") and M(36") . The Centerline Dist. is 342.86 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1480. Please confirm whether the nozzle locations will be changed or keep the locations. |  | OK
Open | 3-25 | D-1401 | Supplementary Comment for G.A drawing | K2 NOZZLE To change K2 nozzle size to 18" | Opening of K2 nozzle is welded to straight flange part of shell. Please confirm the detail of K2 nozzle. |  | To be informed
Open | 3-26 | T1901 | Comment for Body drawing | SHELL THICKNESS Vendor has considered 18mm thickness in design calculation. Vendor is requested to check and confirm the thickness of shell based on WRC107 analysis of nozzle A1 | We calculate the nozzle A1 by design pressure, the nozzle thickness and shell and nozzle thickness are changed to same as MDS(t16). |  | OK
Open | 3-27 | D1901 D1902 | Comment for G.A. drawing | RECTANGULAR TUBES Show rectangular tubes tentatively | The rectangular tubes are indicated on section "Z-Z". We think that it is enough to express the rectangular tube. |  | OK
Open | 3-28 | D1901 D1902 | Comment for Body drawing | ANCHOR BOLT SLOT HOLE Straight section: 40mm | According to standard drawing attach.35, the straight section will be 60mm because the max. temp. difference is over 280℃.(Ope. Temp. 317℃ - AMB. Temp.(About 20℃)). Please confirm. |  | OK, but D1902 is 40mm
| Attachments: |  |  | N/A
TC-4
Closed | 4-1 | D1904 | Strength calculation | Calculation concept | We would like to inform you the concept of calculation as following: 1. Design pressure/temperature of shell - Int.: 4 bar+1.033 bar at 350 deg - Ext.: 8.5 bar at 195 deg - Ext.: Shop&Filed hydrotest pressure at AMB. 2. Nozzle - Only internal pressure will effect on The nozzles and body flange. - Only the opened area of jacket will be applied as a reinforcement area. In this area, the external C.A. is 0 and internal C.A. is 3. Please refer to the submitted calculation. | F.V (1.033 bar) is not applicable for shell & is applicable to jacket only. Ok, noted
Closed | 4-2 | D1904 | G.A. and jacket detail drawing | Jacket closure | According to MDS, the jacket closure is type (c) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. In this case, for nozzle, the shape of jacket closure is a shape transforming the cone and it cannot be made by rolling of plate. So, it is very difficult to forming plate and the installation also. Therefore, we would like to change the shape of jacket closure type (d-1) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. | If vendor feels problem in fabrication and installation. So, he may opt for closure type (d-1) of Fig.9-5, provided all the requirements as per Appendix. 9 of ASME Sec. VIII Div.1 are met with.
Closed | 4-3 | D1904 | G.A. and jacket detail drawing | Stiff. ring of jacket | According to MDS, there are two stiff. ring for jacket. We think that the space to locate the shipping saddle is not enough and the vessel is small, so we deleted the stiff. Ring and increase the jacket thickness from min. 10mm to 12mm. Please confirm. | Ok, Noted
Closed | 4-2 | D1904 | G.A. and body detail drawing | Lifting lug at top head | According to MDS, the lifting lug at top head is welded on inside head. However, the weight of top part is about 2.2 tons, and the covering of jacket head which cut off the area for lifting lug is difficult. Therefore, we would like to weld the lifting lug at jacket head. | If suppose lifting lug is welded to jacket, then there may have the chances that jacket to jacket or jacket to shell weld can come in shear stress. So, it is advisable to weld lifitng lug on shell & sungjin can increase the opening in jacket (for lifting lug) suitably.
Attachments:
TC-5
Open | 5-1 | D1101 | G.A. drawing | Nozzle orientation | When we submit the drawings, we did not received the nozzle orientation. There are many change on the drawing, so we submit the drawings without change of nozzle orientation and L-seam orientation. In the next revision, we will incorporate the nozzle and L-seam orientation on the drawing. If you require, we will resubmit the drawing indicated orientation in same revision to replace the drawing.
Open | 5-2 | D1101 | Manhole and Nozzle detail drawings | Hub height | We revise all drawing and calculation for hub height based on nozzle projection.
Open | 5-3 | D1101 | Manhole detail drawing | Elevation of top ladder rung | On the commented drawing, the top ladder rung is located under 900mm from bottom of demister. But, according to standard drawing(attachment-2 of pressure vessel spec.), the top ladder rung shall be located under 805mm from bottom of demister as shown on the drawing. Please confirm.
Open | 5-4 | D1101 | Nozzle detail drawing | Material of small size nozzes except for C nozzle | On the drawing in rev.2, the material of small size nozzles(2"&3") except for C nozzle is SA182-F316. As discussed during meeting in India, all nozzles except for C nozzles will be SA350-LF2-CL1 + 316L W.O.
Open | 5-5 | D1101 | Nozzle detail drawing | Reinf. pad of skirt opening | As discussed during meeting in India, the reinf. pads of skirt opening for C nozzle and skirt access are deleted. (All reinf. pads of skirt opening for all drum will be deleted.)
Open | 5-6 | D1101 D1201 D1202 D1301 | Internal ass'y & detail drawing | Type of demister | On the MDS, the type of demister is TYPE "V-b". However, the demister of Type V is for equipment which manhole is located on the top head. It means that the demister cannot remove after installation because demister fixed by bolting and the nut on lower side is tack welded and the manhole in located under demister. We think that "TYPE II-A-b" is suitable for these equipments, we applied on the drawing. Please confirm.
Open | 5-7 | D1101 D1201 D1202 D1301 | Internal drawings and calculation | Revision of drawing and calculation | The drawing and calculation is first submission, but the revision number is "1". It is because internal vendor submit all drawings in rev.0 to us before receiving Lurgi's datasheet but there are some revision because of change of MDS. So, internal vendor issued all documents in rev.1. We would like to leave the revision number as "1" considering document control of internal vendor. Please confirm.
Attachments:
TC-6
Open | 6-1 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Reference elevation | According to Lurgi standard for platform, the reference elevation is TOS. So. we designed the platform for all items based on TOS elevation. However, on the nozzle orientation for 1/2T-1201, the elevation is based on TOG. Please confirm the basis of reference elevation.
Open | 6-2 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Hillside location of W1 nozzle | On the nozzle orientation, the hillside location of W1 nozzle is 1820mm. In this case, the welding of HB-01 seam and W1 nozzle are overlapped. Therefore, we would like to leave the hillside location of W1 as 1600mm same as latest drawing.
Open | 6-3 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Difference from standard drawing for ladder | On the nozzle orientation, there are some difference from standard drawing for ladder. Please find the example as below: 1. On the plan from el.130000 to el.133000, the distance between center of ladder at 5° and platform at right side is 400mm. However, according to standard details 69815-01-29108, the distance is 380mm. 2. On the plan from EL.130000 to EL.133000, the distance between ladder rung from vessel center is 2950mm. However, according to standard details 69815-01-29108, the distance is 3030mm(vessel O.D./2 (2740mm) + insul. th'k (30mm) + 260mm). Therefore, we would like to follow the standard drawing if the standard drawing and platform information are different.
Open | 6-4 | T1201 | Nozzle orientation 69815-01-28292 rev.0 | A01 orientation | On the plan from EL.100000 to EL.106500, there are two access opening as A02. Please confirm.
Open | 6-5 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | L3A/B, L4A/B orientation | L3A/B, L4A/B orientation is not mentioned on nozzle orientation drawing. Please confirm.
Open | 6-6 | T1301 | Nozzle orientation 69815-01-27530 rev.0 | The location of D1 nozzle on B2 nozzle | On the latest drawing, D1 nozzle is located bottom of neck pipe of B2 nozzle. However, on the nozzle orientation, the D1 nozzle looks like using elbow. If it is correct, D1 nozzle shall be changed from long welding neck flange to welding neck flange + elbow + pipe. Please confirm.
Open | 6-7 | D1301 | Nozzle orientation 69815-01-27522 rev.0 | The top platform elevation | On the nozzle orientation, the elevation of top platform is T.L+ 8170mm. In this case, the bracket of top platform is interfered with top head. Therefore, we would like to increase the elevation of top platform from T.L+8170mm to T.L+8520mm.
Open | 6-8 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Off-centered dimention of S1&S2 nozzle | As per nozzle orientation, off-centered dimention of S1&S2 nozzle is 1900mm, but the nozzles are interfered with circ. seam of head as mentioned on meeting in India. The location of S1&S2 nozzle have been confirmed by comments received on 7.7.2010, so the location of S1&S2 nozzle will be following the comments as 1950mm from center line. Please confirm.
Open | 6-9 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Projection of L3B&L8B nozzle | As per nozzle orientation, the projection of L3B&L8B nozzle is 3720mm. In this case, the beveled transition of forged neck is located under surface of vessel. Therefore, we increased nozzle projection from 3720mm to 3800mm same as last revision. Please confirm.
Open | 6-10 | D1401 | Nozzle orientation 69815-01-28151 rev.0 | Off-centered dimention of K1 nozzle | As per nozzle orientation, off-centered dimention of K1 nozzle is 990mm, but the nozzles are too closed with M manhole under ASME code as mentioned on meeting in India. The location of K1 nozzle have been confirmed by comments received on 19.7.2010, so the location of K1 nozzle will be following the comments as 1480mm from center line. Please confirm.
Attachments:
TC-7
Open | 7-1 | T1201 D1201 D1202 D1301 | - | Material of external bolt/nut under sour service | According to MDS, the material of external bolt/nut is SA193-B7/SA194-2H. Also, as per NACE MR 0103, the bolt/nut material exposed to sour environments shall be used SA193-B7M/SA194-2HM. We think that the external bolt/nuts are not contacted with sour contents, so it is not required to apply NACE MR 0103. Please confirm.
Open | 7-2 | T1301 | Body detail(1/2) 698150131085 | The material of Y-ring | According to comment, the material of Y-ring shall be SA266-2 instead of SA105N. There was a mistake for purchacing of material, so the Y-ring material was according to SA105 instead of SA266-2. Even though, the material is over the limitation of SA105, but we think that the most important factor of material is mechanical property and the mechanical property of SA105 is same between SA105 and SA266-2. We calculated the y-ring by FEA and the result was satisfactory. The material was verified by simulation test as attached mill certification. Now, we had purchased the forging material and welded into the shell. Therefore, we would like to use the forging material in SA105.
Open | 7-3 | T1301 | Body detail(2/2) 698150131086 | Trunnion lug | According to comment, the trunnion lug is not required and is changed to lifting lug as discussed during meeting. However, we had purchased the material for trunnion lugs, so we would like to use the trunnion lugs.
Open | 7-4 | T1301 | Nozzle detail (1/2) 698150131088 | Raised face for filler flange | According to comment, the thickness of raised face for filler flange shall be 6.35mm. 7mm thickness of raised face is based on B16.47 2003 edition. The flange is non-standard flange, thickness of raised face is not effect on the strength calculation and we check the flange thickness(191mm) by calculation and there is no problem for flange. Also, the difference is very small as 0.65mm, so we would like to use the rased face for filler flange as 7mm.
Open | 7-5 | D1301 | Nozzle detail (3/3) 698150131069 | The reinf. pad for access opening | According to comment, the reinf. pad for access opening shall be full penetration welding. However, as discussed during meeting, the reinf. pad will be deleted for drums. For information, the skirt and opening will be full penetration welding.
Open | 7-6 | D1401 | Nozzle detail (4/4) 698150131099 | The material of skirt vent | According to comment, the material of skirt vent shall be SA106-B as in earlier revision. However, the skirt vent is welded to non-pressure part, so we think that it is not required to use SA106-B. Therefore, we would like to change the material of skirt vent from SA106-B to SA53-B.
Open | 7-7 | ALL ITEMS | - | Location of monkey ladders | The location of monkey ladders are commented, but all monkey ladders are interfered with the skirt bracing beam. In current design, the orientation of monkey ladder shall be in same or +/- 10 deg of lifting trunnion/lugs.
END OF DOCUMENT
TC-8
Open | 8-1 | D1311 | General assembly (1/2) 698150131072 | Location of L9A/B & L10A/B nozzle | You commented to rearrange the seam(B-02). However, there is no piece of shell to avoid the interference. Therefore, we would like to locate L9A/B at T.L.+1425mm and L10A/B at T.L.+1675mm and leave the actual distance between weld edges. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 8-2 | D1311 | General assembly (1/2) 698150131072 | Hillside nozzle projection in shell side | All nozzles projection in hill side located in shell is changed from 3750mm to 3780mm. The flange, pipe and forged neck have been welded based on the projection 3750mm. We would like to keep the projection in hill side located in shell as 3750mm. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 8-3 | D1311 | General assembly (1/2) 698150131072 | Projection of A2 and B2 | There is no projection of A2 and B2 nozzle. We would like to design A2 and B2 nozzle projection will be 3930mm. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 8-4 | T1301 | Nozzle detail (2/2) 698150131089 | D1 nozzle design | D1 nozzle type is changed, but the projection is not confirmed. We would like to proceed the nozzle design as projection 500mm from B2 nozzle C.L. and off centered 261mm. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 8-5 | T1301 | General assembly (1/2) 698150131083 | Distributor size | The oblong holes and the length is under hold. Please release the hold. | Copy handed over to Sungjin (수정된 size 접수함: 1/27 회의록에 추가 예정)
Open | 8-6 | T1301 | Nozzle detail (1/2) 698150131088 | Material and Length of 1" pipe for S1, S2 and S3 nozzle | The type of 1" pipe for S1, S2 and S3 nozzles is changed to threaded pipe, so the pipe length will be changed from 446.5mm to 490mm. The reducer and 1 1/2" pipe will be changed to removable internal, so the material will be changed form C.S to 304L S.S. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 8-7 | D1101 | Manhole detial | The orientation of internal rung | The orientation of internal rung is under hold. We will locate the internal rung based on M manhole orientation. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
END OF DOCUMENT

## 1st 추가 (2) (hidden)
TECHNICAL CLARIFICATION SHEET for 1st priority
▶Project : Iran LNG - Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0003 | 09.Feb.2011
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Lurgi's Response
[5 empty] | TC-1 |  | Confirmation during meeting
Open | 1-1 | D-1101 | page.7 Comment for Calculation rev.1 | Bottom Skirt Length: 4800 -> 3458 | The skirt length in PV-elite shall include the basering thickness because of the distance from base elevation to bottom T.L. Therefore, we changed the bottom skirt length from 3458mm to 3500mm. |  | OK
Open | 1-2 | D-1101 | page.7 Comment for Calculation rev.1 | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 1-3 | D-1101 | Comment for General assembly rev.1 | To change of off-centered distance of nozzle: V(4") nozzle : C.L.+1200 P(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2")(C.L.+1100) and B(46") The Centerline Dist. is 375.36 while the sum of the ins. Radii is 559.60. - V(4")(C.L.+1200) and B(46") The Centerline Dist. is 411.43 while the sum of the ins. Radii is 580.25. To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V nozzle shall be over C.L.+2000. Please confirm whether the nozzle locations will be changed or keep the locations. |  | TO BE INFORMED
Open | 1-4 | D-1101 | Comment for Manhole detail rev.1 | To avoid any changes of cracking/shearing, weld overlay on face of the flange shall be done by providing an under cut in the flange thk. And thus increasing the flange overall thk. by approx.2mm. | We normally perform weld overlay on face of the flange with overlay thickness min.4.5mm and there is no change of cracking/shearking. The weld overlay detail shown on the revised drawing in rev.2 is enough to meet spec. requirement and avoid any change. Therefore, we will proceed the weld overlay of flange same as revised drawing in rev.2. |  | OK
Open | 1-5 | D-1101 | Comment for Manhole detail rev.1 | Please check the material "SA350-LF2 CL.1". If "class" is applicable in 'Div.2'. | According to Sec.VIII Div.2 2004 ED.+2006 ADD., the class of SA350-LF2 is not indicated and also in Sec.II Part.D table.2A. However, according to Sec.II Part.A SA350, SA350-LF2 is shall be indicate the class of material to purchase. SA350-LF2 class.1 and class.2 have same mechanical and chemical property and the impact test requirement is different. (Standard impact test temperature - Class.1: -46℃, Class.2 -18℃) Therefore, we will use class.1 of SA350-LF2 because MDMT is -30℃. |  | OK
Open | 1-6 | D-1101 | Comment for nozzle detail (2/3) rev.1 | Nozzle size 3" and below, weld overlay not required - S.S. SA350-LF2 CL.1+316 SS W.O. -> SA182-F316 | We will weld overlay for all nozzles except for liquid outlet nozzle C(3"). On the specification, there is no requirement that nozzles 3" and below shall be solid alloy nozzle. Therefore, we would like to perform the weld overlay for all nozzles except for C nozzle. If solid alloy nozzle shall be used by your requirement, the cost impact will occur. |  | OK
| Attachments: |  |  | N/A
TC-2
Open | 2-1 | ALL ITEMS | Comment for G/A drawing | Design of internal and detail drawings including supports. | We will submit the calculation and detail drawing later.
Open | 2-2 | ALL ITEMS | Comment for Body drawing | Vendor to confirm the orientation of all L/S seams in next revision. | The weld seam orientation can be fixed after receiving the orientation of nozzles. Please inform us the orientation of nozzle.
Open | 2-3 | ALL ITEMS |  | Vendor to ensure that welding of nozzles should not clash with any L/seam and C/seam of shell and D/end (submit development drawing) | We will try to avoid the clash of nozzle and weld seam, but we will inform you if there is no method in our side. For clash of L/seam, we can check after receiving the nozzle orientation. After receiving the orientation, we will submit the development drawing.
Open | 2-4 | ALL ITEMS |  | Weld size of washer in anchor chair | There is no standard of size of washer. We assume the weld size as 6mm. Please confirm. |  | 8mm
Open | 2-5 | ALL ITEMS |  | Weld size of Lifting, tailing or Trunnion lug | The weld size is verified by calculation, but your comment is too bigger than the calculation. Therefore, we would like to set the weld size of lifting, tailing or trunnion lug according to calculation. |  | As per comment
Open | 2-6 | ALL ITEMS |  | TRUNNION Provide two nos. cross stiffeners. | According to calculation, the trunnion is satisfactory without the stiffener. Therefore, we would like to leave the design of trunnion as is. If you have a standard of trunnion based on your comment, please send. |  | Required
Open | 2-7 | ALL ITEMS |  | REINFORCEMENT OF SKIRT OPENING Provide pad and Calculate the skirt considering opening | All skirt opening except skirt vent are provided the reinforcement pad. The area of reinf. pad and sleeve pipe is larger than opening area, so we think that the calculation of skirt opening is not needed. Therefore, we would like to except the calculation for skirt opening. |  | OK
Open | 2-8 | ALL ITEMS |  | HEIGHT OF MONKEY LADDER To change the spacing between ladder rung as 300 | If the spacing between ladder rung as 300, the vertical heights of each items are different because of angle of ladder. The different vertical height of ladder rung make user inconvenience, so, we will keep the vertical height between ladder rung as 300mm. |  | As per comment
Open | 2-9 | ALL ITEMS | Comment for Nozzle drawing | Flange face thickness for 600# flange | Flange face thickness is 7mm according to B16.5 2003ED and 6.4mm according to B16.47 1996ED. We will consider flange face thickness as 7mm because it can acceptable for tolerance.
Open | 2-10 | ALL ITEMS | Comment for Calculation -Fireproofing | Model the skirt by consider fire proofing of 50 thk on both sides of skirt (Inside 50 thk & outsize 50 thk) | We perform the modeling of the fire proofing as 100mm(inside 50mm&outside 50mm) on outside by insulation in PV-elite. It is because insulation and fireproofing have to be different from lining. Therefore, we would like to put the fireproofing as 100mm on outside only for calculation because it is more severe design condition. |  | OK
Open | 2-11 | ALL ITEMS | Comment for Calculation -Nozzle Orientation | Nozzle orientation = 0 deg. | We assumed the nozzle orientation and incorporated in calculation. After receiving the orientation, we will revise the calculation. The change of nozzle orientation is no meaning, so we will leave the orientation as is at this stage.
| Attachments: |  |  | N/A
TC-3
Open | 3-1 | T-1201 | Comment for G/A drawing | DEMISTER Arrangement of demister is not correct. Please show demister arrangement as shown in Lurgi MDS rev.00. Also Provide detail and design of demister support beam(If required) | On MDS, the size of demister is under hold. Please confirm the size of demister. We will submit the detail drawing later. |  | By internal vendor
Open | 3-2 |  |  | TOP DAVIT 2500kg(Hold). Provide detail | The capacity is under hold. Please release the hold. The capacity as 2500kg is not mentioned on spec. S-00-1351-001 attachment-20, so please confirm the size of L and S mentioned on the spec. After receiving the size, we will calculate the top davit based on standard drawing. |  | To be informed
Open | 3-3 |  |  | ANCHOR BOTL ORIENTATION Please remove this detail. It is already covered in body detail. | We would like to leave the anchor bolt orientation on G/A drawing to indicate the anchor bolt size and quantity on G/A drawing. The other duplicated details are removed on the G/A drawing. |  | OK
Open | 3-4 |  | Comment for G/A drawing attached on calculation | TOLERANCE Sungjin to indicate general tolerance on dimension, Projection of nozzles, Location of nozzles, overall tolerance, verticality etc. as per Tolerance standard. | For tolerance, the note is indicated on general note as " vessel fabrication tolerances shall be in accordance with ASME code & ATTACHMENT-1 on 69815-01-06035 REV. 01. We think that the indication of tolerance on the drawing duplicately is not needed, so we would like to not indicate the tolerance on the drawing. |  | OK
Open | 3-5 |  |  | PLATFORM/LADDER DETAIL Sungjin to refer attached revised platform / ladder details on equipments. | We cannot find the platform / ladder detail. Please inform us. |  | OK
Open | 3-6 |  |  | NOZZLE ELEVATION Nozzle elevation for all process nozzles to be confirmed by equipment vendor based on feed back from column internal vendor. | After design of internal by internal vendor, we will inform if there is a change of nozzle elevation by process requirement. |  | OK
Open | 3-7 |  | Comment for Body drawing attached on calculation | ANCHOR BOLT DETAIL Details of provided anchor bolt of M72(SA193 Gr.B7) as it is in sungjin scope of supply | We will indicate the detail of anchor bolt on the template drawing in next revision. |  | Not Applicable
Open | 3-8 | T-1201 | Comment for Manhole detail (1/2) | TAPPED HOLES 3-M24 tapped holes @ 120 deg. Apart: 60 deg, 180 deg, 300 deg when top of flange is 0 deg. | We will provide 3-M24 tapped holes @ 120 deg. Apart: 0 deg, 120 deg, 240 deg when top of flange is 0 deg. Please confirm. |  | OK
Open | 3-9 |  | Comment for Nozzle detail (3/4) | INTERNAL PIPE OF A2 Also show internal plate flange pipe with elbow in dotted lines, thought it is in scope of column internal vendor | All internals by column internal vendor will be supplied by Sungjin. The detail of internal pipe of A2 nozzle will be indicated on separated drawing, so we will mention the drawing no. of internal pipe of A2 on nozzle drawing. |  | OK
Open | 3-10 |  | Comment for Nozzle detail (4/4) | VORTEX BREAKER Kindly note that this I s perforated plate vortex breaker. Vendor to ensure that free area perforated plate >> nozzle area. Therefore, vendor is requested provide details of perforated area considered. | We designed the hole size as 25 dia - 362 EA as shown on the drawing. The free area is 1776.96cm^2 and nozzle area is 1720.21cm^2, so the free area of perforated plate is larger than nozzle area. Please confirm the size and quantity of holes on perforated plate. |  | To be informed
Open | 3-11 |  | Comment for Calculation - inserted page | WEIGHT OF INTERNAL Consider weight of internals after getting confirmation form column internal vendor as column internals are in sungjin scope | The current calculation consider assumed weight of internal. After design of internal, we will incorporate the weight of internal in the calculation. |  | OK
Open | 3-12 |  | Comment for Calculation - inserted page | ANCHOR BOLT Sungjin to provide detail drawings and design of anchor bolt including length | According to e-mail on 30.Apr.2010, Lurgi mentioned that Lurgi can provide the details provide the vendor assures following the same as it is for SA193 Gr B7 anchor bolts. We request detail of anchor bolt by e-mail on 18.May.2010, but we did not received the detail. After receiving the detail of anchor bolt, we will submit the calculation of anchor bolt. |  | Not Applicable
Open | 3-13 | T-1301 | Comment for G.A. drawing | GENERAL NOTE All removable internals shall pass through manhole I.D. except nozzle(A1), as internal pipe of nozzle(A1) is 36". So, shall be placed before the closing seam. | This note is not applied to this item. Please confirm. |  | OK
Open | 3-14 | T-1301 | Comment for Body drawing | Lifting Trunnion, not required.(Refer design calculation pg.20) Please provide lifting lug. | We will be revise in next revision. |  | OK
Open | 3-15 | T-1301 | Comment for Manhole drawing | To mark "shell" under R2235 | The inside diameter without the note is shell inside diameter, the inside diameter is shell I.D. If the nozzle locate on head, the note "2:1 ELL. HEAD" or "HEMI. HEAD" is indicate. Therefore, we do not indicate the note "SHELL". |  | OK
Open | 3-16 | D-1201 D-1202 | Comment for G.A. drawing | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-17 | D-1201 D-1202 | Comment for G.A. drawing | MATERIAL OF GASKET SS316 SPWG FILLED WITH SS316 INNER RING & CS OUTER RING | The material of gasket is mentioned on general note 8 on G.A. drawing (2/2). |  | OK
Open | 3-18 | D-1201 D-1202 | Comment for Nozzle detail (2/3) | To change of off-centered distance of nozzle: V1(4") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1100 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") The Centerline Dist. is 371.11 while the sum of the ins. Radii is 462.60 - V1(3") and B1(36") The Centerline Dist. is 405.81 while the sum of the ins. Radii is 469.65 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1500. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-19 | D-1301 | Comment for G.A. drawing (1/2) | To change of off-centered distance of nozzle: V1(2") nozzle : C.L.+1200 P1(2") nozzle : C.L.+1200 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - P1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 - V1(2") and B1(36") . The Centerline Dist. is 405.94 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1700. Please confirm whether the nozzle locations will be changed or keep the locations. |  | To be informed
Open | 3-20 | D-1301 | Comment for G.A. drawing (1/2) | TOLERANCE Tolerance on instrument pair nozzle shall be ±1. | According to spec., the tolerance of the distance between nozzles for level instruments is ±2. Please confirm whether ±1 tolerance is special requirement. |  | As per comment
Open | 3-21 | D-1301 | Comment for G.A. drawing (1/2) | INLET PIPE OF A1 Delete inlet pipe, it will replace with schoepentoeter (By others) | Please confirm whether the support of schoepentoeter is required. If required, please inform us. |  | By internal vendor(Sulzer)
Open | 3-22 | D-1301 | Comment for G.A. drawing (2/2) | ORIENTATION Please show all nozzles with impingement baffle as applicable. | On the orientation, one LT nozzle between 1 set of LT nozzle have impingement baffle. So, it may make a confusion for applied nozzle of baffle. We will indicate baffle elevation and detail of nozzle which have the baffle. |  | OK
Open | 3-23 | D-1311 | Comment for Body drawing | ANCHOR BOLT HOLE SIZE 5mm between straight part of hole | The comment is different from MDS. Please confirm.
Open | 3-24 | D-1401 | Comment for G.A drawing | To change of off-centered distance of nozzle: K1(2") nozzle : C.L.+1000 | The centerline distances for below nozzles are less then the sum of inside radius mentioned on ASME Sec.VIII Div.2 AD-501(a)(3), as below: - K1(2") and M(36") . The Centerline Dist. is 342.86 while the sum of the ins. Radii is 458.60 To meet the requirement of ASME code and avoid the interference, the off-centered distance of P1 and V1 nozzle shall be over C.L.+1480. Please confirm whether the nozzle locations will be changed or keep the locations. |  | OK
Open | 3-25 | D-1401 | Supplementary Comment for G.A drawing | K2 NOZZLE To change K2 nozzle size to 18" | Opening of K2 nozzle is welded to straight flange part of shell. Please confirm the detail of K2 nozzle. |  | To be informed
Open | 3-26 | T1901 | Comment for Body drawing | SHELL THICKNESS Vendor has considered 18mm thickness in design calculation. Vendor is requested to check and confirm the thickness of shell based on WRC107 analysis of nozzle A1 | We calculate the nozzle A1 by design pressure, the nozzle thickness and shell and nozzle thickness are changed to same as MDS(t16). |  | OK
Open | 3-27 | D1901 D1902 | Comment for G.A. drawing | RECTANGULAR TUBES Show rectangular tubes tentatively | The rectangular tubes are indicated on section "Z-Z". We think that it is enough to express the rectangular tube. |  | OK
Open | 3-28 | D1901 D1902 | Comment for Body drawing | ANCHOR BOLT SLOT HOLE Straight section: 40mm | According to standard drawing attach.35, the straight section will be 60mm because the max. temp. difference is over 280℃.(Ope. Temp. 317℃ - AMB. Temp.(About 20℃)). Please confirm. |  | OK, but D1902 is 40mm
| Attachments: |  |  | N/A
TC-4
Closed | 4-1 | D1904 | Strength calculation | Calculation concept | We would like to inform you the concept of calculation as following: 1. Design pressure/temperature of shell - Int.: 4 bar+1.033 bar at 350 deg - Ext.: 8.5 bar at 195 deg - Ext.: Shop&Filed hydrotest pressure at AMB. 2. Nozzle - Only internal pressure will effect on The nozzles and body flange. - Only the opened area of jacket will be applied as a reinforcement area. In this area, the external C.A. is 0 and internal C.A. is 3. Please refer to the submitted calculation. | F.V (1.033 bar) is not applicable for shell & is applicable to jacket only. Ok, noted
Closed | 4-2 | D1904 | G.A. and jacket detail drawing | Jacket closure | According to MDS, the jacket closure is type (c) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. In this case, for nozzle, the shape of jacket closure is a shape transforming the cone and it cannot be made by rolling of plate. So, it is very difficult to forming plate and the installation also. Therefore, we would like to change the shape of jacket closure type (d-1) of Fig. 9-5, Appendix.9, ASME Sec.VIII Div.1. | If vendor feels problem in fabrication and installation. So, he may opt for closure type (d-1) of Fig.9-5, provided all the requirements as per Appendix. 9 of ASME Sec. VIII Div.1 are met with.
Closed | 4-3 | D1904 | G.A. and jacket detail drawing | Stiff. ring of jacket | According to MDS, there are two stiff. ring for jacket. We think that the space to locate the shipping saddle is not enough and the vessel is small, so we deleted the stiff. Ring and increase the jacket thickness from min. 10mm to 12mm. Please confirm. | Ok, Noted
Closed | 4-2 | D1904 | G.A. and body detail drawing | Lifting lug at top head | According to MDS, the lifting lug at top head is welded on inside head. However, the weight of top part is about 2.2 tons, and the covering of jacket head which cut off the area for lifting lug is difficult. Therefore, we would like to weld the lifting lug at jacket head. | If suppose lifting lug is welded to jacket, then there may have the chances that jacket to jacket or jacket to shell weld can come in shear stress. So, it is advisable to weld lifitng lug on shell & sungjin can increase the opening in jacket (for lifting lug) suitably.
Attachments:
TC-5
Open | 5-1 | D1101 | G.A. drawing | Nozzle orientation | When we submit the drawings, we did not received the nozzle orientation. There are many change on the drawing, so we submit the drawings without change of nozzle orientation and L-seam orientation. In the next revision, we will incorporate the nozzle and L-seam orientation on the drawing. If you require, we will resubmit the drawing indicated orientation in same revision to replace the drawing.
Open | 5-2 | D1101 | Manhole and Nozzle detail drawings | Hub height | We revise all drawing and calculation for hub height based on nozzle projection.
Open | 5-3 | D1101 | Manhole detail drawing | Elevation of top ladder rung | On the commented drawing, the top ladder rung is located under 900mm from bottom of demister. But, according to standard drawing(attachment-2 of pressure vessel spec.), the top ladder rung shall be located under 805mm from bottom of demister as shown on the drawing. Please confirm.
Open | 5-4 | D1101 | Nozzle detail drawing | Material of small size nozzes except for C nozzle | On the drawing in rev.2, the material of small size nozzles(2"&3") except for C nozzle is SA182-F316. As discussed during meeting in India, all nozzles except for C nozzles will be SA350-LF2-CL1 + 316L W.O.
Open | 5-5 | D1101 | Nozzle detail drawing | Reinf. pad of skirt opening | As discussed during meeting in India, the reinf. pads of skirt opening for C nozzle and skirt access are deleted. (All reinf. pads of skirt opening for all drum will be deleted.)
Open | 5-6 | D1101 D1201 D1202 D1301 | Internal ass'y & detail drawing | Type of demister | On the MDS, the type of demister is TYPE "V-b". However, the demister of Type V is for equipment which manhole is located on the top head. It means that the demister cannot remove after installation because demister fixed by bolting and the nut on lower side is tack welded and the manhole in located under demister. We think that "TYPE II-A-b" is suitable for these equipments, we applied on the drawing. Please confirm.
Open | 5-7 | D1101 D1201 D1202 D1301 | Internal drawings and calculation | Revision of drawing and calculation | The drawing and calculation is first submission, but the revision number is "1". It is because internal vendor submit all drawings in rev.0 to us before receiving Lurgi's datasheet but there are some revision because of change of MDS. So, internal vendor issued all documents in rev.1. We would like to leave the revision number as "1" considering document control of internal vendor. Please confirm.
Attachments:
TC-6
Open | 6-1 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Reference elevation | According to Lurgi standard for platform, the reference elevation is TOS. So. we designed the platform for all items based on TOS elevation. However, on the nozzle orientation for 1/2T-1201, the elevation is based on TOG. Please confirm the basis of reference elevation.
Open | 6-2 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Hillside location of W1 nozzle | On the nozzle orientation, the hillside location of W1 nozzle is 1820mm. In this case, the welding of HB-01 seam and W1 nozzle are overlapped. Therefore, we would like to leave the hillside location of W1 as 1600mm same as latest drawing.
Open | 6-3 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | Difference from standard drawing for ladder | On the nozzle orientation, there are some difference from standard drawing for ladder. Please find the example as below: 1. On the plan from el.130000 to el.133000, the distance between center of ladder at 5° and platform at right side is 400mm. However, according to standard details 69815-01-29108, the distance is 380mm. 2. On the plan from EL.130000 to EL.133000, the distance between ladder rung from vessel center is 2950mm. However, according to standard details 69815-01-29108, the distance is 3030mm(vessel O.D./2 (2740mm) + insul. th'k (30mm) + 260mm). Therefore, we would like to follow the standard drawing if the standard drawing and platform information are different.
Open | 6-4 | T1201 | Nozzle orientation 69815-01-28292 rev.0 | A01 orientation | On the plan from EL.100000 to EL.106500, there are two access opening as A02. Please confirm.
Open | 6-5 | T1201 | Nozzle orientation 69815-01-28297 rev.0 | L3A/B, L4A/B orientation | L3A/B, L4A/B orientation is not mentioned on nozzle orientation drawing. Please confirm.
Open | 6-6 | T1301 | Nozzle orientation 69815-01-27530 rev.0 | The location of D1 nozzle on B2 nozzle | On the latest drawing, D1 nozzle is located bottom of neck pipe of B2 nozzle. However, on the nozzle orientation, the D1 nozzle looks like using elbow. If it is correct, D1 nozzle shall be changed from long welding neck flange to welding neck flange + elbow + pipe. Please confirm.
Open | 6-7 | D1301 | Nozzle orientation 69815-01-27522 rev.0 | The top platform elevation | On the nozzle orientation, the elevation of top platform is T.L+ 8170mm. In this case, the bracket of top platform is interfered with top head. Therefore, we would like to increase the elevation of top platform from T.L+8170mm to T.L+8520mm.
Open | 6-8 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Off-centered dimention of S1&S2 nozzle | As per nozzle orientation, off-centered dimention of S1&S2 nozzle is 1900mm, but the nozzles are interfered with circ. seam of head as mentioned on meeting in India. The location of S1&S2 nozzle have been confirmed by comments received on 7.7.2010, so the location of S1&S2 nozzle will be following the comments as 1950mm from center line. Please confirm.
Open | 6-9 | D1311 | Nozzle orientation 69815-01-27525 rev.0 | Projection of L3B&L8B nozzle | As per nozzle orientation, the projection of L3B&L8B nozzle is 3720mm. In this case, the beveled transition of forged neck is located under surface of vessel. Therefore, we increased nozzle projection from 3720mm to 3800mm same as last revision. Please confirm.
Open | 6-10 | D1401 | Nozzle orientation 69815-01-28151 rev.0 | Off-centered dimention of K1 nozzle | As per nozzle orientation, off-centered dimention of K1 nozzle is 990mm, but the nozzles are too closed with M manhole under ASME code as mentioned on meeting in India. The location of K1 nozzle have been confirmed by comments received on 19.7.2010, so the location of K1 nozzle will be following the comments as 1480mm from center line. Please confirm.
Attachments:
TC-7
Open | 7-1 | T1201 D1201 D1202 D1301 | - | Material of external bolt/nut under sour service | According to MDS, the material of external bolt/nut is SA193-B7/SA194-2H. Also, as per NACE MR 0103, the bolt/nut material exposed to sour environments shall be used SA193-B7M/SA194-2HM. We think that the external bolt/nuts are not contacted with sour contents, so it is not required to apply NACE MR 0103. Please confirm.
Open | 7-2 | T1301 | Body detail(1/2) 698150131085 | The material of Y-ring | According to comment, the material of Y-ring shall be SA266-2 instead of SA105N. There was a mistake for purchacing of material, so the Y-ring material was according to SA105 instead of SA266-2. Even though, the material is over the limitation of SA105, but we think that the most important factor of material is mechanical property and the mechanical property of SA105 is same between SA105 and SA266-2. We calculated the y-ring by FEA and the result was satisfactory. The material was verified by simulation test as attached mill certification. Now, we had purchased the forging material and welded into the shell. Therefore, we would like to use the forging material in SA105.
Open | 7-3 | T1301 | Body detail(2/2) 698150131086 | Trunnion lug | According to comment, the trunnion lug is not required and is changed to lifting lug as discussed during meeting. However, we had purchased the material for trunnion lugs, so we would like to use the trunnion lugs.
Open | 7-4 | T1301 | Nozzle detail (1/2) 698150131088 | Raised face for filler flange | According to comment, the thickness of raised face for filler flange shall be 6.35mm. 7mm thickness of raised face is based on B16.47 2003 edition. The flange is non-standard flange, thickness of raised face is not effect on the strength calculation and we check the flange thickness(191mm) by calculation and there is no problem for flange. Also, the difference is very small as 0.65mm, so we would like to use the rased face for filler flange as 7mm.
Open | 7-5 | D1301 | Nozzle detail (3/3) 698150131069 | The reinf. pad for access opening | According to comment, the reinf. pad for access opening shall be full penetration welding. However, as discussed during meeting, the reinf. pad will be deleted for drums. For information, the skirt and opening will be full penetration welding.
Open | 7-6 | D1401 | Nozzle detail (4/4) 698150131099 | The material of skirt vent | According to comment, the material of skirt vent shall be SA106-B as in earlier revision. However, the skirt vent is welded to non-pressure part, so we think that it is not required to use SA106-B. Therefore, we would like to change the material of skirt vent from SA106-B to SA53-B.
Open | 7-7 | ALL ITEMS | - | Location of monkey ladders | The location of monkey ladders are commented, but all monkey ladders are interfered with the skirt bracing beam. In current design, the orientation of monkey ladder shall be in same or +/- 10 deg of lifting trunnion/lugs.
END OF DOCUMENT
TC-8
Open | 8-1 | D1311 | General assembly (1/2) 698150131072 | Location of L9A/B & L10A/B nozzle | You commented to rearrange the seam(B-02). However, there is no piece of shell to avoid the interference. Therefore, we would like to locate L9A/B at T.L.+1425mm and L10A/B at T.L.+1675mm and leave the actual distance between weld edges.
Open | 8-2 | D1311 | General assembly (1/2) 698150131072 | Hillside nozzle projection in shell side | All nozzles projection in hill side located in shell is changed from 3750mm to 3780mm. The flange, pipe and forged neck have been welded based on the projection 3750mm. We would like to keep the projection in hill side located in shell as 3750mm.
Open | 8-3 | D1311 | General assembly (1/2) 698150131072 | Projection of A2 and B2 | There is no projection of A2 and B2 nozzle. We would like to design A2 and B2 nozzle projection will be 3930mm.
Open | 8-4 | T1301 | Nozzle detail (2/2) 698150131089 | D1 nozzle design | D1 nozzle type is changed, but the projection is not confirmed. We would like to proceed the nozzle design as projection 500mm from B2 nozzle C.L. and off centered 261mm.
Open | 8-5 | T1301 | General assembly (1/2) 698150131083 | Distributor size | The oblong holes and the length is under hold. Please release the hold.
Open | 8-6 | T1301 | Nozzle detail (1/2) 698150131088 | Material and Length of 1" pipe for S1, S2 and S3 nozzle | The type of 1" pipe for S1, S2 and S3 nozzles is changed to threaded pipe, so the pipe length will be changed from 446.5mm to 490mm. The reducer and 1 1/2" pipe will be changed to removable internal, so the material will be changed form C.S to 304L S.S.
Open | 8-7 | D1101 | Manhole detial | The orientation of internal rung | The orientation of internal rung is under hold. We will locate the internal rung based on M manhole orientation.
TC-9
Open | 9-1 | T1201 T1301 D1101 D1301 | General assembly (1/2) | Earthing lug orientation | The earthing lugs orientation is not mentioned on orientation information and comment. We would like to weld of earthing lugs at orientation 0 deg & 180 deg for item T1201, T1301, D1101, D1301. | OK
Open | 9-2 | T1301 | Interference list | Elevation of skirt vent | During Lurgi meeting, we discussed the interference of skirt vent of T1301 and confirmed to reduce the distance between weld edges. However, we expect the skirt vent may be interfered with B-06 because of fabrication tolerance. Therefore, we would like to change the elevation of skirt vent for T1301 from TL-1600 to TL-985 according to standard drawing. | OK
END OF DOCUMENT
TC-10
Open | 10-1 | T1201 | Technical clarification sheet 6-5 | L3A/B, L4A/B orientation | We received the orientation for L3A/B and L4A/B during Lurgi meeting as 60 deg and 135 deg. We checked the interference for these nozzles and there are some interference as below: 1. L4B at 135 deg is interfered with S1 nozzle at 135 deg => We would like to change the orientation of S1 nozzle from 135 deg to 145 deg. 2. L3B at 60 deg is interfered with #2 platform frame ring (T.O.G.: T.L.+900) => we would like to change the orientation of L3A/B nozzle from 60 deg to 115 deg. Please refer to the development drawing (attachment#1) and confirm. | According to New orientation
END OF DOCUMENT

## 2nd (hidden)
Additional Outstanding
▶Project : Iran LNG - Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0009 | 26.Jan.2011
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Lurgi's Response
TC-1
Open | 1-1 | D-1901 D-1902 D-1911 | MDS | Free area of perforated plate | According to MDS, the free area is 35% and the slot hold size is 40x10mm. However, to keep free area as 35%, the slot hole size shall be 45x10mm. Please confirm. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 1-2 | D-1901 D-1902 D-1911 | MDS | The grating support in head side | According to MDS, the gusset plate of grating support clip in head side is interfered with perforated plate. We would like to locate the gusset plate under of base plate of bracket. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 1-3 | D-1901 D-1902 D-1911 | MDS | The location of support beam of grating | According to MDS, there are the dimention of support beam, but the bracket and support beam is interfered. Therefore, we would like to change the location of support beam from 875 from T.L. and 1800mm pitch to 1100mm from T.L. and 180mm pitch. Also, we would like to select the beam location based on strength calculation. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 1-4 | D-1901 D-1902 | MDS | The area of refractory | The area of refractory is not clear. We would like to confirm the refractory height as 2100mm(650mm+ 1000mm). | To be confirmed by process eng'g. (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 1-5 | T1911 | MDS | The length of shell section | According to MDS, there is some interference between reinf pad of A1 nozzle and stiff. Ring and C-seam. So, we increase the length of shell in t16 and rearrange the elevation of stiff. ring shown on the general aseembly in rev.2. | OK, Acceptable (Meeting시 협의한 사항: 1/27 회의록에 추가 예정)
Open | 1-6 | T2001 T2002 | General assembly (1/2) | The size of wire mesh | According to comment, the wire mesh is 20mesh(upper)+4mesh(lower) with dia.0.4. However, the internal vendor cannot purchase the wire mesh in Korea mentioned on commnet, we would like to change the size of the wire mesh to 20mesh(upper) with dia.0.4 + 4mesh(lower) with dia.0.8. | To be confirmed by process eng'g (HMT와 가능여부 재협의 예정)
| Attachments: |  |  | N/A

## 2nd (2) (hidden)
TECHNICAL CLARIFICATION SHEET for 2nd priority
▶Project : Iran LNG - Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0009 | 9.Feb.2011
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Lurgi's Response
TC-1
Open | 1-1 | D-1901 D-1902 D-1911 | MDS | Free area of perforated plate | According to MDS, the free area is 35% and the slot hold size is 40x10mm. However, to keep free area as 35%, the slot hole size shall be 45x10mm. Please confirm.
Open | 1-2 | D-1901 D-1902 D-1911 | MDS | The grating support in head side | According to MDS, the gusset plate of grating support clip in head side is interfered with perforated plate. We would like to locate the gusset plate under of base plate of bracket.
Open | 1-3 | D-1901 D-1902 D-1911 | MDS | The location of support beam of grating | According to MDS, there are the dimension of support beam, but the bracket and support beam is interfered. Therefore, we would like to change the location of support beam from 875 from T.L. and 1800mm pitch to 1100mm from T.L. and 180mm pitch. Also, we would like to select the beam location based on strength calculation.
Open | 1-4 | D-1901 D-1902 | MDS | The area of refractory | The area of refractory is not clear. We would like to confirm the refractory height as 2100mm(650mm+ 1000mm).
Open | 1-5 | T1911 | MDS | The length of shell section | According to MDS, there is some interference between reinf pad of A1 nozzle and stiff. Ring and C-seam. So, we increase the length of shell in t16 and rearrange the elevation of stiff. ring shown on the general assembly in rev.2.
Open | 1-6 | T2001 T2002 | General assembly (1/2) | The size of wire mesh | According to comment, the wire mesh is 20mesh(upper)+4mesh(lower) with dia.0.4. However, the internal vendor cannot purchase the wire mesh in Korea mentioned on comment, we would like to change the size of the wire mesh to 20mesh(upper) with dia.0.4 + 4mesh(lower) with dia.0.8.
TC-2
Open | 2-1 | D-1901 D-1902 D-1911 | General assembly (1/2) | Size of rectangular tube | According to comment of G.A. drawing on D-1901 received during Lurgi meeting, the rectangular tube size is 75 x 25 x 5 th'k. However, according to calculation, the rectangular tube shall be 120 x 35 x 5 th'k. We would like to increase the size of rectangular tube as 120 x 35 x 5 th'k. according to calculation. For information, the rectangular tube size on the submitted drawing is 85 x 35 x 5 th'k. We rechecked the size and the rectangular tube shall be increased to 120 x 35 x 5 th'k. According to increase of tube size, the location of support beam will be moved down as 35mm and the area of refractory will be increased according to confirmation during Lurgi meeting. | OK
Open | 2-2 | T-1901 D-1904 | General assembly (1/2) | Earthing lug orientation | The earthing lugs orientation is not mentioned on orientation information and comment. We would like to weld of earthing lugs at orientation 0 deg & 180 deg for item T-1911 and D-1904. | OK
END OF DOCUMENT

## TCL (Empty))
CONTRACTOR : |  |  |  | 300 KT POLYETHYLENE PLANT ARYA SASOL POLYMER COMPANY (ASPC) |  |  |  |  | OWNER:
|  |  |  | Technical Clarification Sheet |  |  |  |  | MC:
P.O. Number : |  | PO-PC2312-08 |  | Technical Clarification Reference No.: |  |  | Vendor Abbreviation: | Clarification Date: | Purchaser Response Date:
Doc. NO.: |  |  |  | Transmittal Number : |  |  |  |  | 2024.07.26 (DY) 2024.08.04 (Sazeh)
Item | Status | Tag No. | Reference Document |  | Subject / Comment | Clarification sought by Vendor |  |  | Purchaser Response
1 | [5 empty] | Agreed, Updated
2 | [5 empty] | Agreed, updated as far as possible with the current information
3 | [5 empty] | True, no controller in the LPS. Therefore UPS removed.
4
5
6
7
8
9
10
11
12
13
14

## ATT (hidden)
S/No. | Item no. | Description | Q'ty | Revision No.
|  |  |  | G.A. drawing | MDS | PDS
1 | 1T-1202 & 2T-1202 | Regenerator | 2 | 3 | 0 | 2
2 | 1T-1203 & 2T-1203 | HP Flash Column | 2 | 3 | 1 | 3
3 | 1T-1311 & 2T-1311 | Absorber | 2 | 3 | 1 | 3
4 | 1T-1312 & 2T-1312 | Regenerator | 2 | 3 | 1 | 4
5 | 1T-1912 & 2T-1912 | LTGT - Absorber | 2 | 2 | 1 | 3
6 | 1T-1913 & 2T-1913 | AGE - Absorber | 2 | 2 | 0 | 2
7 | 1T-1914 & 2T-1914 | Regenerator | 2 | 2 | 2 | 3
[7 empty] | S/No. | Item no. | Description | Q'ty
[7 empty] | 1 | 1T-1202 & 2T-1202 | Regenerator | 2
[7 empty] | 2 | 1T-1203 & 2T-1203 | HP Flash Column | 2
[7 empty] | 3 | 1T-1311 & 2T-1311 | Absorber | 2
[7 empty] | 4 | 1T-1312 & 2T-1312 | Regenerator | 2
[7 empty] | 5 | 1T-1912 & 2T-1912 | LTGT - Absorber | 2
[7 empty] | 6 | 1T-1913 & 2T-1913 | AGE - Absorber | 2
[7 empty] | 7 | 1T-1914 & 2T-1914 | Regenerator | 2

## WY_TC (2) (hidden)
TECHNICAL CLARIFICATION SHEET for Gas sweetening area column group I (Wooyang items)
▶Project : Gas Treating Project |  |  |  |  | ▶P.O. No.: ILC-P1B-P-00-1400-0020 | 2011-06-14
Status | Sr No | Item | Reference Document | Subject / Comment | Clarification sought by Sungjin | ILC/Nardis's Response
TC-1
Open | 1-1 | All items | TPS | Revision no. for general assembly drawing, MDS & PDS | * Total Q'ty: 7 items 14 sets Above table is based on TPS. Please confirm whether there is a change.
Open | 1-2 | All items | E-mail sent on 3.Jun.2011 (Att.#5-1) | Latest information | We received all submitted drawings and calculations by Wooyang and all commented drawings and calculations. However, we found some difference between information as below table: 1. General assembly drawings: Some drawings are different between drawings received with P.O. and drawings received by Nardis. 2. Calculations: Revised calculations which comments are reflected are submitted by Wooyang. Therefore, we would like to confirm the latest information as below: 1. For drawings, we will follow latest commented general assembly drawings received with P.O. only. Other drawings will be only for reference. 2. Please confirm whether there is a commented calculation for latest calculation submitted by Wooyang. For example, please confirm whether there is a commented calculation for VP-ILC-P1B-P-00-1351-004-111 in rev.5 for 1/2T-1203.
Open | 1-3 | All items | - | Design base | 1. The priority of information between G.A. drawing, MDS and PDS According to contract base, we will follow the commented drawings made by Wooyang and the comments will be reflected on the drawing. Therefore, we will design based on below priority - 1st priority: G.A. drawing and calculation by Wooyang - 2nd priority: TPS including MDS & PDS 2. We will design based on confirmation for items for 1st priority, 2nd priority and 1st priority change order by MOM, comments and so on from ILC, Nardis and Lurgi.
Open | 1-4 | All items | Att.#5-2 | Information schedule | * Requested date by Sungjin 1. Nozzle orientation: During KOM 2. Platform & Ladders: During KOM 3. Position & orientation of lifting / tailing lug, nameplate, grounding lug: During KOM 4. Pipe support clips: 30.Aug.2011 5. Top davit only for T-1914: During KOM 6. Orientation of monkey ladder: During KOM => If you have no opinion, we would like to select the orientation considering the interference between skirt bracing or others same as 1st&2nd priority items. We think that most of information have been made because these items have been started long times ago by Wooyang. To design the platform and ladder and check the interference quickly, we would like to receive the information during KOM.
Open | 1-5 | All items | - | Scope of supply | Except for anchor bolt, we will follow the scope of supply mentioned on TPS. The scope of supply of anchor bolt is Sungjin's scope based on contract.
Open | 1-6 | All items | - | Material | 1. The material will be same with the material list mentioned on G.A. drawing except for clad material for T1312. According to G.A. drawing for T1312, the clad material is SA516-70 + 304L S.S, but it is different from MDS(SA516-70 + 316L S.S) and other material of pressure part on G.A. drawing. We will design and procure the clad material as SA516-70 + 316L S.S. 2. The material which is not mentioned on G.A. drawing will be followed by MDS and same with 1st & 2nd priority items.
Open | 1-7 | T-1202 T-1311 T-1912 T-1913 T-1914 | Att.#5-3 | Internal scope and installation | 1. Internal scope and installation The internal listed in Attachment#5-3 is only for internals fabricated or designed by internal vendor. Please confirm the scope of internal. 2. Internal vendor and Change of internal type According to contract base, the internal vendor will be HMT.(Hanbal Masstech) But, the type of internals shall be changed as below: a) 3 Montz Thormann channel Tray -> 3 Bubble cap tray b) Sulzer Mellapak (M 250.X) -> HMT Packing (NSP 250 X) Please confirm the internal vendor and the change of internal type
Open | 1-8 | All items | - | Hold List | According to MDS, there are hold list for each items, but on the G.A. drawing is not indicated HOLD. So, we would like to clarify HOLD for each cases as below: 1. Holds related with internal (Elevation of nozzle, TL to TL height) The holds related with internal will be confirmed by internal vendor. After confirmation by internal vendor, we will proceed the design based on confirmation by internal vendor. 2. Holds for nozzles (Elevation, projection, size and quantity and so on) : According to G.A. drawing, the nozzles are not under HOLD. Therefore, we will ignore the hold for nozzles. 3. Holds for additional nozzle loads : There is not additional nozzle loads except for the nozzle loads mentioned on MDS. All nozzle will be checked according to spec.. 4. Holds for skirt height : According to G.A. drawing, the skirt elevation is not under HOLD. Therefore, we will ignore the hold for nozzles. Please confirm.
END OF DOCUMENT