## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | NDE procedure | N-278-VD-6019-GN-PRC-0016-01 (17735-15)
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 1 |  | Please check whether ferrite content check (from page 66 till 71) is applicable here or not. | This is not a project requirement there for pages are removed
2 | 7 | 1 |  | In the titel of document, MT is for lifting lugs and here for structural steel of skid. Vendor shall clarify this matter. | Structural welding code AWS D1.1 covers all structural steel a sub category of this code are lifting lugs, support plates, structural steel beams etc. There for its not needed to specify each component by sub name. Airpack will send NDE inspection drawings to ensure right components will be inspected
3 | 7 | 1 |  | Does it vendor's internal documents. | As section 2.1 describes those document numbers are sub vendor document numbers
4
5
6 | [8 empty] | Open
7
8