## Table 1
23249-01 | 0 | L03-RE037-PN-DIS-001 | Vendor Document Schedule | IFE
23249-01 | 1 | L03-RE037-PN-DIS-001 | Vendor Document Schedule | IFE
23249-03 | 0 | L03-RE037-PR-PID-001 | Piping & Instrument Diagram (P&ID) | IFE
23249-03 | 1 | L03-RE037-PR-PID-001 | Piping & Instrument Diagram (P&ID) | IFE
23249-04A | 0 | L03-RE037-ME-GAD-001 | General Arrangement Drawing (incl foundation load details) | IFE
23249-04A | 1 | L03-RE037-ME-GAD-001 | General Arrangement Drawing (incl foundation load details) | IFE
23249-04B | 0 | L03-RE037-ME-GAD-002 | 3D model | IFE
23249-05 | 0 | L03-RE037-EL-DIG-001 | Wiring Diagram (including Terminal Diagram) | IFE
23249-05 | 1 | L03-RE037-EL-DIG-001 | Wiring Diagram (including Terminal Diagram) | IFE
23249-06 | 0 | L03-RE037-EL-LST-002 | Instrument & I/O List | IFE
23249-06 | 1 | L03-RE037-EL-LST-002 | Instrument & I/O List | IFE
23249-07 | 0 | L03-RE037-EL-GAD-003 | Panel Layout Drawing | IFE
23249-07 | 1 | L03-RE037-EL-GAD-003 | Panel Layout Drawing | IFE
23249-08 | 0 | L03-RE037-QC-ITP-001 | Inspection & Test Plan (ITP) | IFE
23249-08 | 1 | L03-RE037-QC-ITP-001 | Inspection & Test Plan (ITP) | IFE
23249-09 | 0 | L03-RE037-QC-LST-001 | Utility Consumption | IFE
23249-09 | 1 | L03-RE037-QC-LST-001 | Utility Consumption | IFE
23249-10 | 0 | L03-RE037-ME-DSH-001 | Main Motor Data Sheets | IFE
23249-10 | 1 | L03-RE037-ME-DSH-001 | Main Motor Data Sheets | IFE
23249-11 | 0 | L03-RE037-ME-DSH-002 | Equipment Data Sheet | IFE
23249-11 | 1 | L03-RE037-ME-DSH-002 | Equipment Data Sheet | IFE
23249-12 | 0 | L03-RE037-IN-DSH-003 | Instrument Data Sheets | IFE
23249-12 | 1 | L03-RE037-IN-DSH-003 | Instrument Data Sheets | IFE
23249-13 | 0 | TBA | 2 Years Spare Part List | IFI
23249-14 | 0 | L03-RE037-QC-PCJ-001 | FAT Procedure | IFE
23249-14 | 1 | L03-RE037-QC-PCJ-001 | FAT Procedure | IFE
23249-15 | 0 | L03-RE037-QC-PCJ-002 | NDE Procedure | IFE
23249-15 | 1 | L03-RE037-QC-PCJ-002 | NDE Procedure | IFE
23249-16 | 0 | L03-RE037-QC-GAD-004 | Package Nameplate Drawing | IFE
23249-16 | 1 | L03-RE037-QC-GAD-004 | Package Nameplate Drawing | IFE
23249-17 | 0 | L03-RE037-QC-PCJ-003 | Hydrotest procedure | IFE
23249-17 | 1 | L03-RE037-QC-PCJ-003 | Hydrotest procedure | IFE
23249-18 | 0 | L03-RE037-QC-PCJ-004 | Painting Procedure | IFE
23249-18 | 1 | L03-RE037-QC-PCJ-004 | Painting Procedure | IFE
23249-19 | 0 | L03-RE037-ME-INX-001 | Index of Data Book | IFI
23249-19 | 1 | L03-RE037-ME-INX-001 | Index of Data Book | IFI
23249-20 | 0 | L03-RE037-ME-INX-002 | Index of Instruction and Operating Manual | IFI
23249-20 | 1 | L03-RE037-ME-INX-002 | Index of Instruction and Operating Manual | IFI
23249-21 | 0 | L03-RE037-IN-PHY-001 | Control Philosophy | IFE
23249-21 | 1 | L03-RE037-IN-PHY-001 | Control Philosophy | IFE
23249-22 | 0 | L03-RE037-QC-PCJ-005 | Preservation, Packing & Shipping Procedure | IFI
23249-23 | 0 | L03-RE037-EL-LST-003 | Modbus List | IFE
23249-23 | 1 | L03-RE037-EL-LST-003 | Modbus List | IFE
23249-25 | 0 | L03-RE037-QC-WBK-001 | PQR / WPS | IFE
23249-25 | 1 | L03-RE037-QC-WBK-001 | PQR / WPS | IFE
23249-26 | 0 | L03-RE037-QC-WBK-002 | WPQ | IFE
23249-26 | 1 | L03-RE037-QC-WBK-002 | WPQ | IFE
23249-27 | 0 | L03-RE037-IN-DSH-003 | Valve data sheet | IFE
23249-27 | 1 | L03-RE037-IN-DSH-003 | Valve data sheet | IFE
23249-28 | 0 | L03-RE037-IN-DSH-004 | PSV data sheet | IFE
23249-38 | 0 | TBA | Hook-up drawings | IFE
23249-39 | 0 | TBA | Cable List | IFE
23249-40 | 0 | TBA | HMI Pages | IFE