## TQ-299-TCL
Remarks: 1- This TQ sheet shall be exchanged between PPC and Bidders in a native file. 2- Each column and cell shall be filled out just by concerning party means Bidders and PPC. 3- A telephone conversation may be held to close outstanding issues after 2 times exchanging of comments and clarification. 4- Please care that all cell to be formatted in Wrap Text setting and do not try to change column width.
Consultant Company: |  |  |  | ABT 360 KT/Y PP PLANT |  |  |  |  | Owner:
Technical Clarification List
REQ No.: |  |  |  | TCL No.: |  |  |  |  | Project No. :
Vendor's Doc.No.: | [PROPOSAL REV.00] | Rev.: | 00 | Date of Issue: | 2023-MAR |  | Vendor: | AIRPACK |  | TAG No.: | Flare Gas Recovery Reciprocating Compressor
Item No. | Purchaser's 1st Comment/Query |  |  | Vendor's 1st Clarification/Reply |  | Purchaser's 2nd Comment/Query |  |  | Vendor's 2nd Clarification/Reply |  |  | Purchaser's 3rd Comment/Query | Vendor's 3rd Clarification/Reply | Purchaser's 4th Comment/Query | Vendor's 4th Clarification/Reply | Status
A. GENERAL
A.1 | Vendor shall review “Material Requisition for HIGH PRESSURE NITROGEN COMPRESSOR”, Doc#. L02-RE-MRQ-86-037-1 and submit either his confirmation or deviation from this document including, Design Code and Standard, Scope of Work and Scope of Supply tables, Technical Notes, referenced documents, List of Spare parts and etc. Moreover, all deviations on centrifugal compressors specification, data sheets, applicable code and standards and reference document clause 5 of MR, shall be stated in the bid. Otherwise purchaser assumes that Vendor proposal has full compliance with project document and no deviation or claim will be accepted after order. |  |  | Offer is based on the received project process datasheet and configuration of the previous supplied nitrogen compressor. |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Please note there is no material requisition received. For this reason could not be considered. During awarded stage if received this document can be followed.
A.2 | VENDOR is sole responsible to consider this clarification and modify his offer based on this TCL. All modifications which need to be considered on the next revision of offer based on this clarification should be clearly marked with revision and cloud marks. Bidder shall take full responsibility of all consequences due to changes without cloud marks. This clarification has priority over the offer. |  |  | Confirmed, agreed items in TCL will be reflected in our revised offer. |  | Noted |  |  | Closed
A.3 | Generally, if there are discrepancies between Project’s documents (e.g. DWGs, Specifications, datasheets, etc.) and Vendor's design, manufacturing, supplying and so on, it shall be raised by Vendor during Bid stage to make decision by Purchaser, otherwise it will not be acceptable after PO. If happen, more stringent condition, criteria, or safe operation shall be followed by Vendor with no cost and time impact |  |  | Document priority will be covered in the purchse order document in line with the contract of previous supplied nitrogen compressor package. |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | As per above MR is not yet received, for this reason previous reply is still valid.
A.4 | Vendor to note that cross check between Vendor technical documents is Vendor responsibility. In case of any discrepancies found, we consider the data in the strongest document as reference. Vendor to confirm |  |  | Confirmed |  | Noted |  |  | Closed
A.5 | Preliminary engineering, manufacturing and delivery time schedule shall be issued at this stage |  |  | Delivery lead time is provided in commercial offer. A detailed schedule will be provided after order. |  | Noted |  |  | Closed
A.6 | Vendor is responsible for the final selection of the materials for the specified service. Vendor to confirm. |  |  | Confirmed |  | Noted |  |  | Closed
A.7 | In addition to the comments in this TCL, there are some comments on the submitted proposal that should be implemented on revised offer. |  |  | Refer counter response on commented offer. |  | Noted |  |  | Closed
A.8 | Bidder is to submit his deviation /exception/ clarifications or shall confirm the compliance with all job specifications/data sheets/ and the applicable industrial codes and standards mentioned in Material Requisition. It shall be noted that Vendor's responsibility is fulfilling these requirements without exceptions and comments. No deviation other than the aforementioned ones will be accepted. If we don't receive any exception or deviation list, it means that vendor will fulfill our requirements. By the way, purchaser has no responsibility to find any inconformity between proposal and project requirements and deviation list shall be ended up with following expression: “There is no other deviation on MR and its attachments.” |  |  | Please refer item A.1 |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Refer to item A1
A.9 | P&ID for Process Gas system, Lube oil system, Buffer gas system (purge and vent), Machine monitoring, Cooling system and Capacity control system shall be submitted at bid stage. |  |  | Please find attached preliminary P&ID. Package configuration is in line with previous supplied nitrogen compressor package. |  | Please issue the documents separately and do not refer to the previous project |  |  | Please refer to P&ID for included items.
A.10 | The document priority shall be according to below. Vendor to confirm. 1. Purchase order 2. Purchase Agreements including clarification MOMs with attached signed TBA forms and technical clarifications in Email (by order of dates) 3. Latest revision of reference documents 4. Iranian laws & rules & international codes and standards Latest revision of Vendor technical proposal. |  |  | Confirmed |  | Noted |  |  | Closed
A.11 | Material certificate shall be provided as per blow STD: 1-Pressure Part" EN 10204 3.1 2-Non-Pressure Part: EN 10204 2.2 |  |  | Confirmed |  | Noted |  |  | Closed
A.12 | All electrical, instrument and mechanical items including Motors, Mechanical seals, couplings and etc shall be selected from project approved vendor list. Vendor to submit sub supplier list based on NPC AVL REV.08. |  |  | Subvendor list which is approved for previous supplied nitrogen compressor package will be followed. |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | As per above MR is not yet received, for this reason previous reply is still valid.
A.13 | Size and details of installation for foundation bolts shall be mentioned in GADs during detail design. Foundation bolts are in vendor’s scope. |  |  | Confirmed, skid anchor bolts will be included in revised offer. |  | Noted |  |  | Closed
A.14 | The proposal shall be in accordance with the instructions given of MR. Anyway, below documents, as min., shall be submitted with next revision of proposal implementing all requirement specified in this TCL: 1- General Arrangement Drawing (Incl. Off-Skid Systems) and List of sub-equipment and Connections 2- Filled in Data Sheet (Project format-API 618-5th ed.) 3- Filled Project data sheet 4- Mechanical seal data sheet or seal selection table ( by seal manufacturer) 5- Separate PIDs including battery limits for process gas, lube oil, MMS, seal gas 6- Quality Control Plan 7- Noise Data Sheet 8- Performance Curve 9- Driver and Power Consumer Data Sheet 10- Electrical Load List 11- Utility consumption list 12- Deviation List 13- Copy of Quality System Certificate (Certification for ISO 9001/2 or 3) 14- Reference List of Similar Units 15- Sub-Vendor List 16- Spare part lists 17- Special Tools List Signed and filled out Scope of works and supply in MR |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Please issue the documents separately and do not refer to the previous project |  |  | As per offer supplier data register.
A.15 | Vendor to confirm that equipment, electrical items and instrumentation are designed for outdoor installation. |  |  | Confirmed |  | Noted |  |  | Closed
A.16 | Project painting procedure shall be fully followed by vendor. |  |  | Will be based on approved painting procedure of previous supplied nitrogen compressor package. |  | Pllease follow our project painting specification and do not refer to the previous project |  |  | Document not received, for this reason previous reply is still valid.
A.17 | Motors shall be supplied as per project Specification for Electric Motors |  |  | Motor specifications will be based on previous supplied nitrogen compressor package |  | Please issue the documents separately and do not refer to the previous project |  |  | Document not received, for this reason previous reply is still valid.
A.18 | Each utility, drain, vent and any other auxiliary piping shall be single manifold and have tie-in point at the edge of base plate, equipped with a block valve. Each tie-in point shall be flanged, using RF-WN flanges. Required activities and/or material for distribution of the auxiliary lines within the confines of base plate such as piping, fitting, supporting and are in vendor scope of supply. |  |  | Confirmed |  | Noted |  |  | Closed
A.19 | Design code for all equipment, including Compressor, coupling, motor, gear..., shall be specified in proposal, to be considered, all equipment shall be deigned based on mentioned STD in project documents, otherwise shall be mentioned in deviation list with justification. If this deviation did not mention in bid stage, bidder shall follow project requirement without cost and time impact. |  |  | Technical details as per provided offer. Kindly note that compressor configuration will be similar to supplied nitrogen compressor package. |  | Please issue the documents separately and do not refer to the previous project |  |  | Refer to offer for technical details.
A.20 | Please confirm suitability of utility characteristics available at site as per project documents, especially for cooling water. Any further regulation may be required, shall be part of vendor scope. |  |  | Power supply and cooling water details mentioned in project process datasheet are confirmed. |  | Noted |  |  | Closed
A.21 | Prototype equipment hasn’t been acceptable and equipment shall be validated for similar power rating, speed, mechanical design, materials, compared to at least two units produced by the vendor at the proposed manufacturing plant. These units must have had at least two years' satisfactory operation. |  |  | Confirmed |  | Noted |  |  | Closed
A.22 | Any exception or deviation out of this deviation list will not be accepted after P.O and any claim / cost impact / time delay will not be accepted from Vendor. |  |  | Confirmed |  | Noted |  |  | Closed
A.23 | Please submit signed letter of conformity and deviations from other MR attachments. Otherwise full vendor compliance shall be assumed. |  |  | Please refer item A.1 |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Refer to item A1
A.24 | It has been assumed that MRQ doc. No. “L02-RE-MRQ-86-037-1” with all its attachments has been received by vendor and will be followed by vendor in detail design (after P.O.) except items which has been clearly stated in deviation list |  |  | Please refer item A.1 |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Refer to item A1
A.25 | Document after P.O. shall be provided based on project material requisition. |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | As per above MR is not yet received, for this reason previous reply is still valid.
A.26 | All document and drawing shall be based on “English”. |  |  | Confirmed |  | Noted |  |  | Closed
A.27 | Catalogue for all of sub equipment and instrumentation shall be submitted. |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Please attach the documents separately and do not refer to the previous project |  |  | Document supply as per offer supplier data register.
A.28 | 1-Vendor shall submit Sub-Vendor List for each component within the package including country of origin in Bid stage. 2-Subvendor list shall be selected based on project approved vendor list. |  |  | Subvendor list which is approved for previous supplied nitrogen compressor package will be followed. |  | Noted |  |  | Closed
A.29 | Vendor to submit his reference list. Reference list shall include compressor type, flow, discharge pressure, power, material, project name, client company and installation year. |  |  | Please find attached |  | Noted |  |  | Closed
A.30 | List of required special tools used during package installation and dismantling shall be provided. Special tools list shall be separated for compressor, seal, gear box, cooler, pumps etc. To be considered, Bidder responsible to supply all special tools for installation, lifting, pre-commissioning, commissioning, maintenance etc and any loss device for aforementioned stage, bidder shall be supplied without any cost and time impact. |  |  | Special tools are not required for offered equipment |  | Noted |  |  | Closed
A.31 | In addition to above item, the special tool list shall include, as minimum, rotor bundle removal unit with extension rails, hydraulic wrench for compressor barrel bolts, nitrogen pre-charge kit for oil accumulators, alignment tool. (if applicable) |  |  | Not applicable |  | Noted |  |  | Closed
A.32 | List of spare parts for pre-commissioning, commissioning, startup and 2 years shall be submitted according to instruction requested in project MR. Any other required spare parts, based on Vendor's recommendation, shall be added to spare part list. Responsibility of shortage of erection, commissioning and start-up spare parts will be in scope of Vendor. Hint: the spare part list shall include all equipment within the package (compressor, cooler, pumps (if applicabkle), etc.) |  |  | Please refer to Airpack offer for recommended spares for start-up/commissioning and 2-yr operation. |  | Noted |  |  | Closed
A.33 | Lubricants for commissioning & first fill shall be supplied by vendor, please confirm. |  |  | Confirmed |  | Noted |  |  | Closed
A.34 | Bidder shall fill out the table for scope of supply and work in Material Requisition and return the completed template with revised proposal. |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Please issue the documents separately and do not refer to the previous project |  |  | As per above MR is not yet received, for this reason previous reply is still valid.
A.35 | Bidder shall signed and stamped all page of project material requisition and attached to revised proposal |  |  | References and document priority to be covered in purchase order document (same as nitrogen compressor package). |  | Please follow our comment and do not refer to the previous project |  |  | As per above MR is not yet received, so at this moment this is not possible.
A.36 | Bidder shall submit filled project data sheet at this stage. |  |  | Detailed datasheet will be provided after order, during detail engineering stage (containing same information as the previous supplied nitrogen compressor package). |  | Noted |  |  | Closed
B. CODES STANDRDS AND REGULATION
B.1 | Please send us your deviation from standards which has been mentioned in MRQ or referred to project specification |  |  | Please refer item A.1 |  | Please follow our comment and do not refer to the previous project |  |  | Refer to item A1
B.2 | Please specify design code for: -Compressor -Lubrication System -Oil pump -Water pump -Heater -Cooler -Filter |  |  | Airpack manufacturing standard, suitable for use in oil&gas industry. Package configuration/design will be based on previous supplied nitrogen compressor package. |  | Please follow our comment and do not refer to the previous project |  |  | Airpack manufacturing standard, suitable for use in oil&gas industry is considered.
C. SCOPE OF WORK AND SUPPLY
C.1 | Requirement of access ladder and platforms shall be studied and designed/supplied by vendor, in case required. Please confirm your compliance and clarify requirement. |  |  | Not required |  | Noted |  |  | Closed
C.2 | In case of multi-skid configuration, interconnecting piping system (including supporting) shall be designed and supplied by vendor. Please confirm. |  |  | Not applicable, all items are installed on a common skid. |  | Noted |  |  | Closed
C.3 | Utility distribution around compressor unit shall be part of vendor scope (including additional adjustment may be required). Please confirm. |  |  | Confirmed |  | Noted |  |  | Closed
C.4 | Please clarify requirement of spreader beam for compressor units erection. In case recommended, certified beam complete with suitable shackles and wires (connecting skid/equipment to beam) shall be part of vendor scope. Please confirm. |  |  | Not required. Package will be provided with four-point lifting frame, suitable for single point lifting. Same as the supplied nitrogen compressor package. |  | Noted |  |  | Closed
C.5 | Please clarify requirement of hydraulic bolt tensioning device for proposed compressor units (it is not included in proposed special tools ) |  |  | Not required |  | Noted |  |  | Closed
C.6 | Please recheck and clarify requirement of winterization and heat tracing for proposed compressor units. In case of requirement within compressor package boundary, it shall be designed and supplied by vendor. |  |  | Not required |  | Noted |  |  | Closed
C.7 | Please recheck and clarify insulation requirement for proposed compressor units. Where required, insulation design, supply of applicable supports/clips, and provision of MTO shall be part of vendor scope. Supply of insulation material within skid limits shall be also by vendor. Please confirm. |  |  | Not required. Personnel protection (guard) will be provided for hot parts. Same as supplied nitrogen compressor package. |  | Noted |  |  | Closed
C.8 | PDIT for suction strainer to be considered in scope of supply |  |  | Noted, will be included. |  | Noted |  |  | Closed
D. PROCESS
D.1 | All Notes in Process Data sheet to be reviewed and confirmed, Otherwise deviation shall be submitted in deviation list. |  |  | Please refer item A.1 |  | All notes in our datasheet shall be confirmed by vendor |  |  | Confirmed
D.2 | Utility consumption list shall be included in technical offer. For utility summary, cooling water demand and oil consumption to be replied. |  |  | Utility consumption list will be provided during detail engineering stage. |  | Noted |  |  | Closed
D.3 | Bellow mentioned document shall be submitted (A.P.): 1- Preliminary Control philosophy 2- Preliminary Shutdown philosophy |  |  | Will be provided during detail engineering. Note it will be similar to control philosophy of supplied nitrogen compressor package. |  | Please issue the documents separately and do not refer to the previous project |  |  | These documents will be available during detail engineering.
D.4 | -Equipment with tag number and description to be reported with their impotent specification. (project numbering System shall be followed) - Preliminary Line size to be specified. -Control Signal to be shown. - Any special design consideration to be reported in the PID as a note. -Figure of control system to be rechecked by project legend. -Vendor to confirm symbol and legend PID of the project to be followed. (or strictly state that vendor's internal symbol and legend will be used. in this case such symbol and legend shall be issued during bid stage for check and approval by purchaser.) |  |  | Same symbols and legends will be applied as for the supplied nitrogen compressor package. |  | Noted, Please issue and follow the documents separately and do not refer to the previous project |  |  | Noted, during detail engineering PID legend will be considered.
D.5 | Requirement of automatic depressurizing to be clarified by vendor. All required facilities shall be considered by vendor. |  |  | Confirmed. Will be clarified in the package control philosophy. |  | Noted |  |  | Closed
D.6 | Vendor to specify required instrument for safe and reliable operation if any. |  |  | Instrumentation for safe and reliable operation is included. |  | Noted |  |  | Closed
D.7 | Only one tie-in per utility will be provided at package B.L. Distribution of the utilities inside the package will be in vendor’s scope. To be confirmed. |  |  | Confirmed |  | Noted |  |  | Closed
D.8 | All hydrocarbon drains inside vendor B.L shall be manifold by vendor and there is only one tie in with purchasers. |  |  | Confirmed |  | Noted |  |  | Closed
D.9 | All the tie in points (utilities and vents/drains) on all of the vendor PIDs, shall be equipped with one block valve for isolating which would be in vendor scope of supply. |  |  | Confirmed |  | Noted |  |  | Closed
D.10 | Line list document to be submitted (After P.O) |  |  | Confirmed |  | Noted |  |  | Closed
D.11 | Reported information for site data should be reviewed and corrected based on project documents. For instance Elevation, etc. |  |  | Confirmed |  | Noted |  |  | Closed
D.12 | Cooling water condition in the plant based on project document to be considered as below Cooling water temperature supply /return Temperature: 42/52 °C Cooling water pressure supply: 8 barg (normal) Maximum ∆P for cooling water consumers : 1.5 bar In case , vendor requires other condition for utilities different from data specified in project document , all facilities will be in vendor scope of supply |  |  | Confirmed |  | Noted |  |  | Closed
E. MECHANICAL
E.1 | Please recheck the nameplate power for compressor. Please specify rated power for PSV (Project recommended set pressure) and motor power shall be 10% over this value. Compressor motor shall be suitable for startup of settle out condition. |  |  | Confirmed |  | Noted |  |  | Closed
E.2 | Compressor MAWP shall be selected based on this PSV setting. Motor power shall be selected based on absorbed power of compressor at PSV set pressure with 10% margin. Hydrotest shall be 1.5xMAWP. Helium leak test shall be 1xMAWP. |  |  | Confirmed, except for helium leak test which is not performed. |  | Noted |  |  | Closed
E.3 | Based on project material requisition, after and inter cooler shall be supplied by bidder, so related data shall be indicated at this stage. |  |  | Intercooler is included. Aftercooler is not included since discharge temperature is below 100°C (as required in process datasheet). |  | Noted |  |  | Closed
E.4 | For compressor, outlet temperature shall not be greater than project requirements. If so, please consider after cooler with all accessories if necessary. |  |  | Confirmed, it is below 100 °C as required in process datasheet |  | Noted |  |  | Closed
E.5 | V-belt drivers are generally not acceptable. |  |  | Not, direct drive will be considered in revised offer. |  | Noted |  |  | Closed
E.6 | Please specify minimum pressure required for operation cylinder unloader valves. To be considered, Required pressure as per project documents and any regulation will be provided by vendor. |  |  | Pressure reducer valve for instrument air supply is included. |  | Noted |  |  | Closed
E.7 | To be considered, Required pressure as per project BEDD and any regulation will be provided by vendor. |  |  | Pressures mentioned in process datasheet are considered and mentioned in Airpack offer. |  | Noted |  |  | Closed
E.8 | Package base plate shall be provided by vendor with anchor bolt, nut, shims, jack screw and etc. |  |  | Confirmed, will be provided. |  | Noted |  |  | Closed
E.9 | Crankcase rapid pressure relief device shall be considered by vendor |  |  | Not applicable. Crankcase is provided with breather (atmospheric pressure). |  | Noted |  |  | Closed
E.10 | As per client request, non-spark coupling guard shall be as per annex H of API 671. Also non-spark guard for fly wheel shall be considered. |  |  | Non-sparking coupling guard will be provided. |  | As per client request, non-spark coupling guard shall be as per annex H of API 671. Please Confirm |  |  | Noted, will be considered in revised offer.
E.11 | Piping and supports between all consoles and compressor unit shall be supplied by bidder (if applicable) |  |  | Confirmed within package battery limits |  | Noted |  |  | Closed
E.12 | Barring device shall be electric motor type for all compressors. If need. |  |  | Not required for offered compressor |  | Noted |  |  | Closed
E.13 | As per client request, BkW VS. suction pressure curves shall be provided after P.O. |  |  | Confirmed |  | Noted |  |  | Closed
E.14 | Settle out gas pressure shall be specified after P.O. based on client P&ID and piping isometrics. |  |  | Confirmed |  | Noted |  |  | Closed
E.15 | Please be noted that ASTM material shall be used. |  |  | Generally confirmed. In case of compressor parts/interals european EN equivalent might be applied. |  | Noted |  |  | Closed
E.16 | Cylinder and liner shall have same material code, please mention. |  |  | Will be provided during detail engineering. |  | Noted |  |  | Closed
E.17 | All safety valves and thermal relief valves shall have by-pass with valve. all safety valves and thermal relief shall have downstream upstream L.O. full bore ball valve. |  |  | Dual PSV's with interlock valve are included (same configuration as per supplied nitrogen compressor) |  | Please confirm our comment and do not refer to the previous project |  |  | Dual PSVs with interlock are considered.
E.18 | Provide visual flow indicator on cooling water outlets with isolation valve. |  |  | Flow gauge (VA type) will be considered on cooling water return line |  | Noted |  |  | Closed
E.19 | If gear lube oil unit is independent from compressor lubrication system, it shall be equipped with same auxiliaries, protections and instruments as specified for compressor lubrication system. |  |  | Not applicable |  | Noted |  |  | Closed
E.20 | Please specify crank shaft material. Crankshaft shall be made single piece, heat treated forged material. Please confirm and revise offer. |  |  | Cast iron |  | Crankshaft shall be made single piece, heat treated forged material. |  |  | As per manufacturer std, this cannot be changed.
E.21 | Crosshead shoes shall be replaceable. |  |  | Not applicable |  | Noted |  |  | Closed
E.22 | Please specify distance piece MAWP and material |  |  | During detail engineering |  | Noted |  |  | Closed
E.23 | Please provide preliminary utility list of motor, heater, cooling water consumption |  |  | Utility consumption list will be provided during detail engineering stage. Motor rating can be found in Airpack offer. |  | Noted |  |  | Closed
E.24 | Please specify ASTM number for pulsation dampers. |  |  | A 516 Gr 60 |  | Noted |  |  | Closed
E.25 | please specify lifetime for wear parts and guaranteed values. |  |  | During detail engineering |  | Noted |  |  | Closed
E.26 | Please consider forged material for piston rod and revise material. Please specify detail of wear resistant coating on piston rod and its hardness. Materials of below items shall be mentioned: • Cylinder AND LINER • Piston • Piston RING AND WEAR BAND • Piston ROD. • Piston ROD COATING • Valve Seats. • Valve Guards. • Valve Discs • Crosshead Pin • Crosshead • Crosshead Shoes |  |  | Detailed datasheet will be provided after order, during detail engineering stage (containing same information as the previous supplied nitrogen compressor package). |  | Please consider forged material for piston rod and revise material. Materials of below items shall be mentioned: • Cylinder AND LINER • Piston • Piston RING AND WEAR BAND • Piston ROD. • Piston ROD COATING • Valve Seats. • Valve Guards. • Valve Discs • Crosshead Pin • Crosshead • Crosshead Shoes |  |  | As per manufacturer std, this cannot be changed.
E.27 | For oil and water pump: -Spacer type coupling and mechanical seal shall be foreseen. -Design pressure shall be at least equal to relief valve set pressure (for oil pump) and please specify design pressure for water pump. -Main material for aux and main pumps shall be specified -Preliminary flow, power and pressure shall be specified. |  |  | Not applicable Oil pump is mounted on compressor block and driven by crankshaft (same as supplied nitrogen compressor package). |  | Noted |  |  | Closed
E.28 | Please specify sizing of compressor for nitrogen case with specified value. Please submit compressor performance for all other operating conditions as specified in relevant data sheet (start up and catalyst regeneration, etc.) |  |  | Please refer to Airpack offer. Compressor sizing/design is based on values indicated in project process datasheet. |  | Please submit compressor performance for all other operating conditions as specified in relevant data sheet (start up and catalyst regeneration, etc.) |  |  | The worst conditions are considered in the offer.
E.29 | -BkW vs. suction pressure curves, rod load / gas load charts and speed / torque curve data also shall be provided after P.O. -For gas force, mass force and combined rod load, please consider that calculation shall be based on lowest suction pressure and relief valve set pressure. Also loads shall be shown for CES and HES separately. Mentioned curves shall be completed after P.O. |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Please confirm our comment and do not refer to the previous project Any deviatin too be specified. |  |  | Document supply as per offer supplier data register.
E.30 | Allowable vibration shall be guaranteed that The maximum allowable effective vibration velocity (Veff) measured on the cylinder end in any direction shall be less than 7.5 mm/s RMS. The allowable effective vibration velocity (V eff) = 4.5 mm/s RMS shall not be exceeded at the crankcase. The compressor BIDDER shall verify that excitations (gas side or mechanical stemming from the machine) do not cause impermissibly high amplitudes and stresses to the piping. Reference shall be introduced for velocity, safety margin shall be considered and indicated by vendor after lateral and tensional analysis between critical and rotational speed. |  |  | Noted |  | Noted |  |  | Closed
E.31 | All tie-ins shall be flanged complying with project PMS |  |  | Confirmed |  | Noted |  |  | Closed
E.32 | Bearing RTDs for vibration monitoring facility shall be Dual-Elements type. |  |  | Not available (in line with supplied nitrogen compressor package) |  | Noted |  |  | Closed
E.33 | scope of pulsation study and schedule for purchaser input to be agreed at later stage. Study shall be in full compliance with API 618 – Approach 2 - (with pre-study) and includes submission of detailed report. |  |  | Pulsation study acc. API design approach 1 will be provided. |  | Study shall be in full compliance with API 618 – Approach 2 - (with pre-study) and includes submission of detailed report. |  |  | Noted, will be included in revised offer.
E.34 | Actual rod loading shall not exceed 85% of allowable values |  |  | Noted |  | Noted |  |  | Closed
E.35 | Lube oil interconnecting piping shall be made of type 316L material. Please confirm. |  |  | Confirmed downstream oil filter (upstream will be as per mfr std) |  | Noted |  |  | Closed
E.36 | Please submit materials of construction for compressor accessories (including pulsation dampers, coolers, filters, valves, etc). |  |  | Detailed datasheet will be provided after order, during detail engineering stage (containing same information as the previous supplied nitrogen compressor package). |  | Material shal be in conformity with the revant standards and with owner's acceptance |  |  | Noted
E.37 | Please clear your points on project data sheet section of “NOTES”. Please mark “Confirmed” all project data sheet notes. |  |  | Detailed datasheet will be provided after order, during detail engineering stage (containing same information as the previous supplied nitrogen compressor package). |  | Please confirm our comment and do not refer to the previous project Any deviatin too be specified. |  |  | Comments if any will be included in detailed deviation list.
E.38 | Design pressure of compressors shall be as min. outlet PSV set pressure. |  |  | Confirmed |  | Noted |  |  | Closed
E.39 | Brass or cast iron safety relief valves and fittings are not permitted. All safety relief valves shall have flanged inlet and outlet connections |  |  | Confirmed |  | Noted |  |  | Closed
E.40 | Pulsation dampers shall be designed for full vacuum conditions. |  |  | Not applicable for offered compressor |  |  |  |  | Closed
E.41 | Suction pulsation suppression devices shall be designed for the same design pressure as the discharge pulsation suppression devices except when protected by a relief valve provided |  |  | Confirmed |  | Noted |  |  | Closed
E.42 | Friction bearings shall not be used for compressors and pressurized oil system shall be used. |  |  | Not applicable |  | Noted |  |  | Closed
E.43 | Separate control panel (PLC based) shall be considered for each compressor. Instrument shall be considered for MMS based on figure H.6 of API 670. or Vendor shall declare that MMS is not recommended for this package. |  |  | PLC based UCP is included MMS is not applicable |  | Noted |  |  | Closed
E.44 | MMS with monitoring and protection shall be considered, MMS for transmission of data and protection based on API 670 shall be considered. Following items shall be connected to MMS: -rod drop detector -vibration elements -key phasor -bearing and unloader valves temperature transmitter |  |  | MMS is not applicable |  | Noted |  |  | Closed
E.45 | Capacity control value shall be mentioned by bidder at this stage |  |  | Capacity control via recycle valve and bypass line (provided by others as per note in process datasheet) |  | Noted |  |  | Closed
E.46 | All inspection and test shall be done based on project ITP, but all inspection and test will be finalized during PIM and based on approved ITP. |  |  | Will be based on agreed ITP for nitrogen compressor package |  | Noted |  |  | Closed
E.47 | functional test for instrument and aux. system for compressor shall be done at shop. |  |  | Confirmed (during FAT) |  | Noted |  |  | Closed
E.48 | Common baseplate mounted compressor + gearbox + electromotor shall be supplied. Vendor to confirm. |  |  | Confirmed |  | Noted |  |  | Closed
E.49 | All loose items such as oil pumps, cooler etc.Shall be skid mounted. |  |  | Confirmed |  | Noted |  |  | Closed
E.50 | All internal piping, valves and fittings with their supports for cooling, sealing, purging, vent, drain and lubrication shall be provided and installed by bidder. Any auxiliary connection inside B.L shall be flanged type and extended up to the skid's boundary. |  |  | Confirmed |  | Noted |  |  | Closed
E.51 | If cooler, lube oil and seal system will be mounted on separate skids, the internal piping shall be fabricated and provided by vendor. Relevant Isometric drawing shall be provided after P.O. |  |  | Not applicable |  | Noted |  |  | Closed
E.52 | In order to provide access to all parts of package, Walkways, platforms, ladders & handrails shall be considered by Vendor. |  |  | Grating will be installed on areas where access is required. All items can be accessed from skid base level. |  | Noted |  |  | Closed
E.53 | Mating flange shall be supplied by Vendor if required. Please confirm. |  |  | Not required, all tie-in connections will be flanged ANSI RF. |  | Noted |  |  | Closed
E.54 | Minimum allowable Nozzle loads shall be min. twice the value specified in ANNEX F of API 617 8th edition. |  |  | Noted |  | Noted |  |  | Closed
E.55 | All tests and inspections requested in project data sheet, mandated in relevant STDs and project specifications for compressor, vessel, pumps, coolers, motor etc. shall be followed by vendor without deviation. |  |  | Will be based on agreed ITP for nitrogen compressor package |  | Noted |  |  | Closed
E.56 | Effects of variations in gas composition and inlet conditions shall be rechecked and considered by vendor in curves, compressor design, control and sizing. |  |  | Values indicated on process datasheet have been considered for compressor design. |  | Noted |  |  | Closed
E.57 | Bidder shall perform a field mechanical reliability and performance test of compressor package to demonstrate the mechanical integrity, operability and controllability of the package. Please confirm. |  |  | Confirmed (against daily rate) |  | Noted |  |  | Closed
E.58 | Coupling guards shall be supplied in accordance with API 671 shall be of non-sparking material. |  |  | Non-sparking coupling guard will be provided. |  | Noted |  |  | Closed
E.59 | Machine monitoring system shall be supplied for each machine in accordance with API 670 Std. MMS rack shall be integrated into vendors UCP. |  |  | MMS is not applicable |  | Noted |  |  | Closed
E.60 | Separate transmitters for control and trip shall be provided. The necessity of voting for shut downs to be clarified by vendor. |  |  | Noted, will be considered |  | Noted |  |  | Closed
E.61 | the Bidder shall review the purchaser's overall machine control system for compatibility with vendor-furnished control equipment. |  |  | Noted |  | Noted |  |  | Closed
E.62 | Each machine shall have its own lube oil system as per API 614, chapter 2. |  |  | Compressor is provided with shaft-driven lube oil pump, filter and cooler and forms part of the compressor assembly. Lube oil distribution lines are integral part of the compressor block. |  | Noted |  |  | Closed
E.63 | Fan Mist eliminator and oil purifier unit to be supplied by vendor. |  |  | Not applicable |  | Noted |  |  | Closed
E.64 | 1. For shaft sealing and seal system, dry gas seal as per API 692 shall be supplied. The arrangement shall be tandem dry gas seal with the intermediate labyrinth. 2. a separation seal is required to prevent leakage to the atmosphere or to the bearing housing. 3. Seal shall be supplied as cartridge type. Seal system including auxiliaries shall be as per API 692 and supplied by vendor. PID shall be submitted with next revision of proposal. |  |  | Not applicable for small size compressors |  | Noted |  |  | Closed
E.65 | As minimum alarms and shutdowns defined in API 692, part 10 and project data sheet shall be considered in seal system |  |  | Not applicable |  | Noted |  |  | Closed
E.66 | Piston diameters shall be less than 500 mm shall only be furnished |  |  | Confirmed |  | Noted |  |  | Closed
E.67 | If necessary to lubrication system, as minimum, full flow twin filters with transfer valve, differential pressure alarm and indication facilities. and compressor sump or the oil reservoir (if separately installed) shall be equipped with an oil thermometer. lubrication system shall be in accordance with Figure G‐5 API 618 latest edition as minimum. |  |  | Compressor is provided with single lube oil filter in line with supplied nitrogen compressor package. Refer preliminary P&ID for details on provided instruments. |  | Noted |  |  | Closed
E.68 | All ASTM equivalent material shall be mentioned by BIDDER if any other standard is followed by BIDDER and Gray cast iron shall not be used for compressor cylinders. |  |  | Detailed datasheet will be provided after order, during detail engineering stage (containing same information as the previous supplied nitrogen compressor package). Compressor cylinders will be cast iron as per OEM proprietary design and in line with previous supplied package. |  | Please be noted that , this package is segregated and completely independent to other supplied pakage ( nitrogen compressor) , so vendor is requested to reply all technical comments independtly |  |  | Detailed datasheet will be provided after order, during detail engineering stage. Compressor cylinders will be cast iron as per OEM proprietary design.
E.69 | All welding of pressure‐containing parts shall be subjected to 100% radiography |  |  | Will be based on agreed ITP for nitrogen compressor package |  | Noted |  |  | Closed
E.70 | Vendor shall be guarantee performance of compressor based on inlet liquid consumption and inlet gas shall be dry, so vendor will be check of need to add special items for preventing from condensing liquid. |  |  | Liquids are not allowed at the inlet of the package. |  | Noted |  |  | Closed
E.71 | Compressors shall be designed for full load continuous duty. They must be able to operate at the differential pressures consequent to vacuum operations and continuous duty in the range of the expected partial loads. The capacity at the normal operating point shall have no negative tolerance. Maximum acceptable positive tolerance is 3%. |  |  | Confirmed |  | Noted |  |  | Closed
E.72 | BIDDER shall also calculate the isentropic compression coefficient and indicate the gas state equations used for determination of gas parameters. |  |  | Noted |  | Noted |  |  | Closed
E.73 | ALLOWABLE SPEEDS The maximum compressor rated speed and the maximum average piston speed shall be limited to: and in non-lubricated compressor cylinders shall not exceed 3 m/s. |  |  | Confirmed |  | Noted |  |  | Closed
E.74 | BIDDER shall indicate calculated adiabatic discharge temperatures and expected discharge temperatures. Expected discharge temperatures shall be within API limits |  |  | Confirmed |  | Noted |  |  | Closed
E.75 | On each compression stage-discharge, control devices shall be installed to generate alarm and shutdown signals when the temperature rises above the maximum expected value (typically alarm for 20°C excess, shutdown for 25°C excess). |  |  | Confirmed |  | Noted |  |  | Closed
E.76 | The maximum actual rod loading shall not exceed 85% of the SUPPLIER’s maximum allowable continuous rod loading. |  |  | Noted |  | Noted |  |  | Closed
E.77 | Single acting, step piston and tandem cylinder arrangements shall not be furnished. Otherwise justification shall be mentioned here. |  |  | Confirmed |  | Noted |  |  | Closed
E.78 | Nominal and maximum torque values for all studs and bolting shall be included in SUPPLIER's documentation |  |  | Noted |  | Noted |  |  | Closed
E.79 | Minimum bearing life for operation under specified conditions shall not be less than 50,000 hours. |  |  | Confirmed |  | Noted |  |  | Closed
E.80 | Crankcases When the distance piece compartment adjacent to the crank case is gas tight, the crankcase shall be provided with relief devices to protect against rapid pressure rise. These devices shall incorporate downward directed apertures (away from the operator's face), a flame-arresting mechanism, and a rapid closure device to minimize reverse flow. The ratio of the total throat area of these devices to the crankcase free volume should be no less than 70 mm2/dm3 (3 in2/ft3). When not an integral part of the frame, crosshead housings shall be attached to the crankcase with studs. A metal-to-metal joint, prepared with suitable sealant, shall be used between the crosshead housing and crankcase, the crosshead housing and distance piece, and the distance piece and cylinder. |  |  | Not applicable |  | Noted |  |  | Closed
E.81 | Type B long single compartment distance pieces can only be used for Air or Nitrogen services. Either Type C: Long/long two compartments or Type D: Long/short two compartments distance pieces shall be used for all other services. So based on the item, bidder shall mentioned the exact type of distance peace. If there is any discrepancy with this phrase offer shall be revised. |  |  | Confirmed |  | Noted |  |  | Closed
E.82 | Each distance piece compartment shall be provided with a valve, plugged bottom drain connection and top vent connection for the Purchaser’s piping. |  |  | Confirmed |  | Noted |  |  | Closed
E.83 | The lube oil system shall include full flow twin filters with transfer valve. The compressor sump or the oil reservoir (if separately installed) shall be equipped with an oil thermometer. When the oil tank is separate, it shall be made of 316 L stainless steel. Lubrication system shall be in accordance with Figure G-5 as a minimum. |  |  | Duplicated point, refer E.67 |  | Noted |  |  | Closed
E.84 | Auxiliary oil pumps shall be electric motor driven and shall act as a pre-lubrication and post-lubrication pump, the operation of which shall be integrated into the compressor start sequence. The auxiliary lube oil pump driver shall be sized for the pump power and the required starting torque at an oil viscosity corresponding to the lowest ambient temperature. |  |  | Not applicable for offered compressor |  | Noted |  |  | Closed
E.85 | Oil coolers shall be provided to maintain the oil supply temperature at/or below 55°C |  |  | Confirmed |  | Noted |  |  | Closed
E.86 | Filter shall be dual flow with change over transfer valve, differential pressure alarm and indication facilities. |  |  | Compressor is provided with single lube oil filter in line with supplied nitrogen compressor package. Refer preliminary P&ID for details on provided instruments. |  | Noted |  |  | Closed
E.87 | Completely oil free delivery must be ensured under all conditions. Neither oil nor oil-mist may enter the process gas chambers in the machine during start-up, run-down, shut-down, full - and part – load operation. |  |  | Confirmed |  | Noted |  |  | Closed
E.88 | BIDDER shall recommend the lubricant specification |  |  | During detail engineering |  | Noted |  |  | Closed
E.89 | For each weld, the following documents shall be submitted to Purchaser for review: a. Welding procedure specification (WPS) b. Procedure qualification record (PQR) c. Welding map with reference for identification of welds and parts to be welded. Full details shall be included (weld design, sizes, materials, pre-heat and post-head treatments, etc).compressor cylinders. |  |  | Confirmed |  | Noted |  |  | Closed
E.90 | BIDDER shall give notice of any major component non conformity during fabrication. Non critical component small repairs, covered by existing and proved internal procedures, can be done without prior approval purchaser. A defect identification plan showing the type and the dimensions of scouring after defect removal shall also be submitted to purchaser. Welded or brazed repairs on cast iron components are prohibited. |  |  | Noted |  | Noted |  |  | Closed
E.91 | All welding of pressure-containing parts shall be subjected to 100% radiography. |  |  | Will be based on agreed ITP for nitrogen compressor package |  |  |  |  | Closed
E.92 | BIDDER shall consider full flow relief valve condition at the discharge and minimum suction condition for driver sizing. |  |  | Confirmed |  | Noted |  |  | Closed
E.93 | When several operating conditions are specified, BIDDER shall determine the worst case (operation and starting) for sizing accordingly the driver. Load on driver in case of operation of a compression stage against safety valve setting discharge pressure shall be evaluated. |  |  | Confirmed |  | Noted |  |  | Closed
E.94 | The compressor flywheel shall be designed in such a way that the maximum degree of irregularity of rotation speed at the most unfavorable operating point does not exceed 1:80. |  |  | Noted |  | Noted |  |  | Closed
E.95 | Unless otherwise specified or requested by SUPPLIER, electric motors shall be suitable for direct starting with the compressor pressurized but unloaded. The starting voltage shall be assumed as 80% of nominal voltage at motor terminals. The barring equipment shall be fitted on the compressor with limit switches supplied by the BIDDER for safety of equipment. |  |  | Confirmed Barring equipment is not included |  | Noted |  |  | Closed
E.96 | The couplings and adaptors must be balanced in accordance with ISO 1940/1 standard grade G-2.5 at maximum continuous speed independently of other rotating parts. |  |  | Confirmed |  | Noted |  |  | Closed
E.97 | separate gear unit shall comply with API Standard 677. When special purpose separate gear unit is applied, it shall comply with the following specifications/standards. - IPS-M-PM-300 - API 613 The minimum service factor shall not be less than 2. Gears with power transmission above 150 kW shall conform to API 613. |  |  | Not applicable |  | Noted |  |  | Closed
E.98 | Regarding cylinder unloader system, pneumatic signal and remote manual operation shall be applied, unless otherwise specified. Control logic diagram shall be recommended by the SUPPLIER. |  |  | Confirmed |  | Noted |  |  | Closed
E.99 | The compressor shall be supplied with all instrumentation, process, hydraulic and pneumatic tubing and piping, local interconnecting equipment and local panel(s), as required for the BIDDER to complete the mechanical installation, calibrate all instruments, test installation equipment, pre-commission loops, in order to enable the package to be commissioned ready for safe operation. The BIDDER proposed standard instrument types shall be subject to review and approval by purchaser. The BIDDER shall provide full details and Specifications of all instrumentation as part of the detailed package submission at the bid stage. The compressor is expected to perform efficiently with the minimum of operator intervention. |  |  | Confirmed. Engineering documents, datasheets and drawings will be submitted after order as part of detail engineering. |  | Noted |  |  | Closed
E.100 | Each piston rod of a horizontal compressor shall be provided with a non-contacting probe for rod run-out measurement. The probe shall be located in the distance piece on the packing case flange and shall be wired to an outside junction box where the proximity sensor is installed. |  |  | Not included for small size compressors. Same is in line with previous supplied nitrogen compressor package. |  | Noted |  |  | Closed
E.101 | An automatic loading-delay interlock shall be considered in the control logic diagram recommended by the vendor. |  |  | Confirmed |  | Noted |  |  | Closed
E.102 | The compressors shall always be started unloaded. If they are in automatic-starting service, they shall be equipped with automatic unloading devices. The BIDDER shall clearly indicate the maximum time the compressors can withstand unloaded operation. BIDDER shall state in the proposal the extent of unloading required for start-up. |  |  | Confirmed, will be mentioned in control philosophy. |  | Noted |  |  | Closed
E.103 | Each compressor control panel shall be designed to accommodate power supplies from AC UPS system for feeding control equipment. (such feeder will be supplied by purchaser) |  |  | Confirmed |  | Noted |  |  | Closed
E.104 | Local start-up panel/gauge board shall be provided by BIDDER for start-up and emergency operation only. It shall include start/stop/emergency stop buttons or switches and alarm/trip status annunciators. Required indicators for operation such as suction/discharge pressure temperature shall be recommended by BIDDER as per their design standard. Also fault annunciation and unloader control switch shall be also considered. |  |  | Confirmed |  | Noted |  |  | Closed
E.105 | Temperature detectors shall be 100 ohm, 3 wires, platinum RTD’s. Transmitters shall be used for all temperature measurement including bearing temperatures. All temperature transmitters shall preferably be head mounted type. Subject to Purchaser’s approval, junction box mounted type may be supplied in locations subject to high vibration. |  |  | Transmitters will be remote mounted, bearing temperature measurements are not possible. Same is in line with previous supplied nitrogen compressor package. |  | Noted |  |  | Closed
E.106 | All pressure gauges shall be of liquid-filled and equipped with adjustable snubber. Please confirm. |  |  | Confirmed |  | Noted |  |  | Closed
E.107 | Protective devices shall be furnished by the SUPPLIER. BIDDER shall recommend protection devices, in addition to listed devices in table 5 API 618 latest edition. Required local instrumentation/devices including junction boxes and wiring within skid or compressor frame shall be furnished by bidder. Bidder shall add the following alarms and shutdowns to table 5: - High lube oil outlet temperature alarm. - High jacket water outlet temperature alarm - Excessive cylinder jacket water temperature alarm and shutdown - High rod-drop “run-out” alarm |  |  | Included instruments as per preliminary P&ID attached. Note this is based on previous supplied nitrogen compressor package. |  | Please confirm owner's comment or submit a deviation list (if any) and do not refer to the previous project |  |  | Included instrumentation as per attached P&ID.
E.108 | For each compressor train this scope shall include, but not be limited to: - Bearing temperature sensors for compressor and drive motor - Vibration sensors and key phasor sensor (if recommended) - Monitors for bearing temperature, vibration and key phasor (if recommended) - Condition Monitoring Data Gathering System The overall high-level process control and safeguarding of the plant and equipment shall be performed by the Purchaser’s DCS and ESD System. However, local machine control and protection shall be provided by the vendor. |  |  | MMS is not applicable |  | Noted |  |  | Closed
E.109 | Provisions shall be made on all process gas compressors for installation of non-contacting proximity probe to measure the vertical run out of each piston rod. Contact type rod-drop detectors shall not be used. |  |  | Not possible on small size compressors. |  | Noted |  |  | Closed
E.110 | Pulsation suppression devices and temporary start up screen (to be installed just upstream of suction pulsation suppression device) shall be supplied by the SUPPLIER. |  |  | Confirmed |  | Noted |  |  | Closed
E.111 | Degassing vent lines shall be designed for the maximum cylinder end pressure. The design shall also ensure that leakage gas from piston rod seals or from possible gas breakout is safety carried off to avoid unacceptable pressure rises. |  |  | Confirmed as applicable |  | Noted |  |  | Closed
E.112 | Pulsation Suppression devices at suction and discharge side of each cylinder shall be supplied by the SUPPLIER |  |  | Confirmed |  | Noted |  |  | Closed
E.113 | The approach selected shall be approach 3, and the BIDDER shall supply pulsation suppression devices on suction and discharge of each stage. The BIDDER shall carry out and hand over to the Purchaser a complete acoustical and mechanical study, taking into account suction, discharge and inter-stage piping, as well as the compressor's upstream/downstream capacities. |  |  | Pulsation study acc. API design approach 1 will be provided. Note the size and length of piping spools is very limited inside the package and hence extensive study is not required. |  | Noted |  |  | Closed
E.114 | Design, manufacturing and test of pulsation dampener shall be done accordance to ASME Sec. 8, Div. 1. The internal portions of the welds shall be ground smooth. Where this is technically impossible, the first pass shall be made using TIG welding process. Connections to process piping, including inter-stage piping, shall be flanged. Machined and studded connections are not acceptable. |  |  | Confirmed |  | Noted |  |  | Closed
E.115 | The units, including integral auxiliary system packages, shall receive a 4-hour mechanical running test before shipment. |  |  | Confirmed (during FAT) |  | Noted |  |  | Closed
E.116 | Auxiliary equipment not integral with compressor such as oil coolers shall be subject to a functional test, 4 hour operational test and cleanliness verification as a subassembly in the SUPPLIER’s or sub-supplier’s shop if not used during a compressor running test. |  |  | Not applicable. All auxiliaries/coolers are mounted on the compressor assembly and will be subject to a complete package running test during FAT. |  | Noted |  |  | Closed
E.117 | BIDDER shall submit performance curves or tables and shall assume complete responsibility for design, engineering and manufacture of the compressor in such a way that it can provide the guaranteed capabilities in industrial service. This responsibility also extends to the specification of the parts and accessories supplied.. |  |  | Confirmed |  | Noted |  |  | Closed
E.118 | Rod-load and gas-load charts shall be furnished for the worst specified operating conditions and in case of operation of one cylinder against safety valve setting discharge pressure. |  |  | Confirmed |  | Noted |  |  | Closed
E.119 | The compressor shall be guaranteed for satisfactory performance at all operating conditions specified on the data sheet. |  |  | Confirmed |  | Noted |  |  | Closed
E.120 | The BIDDER shall guarantee the operating point for the rated case and performance of his equipment as defined in data sheet and/or specifications, during commissioning and for one year (12 months) operation starting from the date of completion of commissioning but not exceeding 18 months after the date of shipment against the following defects: - All operational defects. - All material defects. - All fabrication and design defects. |  |  | Confirmed |  | Noted |  |  | Closed
E.121 | All defective parts shall be replaced by the BIDDER in the shortest possible time, free of charge, inclusive of dismantling, reassembly at site and all transportation costs |  |  | Confirmed for items under package warranty |  | Noted |  |  | Closed
E.122 | The BIDDER shall warranty the provision of spare parts to the CONTRACTOR for a minimum period of 10 years from the date of dispatch. |  |  | Confirmed |  | Noted |  |  | Closed
E.123 | Below inspection and test shall be considered in scope of work: 1-sope inspection test 2-Hydrotest of Cylinder 5-Hydrotest of jacket 3-Heliom Test 4-Lube oil system(4hours) 5-Function Test 6-Mentioned inspection and test in API 618 |  |  | Will be based on agreed ITP for nitrogen compressor package |  | Please confirm owner's comment or submit a deviation list (if any) and do not refer to the previous project |  |  | Hydrotest fr cylinder and jacket will be performed. SAT against daily rates, package cannot be tested at Airpack, as it is a gas compressor.
E.124 | Below items shall be considered in scope of work: 1-Wiring and Tubing to Junction Box within package 2-Insulation and Personnel Protection 3-Piping within the Package 4-Painting • Prime Coats at Shop • Finish Coats at Shop 5-Packing and Marking • Export Packing • Rust Prevention • For Long Term (12 month) 6-Shipping and Transportation to point of delivery (according to delivery condition) 7-Supervision for installation (Per diem) 8-Supervision for erection, commissioning and start up (Per diem) 9-Shop and field training 10-Running test at site 11-Participation in HAZOP and SIL sessions in Purchaser’s office and implementation of HAZOP/SIL outcome 13-PIM (pre‐inspection meeting) 14-Lateral and critical speed analysis and unbalance 15-Review of Purchaser’s Drawings (Foundation, Piping, P&ID endorsement 16-Torsional analysis(If Need) 17-Certification 18-Export customs clearance 19-Obtain any export license or other official authorization for exportation 20-Vendor Shop Training for Client’s Personnel |  |  | Generally confirmed. Meetings held in Airpack office or with remote attendance (MS Teams or equivalent) are included in base. Attending meetings at Contractor office is available against daily rate. |  | Noted |  |  | Closed
E.125 | Cable trays including covers shall be provided with hot dip galvanized steel. |  |  | Confirmed, covers will be added in revised offer. |  | Noted |  |  | Closed
E.126 | Based on submitted technical proposal: Project data shall be followed based on "Ambient, site condition & utility data" |  |  | Confirmed |  | Noted |  |  | Closed
E.127 | Based on submitted technical proposal: Compressor speed and piston speed shall be specified. |  |  | Will be indicated in revised offer. |  | Noted |  |  | Closed
E.128 | Based on submitted technical proposal: Based on project data sheet, bidder area classification shall be based project document. |  |  | Zone 2, IIC, T3 |  | Noted |  |  | Closed
E.129 | Based on submitted technical proposal: All accessories shall be design based on standard that mentioned in project requisition. |  |  | As per Airpack offer |  | Noted |  |  | Closed
E.130 | Based on submitted technical proposal: All safety requirements shall be supplied by bidder. |  |  | Confirmed |  | Noted |  |  | Closed
E.131 | Based on submitted technical proposal: Electric motor starter shall be supply by vendor. |  |  | Motor starters are not included in Airpack scope of supply. This is normally part of plant MCC (by others). |  | Control power circuit to be submitted |  |  | During detail engineering.
F. CONTROL AND INSTRUMENT
F.1 | Vendor shall follow instrument and control specifications as stated in MR. In the event of any conflict between project specifications, data sheets, related standards, codes etc. client shall be consulted for clarification before Proceeding with procurement/engineering. The Package vendor shall not deviate from this specification without the prior written approval from the client. |  |  | Please refer item A.1 |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Refer to item A.1
F.2 | All electronic / electrical Instruments and equipment shall be suitable for area classification as per IEC codes and shall be certified by any recognized authority like FM, CSA, PTB, etc. as per ATEX guidelines etc. |  |  | Confirmed |  | Noted |  |  | Closed
F.3 | All software source and related license shall be delivered to owner(after PO) |  |  | Software is not included. Please note software with license was provided with supply of the nitrogen compressor. Same software program can be used for offered package since PLC make/model will be same. |  | Please be noted that , this package is segregated and completely independent to other supplied pakage ( nitrogen compressor) , so vendor is requested to reply all technical comments independtly . 1) all software source and related license shall be delivered to owner ( after PO) |  |  | Noted, laptop with software will be included in revised offer.
F.4 | package PLC shall have minimum SIL 3 rating for CPU. (for safety related loop digital I/O's shall also be SIL3 rated) |  |  | PLC will be simplex type and non-SIL. Power supply will be redundant. This configuration is same as supplied nitrogen compressor package. |  | the Hazop/SIL Study shall be down by vendor , control system shall meet requirment of SIL study report (Required SIL) |  |  | SIL is not considered, PLC is simplex only power supply will be redundant
F.5 | The following equipment shall be dual redundant: - Communication cards TCP/IP - CPU -Input/output Cards for closed control loops/interlocks - Power Supplies |  |  | Power supply will be redundant. Other components will be simplex type. This is in line with supplied nitrogen compressor package. |  | refer to reply F.4 , requirment of SIL study to be met (REDUNDANCY OF CPU R CARD..) as mentioned in reply F.3 , this package is independent to nitrogen package , please reply completely |  |  | CPU, PS and communication will be redundant in revised offer. Please not Ios will not be redundant, also no SIL is included.
F.6 | Vendor shall follow project tagging and numbering procedure for instrument, control system, panels and cables. |  |  | Confirmed |  | Noted |  |  | Closed
F.7 | Instrumentation JB's enclosure protection shall be IP65 as minimum. |  |  | Confirmed |  | Noted |  |  | Closed
F.8 | Communication protocol with plant DCS shall be based on redundant Modbus RS-485 |  |  | Confirmed |  | Refer to item F.5 , comunication to be modbus TCP/IP |  |  | Confirmed
F.9 | Material for PLC control panel(located on package skid) shall be 316SS suitable for location and explosion conditions. |  |  | Not applicable, PLC based UCP to be remote mounted (indoor, safe area) in line with previous supplied nitrogen compressor package. Local instrument junction boxes will be SS316, IP65 and Ex'e certified. |  | control panel in remote( indoor and safe) is confirmed. Local operation panel (start/ start / alarm..) to be predicted and provided also |  |  | Noted, LPS (local pushbutton station) will be included in revised offer.
F.10 | As a general rule, the following power supply will be available for each UCP: 1 x 230 VAC 50Hz power (from UPS for instrumentation purpose as PLC, ...). The 230 VAC feeders shall never be paralleled. |  |  | Confirmed |  | please be noted that the control panel will be energized by plant UPS ( 120VAC) , also one 230VAC will be provided for lighting , fan.. Of panel |  |  | Confirmed
F.11 | The ‘SMART’ type transmitters supported by ‘HART’ protocol, based on 4-20mA 24VDC, shall be used for all electronic transmitters. |  |  | Confirmed |  | Noted |  |  | Closed
F.12 | Local Panel shall be preinstalled on the skid with all critical lamps and indicators. |  |  | Confirmed for local panels, also refer item F.9 |  | Noted |  |  | Closed
F.13 | All instruments shall be intrinsically safe type with following requirements: -All intrinsic safety barriers shall be active type isolating barriers only. -Barriers must be selected based on entity concept. Cable parameters shall also be considered while matching entity parameters.(cable parameters and distance will be informed to vendor during detail engineering stage after PO). |  |  | Noted, will be considered in revised offer. |  | please submitt instrument vendor list , instrument summery list in your offer |  |  | Please find attached Airpack preferred vendor list.
F.14 | The mapping list shall be submitted in purchaser format after PO and detail design. |  |  | Confirmed |  | Noted |  |  | Closed
F.15 | The scope of work and supply of hookup materials within the package is in vendor responsibility. |  |  | Confirmed |  | Noted |  |  | Closed
F.16 | Instruments, junction boxes and local panels which are part of the skid or Package shall be preinstalled by vendor. The cables for instruments shall also be appropriately glanded (and terminated) at both ends by vendor. |  |  | Confirmed |  | Noted |  |  | Closed
F.17 | Air supplies for field mounted instruments and the local control panels (if applicable) shall be provided from a single main air header connection (provided by client) at one location). The Vendor shall provide all necessary sub-headers and branches required to feed each instrument or machine internal to the packaged equipment skid. |  |  | Confirmed |  | Noted |  |  | Closed
F.18 | All Special cables shall be supplied by bidder |  |  | Not applicable |  | Noted |  |  | Closed
F.19 | Please submit the following items in next clarification round for our review: 1.Preliminary UCP power consumption. 2. preliminary list of manufacturer & type of instruments(instrument list) & detectors per comp package. |  |  | 1. Approx 1.5 kW 2. During detailed engineering. |  | 1) Noted 2) subvendor list and instrument summerry list to be submitted in bidstage 3) brand of PLC and configuration to be submitted |  |  | 2. Please find attached 3. Siemens
F.20 | The housing material all instruments shall be 316ss. |  |  | Confirmed |  | Noted |  |  | Closed
F.21 | All instruments shall be ‘’IS’’ type ,in case of unavailability Eexd type shall be used. |  |  | Confirmed, will be considered in revised offer. |  | Noted |  |  | Closed
F.22 | If PLC includes safety related functions then shall comply with IEC61508/61511 and all safety related functions shall be implemented with SIL3 certified I/O modules, CPU, I/O bus and communication processor modules. |  |  | Refer item F.4/F.5 |  | refer to reply F.4 , SIL study to be down by vendor and requirments of SIL study to be met |  |  | Refer to F4
F.23 | Vendor shall review client P&IDs and comment if any, all required interface signals between vendor control system and client DSC/ESD system shall be clearly specified by vendor. |  |  | Noted |  | Noted |  |  | Closed
F.24 | The UCP’s design shall be based on a fail-safe concept for safety related signals. |  |  | Confirmed |  | Noted |  |  | Closed
F.25 | Instrument tubing and fitting shall be 316L/316 SS material |  |  | Confirmed |  | Noted |  |  | Closed
F.26 | Sunshade shall be provided for local panel |  |  | Noted, will be considered |  | Noted |  |  | Closed
F.27 | All instruments shall be selected from West European/ North American/ Japan/ Korea manufacturer. Please consider. |  |  | Confirmed |  | subvendor list to be submitted |  |  | Please find attached Airpack preferred vendor list.
F.28 | All temperature transmitters shall be head mounted(4-20mA) .direct connection of T/E’s to UCP is not allowed except for MMS system elements. |  |  | Remote mounted transmitters will be applied to avoid transfer of vibrations. |  | Noted |  |  | Closed
F.29 | Please provide Instrumentation and control system spare parts (commissioning and 2 years). |  |  | Not required for two years. Recommended list already included in the offer as option. |  | Noted |  |  | Closed
F.30 | Voting for alarm and trip to be provided as required. |  |  | Not required. |  | Noted |  |  | Closed
G.SAFETY & HSE
G.1 | Hazardous Area Classification Gas Group IIB Temperature Class T3 Zone 2 shall be considered |  |  | Confirmed |  | Noted |  |  | Closed
G.2 | HAZOP and SIL study will be held by Contractor through Third Party with attendance of Vendor representative(s). Vendor attendance at this HAZOP & SIL review meeting has to be included in Vendor scope of supply. Any change results of HAZOP & SIL review meeting shall be at Vendor care and cost unless vendor can convince technically HAZOP & SIL chairman. Vendor shall confirm. |  |  | Included with remote attendance (MS Teams or equivalent). Attending at Contractor office is possible against daily rate. |  | Noted |  |  | Closed
G.3 | "Noise Data Sheet" including "Sound Power Level" and "Sound Pressure Level" shall be specified for octave bound range. |  |  | Noise data sheet will be provided |  | Noted |  |  | Closed
G.4 | In this stage vendor shall guarantee that the noise level at distance of 1 meter form whole compressor package shall not exceed more than project requirements. Any sound reduction measurement (and all necessary accessories) to meet the above mentioned sound limit shall be designed and supplied by vendor. Please confirm. |  |  | < 85 dB(A) at 1m from skid edge |  | Noted |  |  | Closed
H. ELECTRICAL
H.1 | Any deviation from project documents shall be clearly specified to check by purchaser, otherwise, bidder shall follow all requirements of project without any cost and time impact |  |  | Please refer item A.1 |  | Material Requisition of this project shall be followed as a reference for vendor Please follow our Comments |  |  | Refer to A.1
H.2 | Catalogue and data sheet for motors and other electrical equipment (if any) shall be sent to review. |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Noted |  |  | Closed
H.3 | Motors and other electrical equipment(if any) shall be supplied from project approved vendors(AVL). |  |  | Subvendor list which is approved for previous supplied nitrogen compressor package will be followed. |  | Noted |  |  | Closed
H.4 | Commissioning/start-up spare parts for motors and other electrical equipment (if any) shall be specified. |  |  | Not applicable, recommended spare are already in the offer, please refer to offer. |  | Noted |  |  | Closed
H.5 | Execution of motors and other electrical equipment shall be selected based on area classification requirements and according to MR and it's attachments |  |  | Confirmed (Zone 2, IIC, T3) |  | Noted |  |  | Closed
H.6 | On skid cabling from interface junction boxes to motor terminal box shall be done by vendor(or cable race way from motor terminal to package battery limit shall be provided by vendor). |  |  | Cable tray from skid edge up to motor terminal box will be provided. Cabling from plant MCC to motor terminal box by others at site. |  | Noted |  |  | Closed
H.7 | Motor sizing shall be checked to be de-rated as per plant ambient temperature. To be considered, motor shall be designed based on Max. ambient Temp. and this issued shall be marked in motor nameplate power( ** Kw @ Max. Ambient Temp.) |  |  | Confirmed |  | Noted |  |  | Closed
H.8 | Commands from package control panel to MCC and from MCC to package control panel shall be hard wire. (IF APPLICABLE) |  |  | Confirmed |  | Noted |  |  | Closed
H.9 | The noise level of the motor shall not exceed the limits specified in IEC 60034-9. The noise level of the complete equipment consisting of the motor and the driven equipment shall be limited to the values specified in project specification. |  |  | Confirmed |  | Noted |  |  | Closed
H.10 | Voltage and frequency variation design for all electrical devices shall be in accordance with project specification |  |  | Confirmed |  | Noted |  |  | Closed
H.11 | the starting current of MV/LV motors shall not exceed 6/7 times the nominal current respectively. |  |  | Confirmed |  | Noted |  |  | Closed
I. PIPING
I.1 | All stress analysis and supporting inside compressor / package to be done by vendor. |  |  | Not required considering the small line sizes and lengths inside the package battery limits. |  | Noted |  |  | Closed
I.2 | Dynamic analysis and piping support checking to be done by vendor as per piping isometrics. |  |  | Not required considering the small line sizes and lengths inside the package battery limits. |  | Noted |  |  | Closed
I.3 | For compressor with internal piping in vendor scope , all compressor nozzles loads combination checking for balance evaluation to be done by vendor with considering piping allowable loads as per compressor MR . |  |  | Not required considering the small line sizes and lengths inside the package battery limits. |  | Noted |  |  | Closed
I.4 | All tie-in point with piping shall be flanged-type and considered at the edge of the skid. |  |  | Confirmed |  | Noted |  |  | Closed
I.5 | 3D model compatible with PDMS such as STP file to be submitted by vendor. (after PO) |  |  | Confirmed |  | Noted |  |  | Closed
I.6 | Insulation MR to be issued by vendor for supply by piping. Isometric of insulated lines need to be submitted as well. |  |  | Personnel protection will be provided for hot parts. No insulation required. |  | Noted |  |  | Closed
I.7 | Please implement nozzle table detail (discharge/suction…). |  |  | Will be included on GA drawing |  | Noted |  |  | Closed
I.8 | Flange size and rating shall be defined as per ASME B16.5. |  |  | Confirmed |  | Noted |  |  | Closed
I.9 | Vendor has to follow the attached latest PID in her scope of supply/work. Furthermore, Discharge Non Slam Check Valve is in vendor Scope of supply/work. |  |  | Check valve is included. Refer preliminary P&ID for details. |  | Noted |  |  | Closed
I.10 | Vendor has to consider a common header for each of the Utility services and drain lines inside package, in order to have just one Tie-In point for each service at battery limit of package |  |  | Confirmed |  | Noted |  |  | Closed
I.11 | Access way& maintenance area to different units of compressor package to be shown in the general arrangement drawing. |  |  | Confirmed, as applicable |  | Noted |  |  | Closed
J. CIVIL & STRUCTURE
J.1 | Following information shall be supplied for foundation design after PO. Vendor to confirm. 1- An arrangement drawing showing overall dimension of the required concrete support for machines, with location and size of opening, holes, pads, anchor bolts and relevant pocket sizes. 2- A layout showing location of auxiliary equipment and miscellaneous, piping supports and service platform legs. 3- The operating speed range of each machine. 4- The shaft position, both in plan and in elevation. 1- Weight and center of gravity for every machine and base plate. 2- Weight and Centre of gravity of each rotating mass ( for rotating machinery only ) 3- Dynamic loads to be used for calculation of amplitude of vibration of the foundation 4- Static loads acting along anchor bolts axis. Short circuit moment |  |  | Document supply will be based on previous supplied nitrogen compressor package. |  | Please be noted that , this package is segregated and completely independent to other supplied pakage ( nitrogen compressor) , so vendor is requested to reply all technical comments independtly |  |  | Document supply as per offer supplier data register.
K.MATERIAL & QC
K.1 | BIDDER to confirm all Welding/NDT requirements, lining/cladding, and corrosion monitoring systems shall be performed in accordance with project specifications. |  |  | Welding will be done based on approved welding procedures of previous supplied nitrogen compressor package. |  | Please be noted that , this package is segregated and completely independent to other supplied pakage ( nitrogen compressor) , so vendor is requested to reply all technical comments independtly |  |  | Welding will be done based on third party approved welding procedures.
K.2 | Required inspection and tests shall be fulfilled by all involved parties as per QCP/ITP. BIDDER to Confirm. |  |  | Will be based on agreed ITP for nitrogen compressor package |  | Noted |  |  | Closed
K.3 | The hardness of parts, welds and heat-affected zones shall be verified as being within the allowable values through testing. The method, extent, documentation, and witnessing of the testing shall be agreed upon by Purchaser. Hardness test for sour service shall be done in accordance with NACE MR0175/ISO15156. BIDDER to Confirm |  |  | Not applicable, no sour service. |  | Noted |  |  | Closed